## Slide 1
The Kampala Jinja Expressway

## Slide 2
The Kampala Jinja Expressway and the Chinese dragon: a soap opera

## Slide 3
Key EU Infrastructure Projects in Uganda

## Slide 4
The project
77km
18km

## Slide 5: Key features
PPP for Design Build Finance Operate Transfer (DBFOT)
30 years concession
Tolled road (closed and open toll)
Availability payment model
  Gov keeps the traffic risk
  Gov sets the tolls
  Gov keeps all revenues minus availability payment + penalties
  Private sector keeps other risks: financing, design, construction, operation, maintenance.
Significant environmental & social challenges
  2% of Kampala population relocated - mainly in slums
  E&S safeguards to international standards

## Slide 6: Proposed financing

## Slide 7: Main Milestones Government of Uganda
2011-2014: first technical and E&S studies for an EPC contract
2014: IFC comes as transaction adviser to structure the PPP
Sept 2015: Investor conference
2015: Adoption of PPP Act
2015/2017: feasibility study + revision of the E&S studies to reach IFC standards
Dec 2017: Feasibility study approved by PPP committee (necessary to launch the procurement process): decision taken to go for the PPP option
May 2018: Invitation for pre-qualification
2018: Formal request for funding to DFIs (AFD and AfDB) for Viability Gap Funding
Dec 2018: 4 consortia qualified
Sept 2019: project ready to launch the Request for Proposal (RfP)

## Slide 8: Main Milestones EU/AFD
2015: first interaction with IFC and UNRA
April 2016: Identification mission AFD
January 2017: EC Decision to transfer EUR 60 million from the NIP to the AIP (this will be completed by EUR 31.05 million from RIP)
2017: Capacity building to UNRA on E&S
2017-2018: long discussion with stakeholders on the structure and E&S issues
Oct 2018: AIP Board
Nov 2018: AFD board
Dec 2018: Signature of PAGoDA with AFD
May 2019: EUR 2 million additional for Resettlement and livelihood restoration in two major slums on the alignment
2019: support to additional studies on E&S, support to finalisation of the RfP

## Slide 9: PPP Procurement

## Slide 10: Prequalification
Consortia qualified in December 2018: 4 out of 8 bidders
China Communications Construction Company/China First Highway Engineering Company Ltd from China (China),
KJ Connect: Vinci Concession/Vinci Highways/Mota Engil/Sogea Satom/Meridiam (France, Portugal)
Strabag/Ictas/Egis/AIIF3/STOA (Austria, Germany, Turkey, France, Poland),
CCKS: China State Construction Engineering Corporation Ltd, Wu Yi Co. Ltd (China, Korea)
Consortia not qualified
Enkula Expressway (South Africa, Uganda and Saudi Arabia)
Chang Chyi Enterprise Company Limited and China Railway Construction Investment Group Company Ltd (China)
Sharpoorji Pallonji (India)
Tecnasol Luisa Goncal SA (Portugal)

## Slide 11: PPP Financial highlights
Net Benefits | USD 2.73 Bn
Gov Expenses (Availability payment + loans) | USD 2.29 Bn
Gov Revenues (tolls + taxes) | USD 5.02 Bn
Total net benefit for Uganda over 30 years: USD 2.73 Billion
  around USD 100 million/year for the Government
Break-even point 9.5 years after start of construction (earlier than any other option) - then revenues cover all expenses
Real debt repayment only USD 86 million until break-even
  USD 8.6 million/year for 10 years then revenues take over
O&M guaranteed for 30 years at no extra cost

## Slide 12
The proposed model
No hidden costs, no collaterals
High quality bidders
Affordable tolls
Maximized revenues for the Government.
Project designed as an economic corridor
A contribution to GDP growth
Decongestion & improved transit
Lower cost of doing business
Enhanced regional integration and trade
A concessionaire accountable to Government
Concessionaire obligations towards the Government
Government keeps control
PPP - Other advantages

## Slide 13
Best international practices
Mitigate the serious environmental and social challenges
Maximise inclusive economic benefit of the project
Improve road safety
Local content
At least 30% of works subcontracted to Ugandan companies under BUBU Policy
Creation of at least 1500 direct jobs during construction and 250 direct jobs during operation
The first PPP in Uganda
Pioneering and innovative for industrialisation
Gain/retain the confidence of quality investors and longstanding partners
PPP - Other advantages

## Slide 14: And then comes China Railway 17th Bureau Group alias CR17BG
They are here

## Slide 15: First attempt to a direct award Letter to the Infrastructure committee of the Parliament –Sept 2018
REMINDER:
At the same time, the sister company CRCIG also subsidiary of CRCC is part of the PPP pre-qualification process launched in May 2018
CR17BG is informed by the Minister of Finance in writing that the Kampala-Jinja Expressway had already been approved by Government as a PPP and was in the advanced stages of procurement. The Minister’s letter indicates that Government would not undertake the hugely expensive Project under an equally expensive different mode of financing. They are even offered other projects. BUT….

## Slide 16: Second attempt to direct award Meeting with the President thanks to Ugandan Lobbyists – Dec 2018
This is after the sister has failed to be qualified :
failed to demonstrate financial capacity
failed to demonstrate technical capacity

## Slide 17: Response to this second attempt Op-ed from the Vice Chairman of the PPP committee following several article relaying the meeting with the PR – January 2019
Title: "Kampala-Jinja Road tender process should be protected"
"It is therefore extremely surprising that despite the extensive work, time and financial resources both Government and development partners have invested into an exhaustive and open competitive procurement process which began in May 2018, an entity whose associates failed through a formal legal process and applying international best practice endorsed by multinational partners, is attempting once again to disrupt this meticulous work."
"The above process has thus far remained unencumbered and is progressing very well. Attempts to circumnavigate and or, introduce non-open tender bidders or disqualified actors through other processes than those to which the government; development partners and regulators signed up will amount to a defeat of our own laws and regulations"
"It is our Committee’s considered opinion that a project of such magnitude and importance to Uganda and the region that has attracted the support of multiple partners including the EU, AFDB, AFD and IFC must be protected from any external interference in order to maintain the integrity of government; its laws, processes and achieve value for money"
" We must not make the same mistakes again and again. Let us protect and maintain an open tender competitive procurement process to completion, to develop the best possible, well maintained and functional road project for Uganda"
We thought we were safe (Yes! There is a strong governance in this country able to back fire the machinations- are we naïve?) BUT…..

## Slide 18: Third attempt to direct award
Beginning September 2019 : This third attempt starts with a campaign of disinformation in the press: "M7 rightly blocks Kampala-Jinja expressway project protesting IFC, French economic sabotage"
And continues with a new visit with the President – 10th of September (no one from the government structure attends the meeting!)
Following the meeting, the President issues a letter directing the MoWT to not borrow and to consider the CR17BG proposal.
This decision to consider the proposal of CR17BG outside the normal bidding process has been taken without and against the advice of UNRA, the Ministry of Finance and the PPP Unit. They all tried to advise against this move but were not heard by the President.

## Slide 19: Third attempt to undermine the PPP Process CR17BG's proposal
• CR17 would finance the construction of the project and recover the investment through road tolls;
• CR17 would finance the compensation of project affected persons and recover the money through the road toll on the project;
• CR17, being worried that road tolls may not be sufficient to recoup their investment propose to carry out the following activities:
o Build and sell high rise residential properties along the corridor; and
o Build small scale business parks along the corridor
• CR17 is seeking GoU support to allow them build and sell properties along the corridor;
• CR17 requests that GoU commits to give them the rights to any construction and or upgrade works on any existing or future projects that are likely to impact on the traffic that uses KJE. A clear case being the existing jinja highway upgrade, the bridge that connects Munyonyo to Kyaggwe and all link roads connecting to KJE
As a concluding remark, CR17’s proposal would only be provided once a contract (guaranteeing CR17 the project) has been signed with GoU.
Way forward proposed by the MoWT:
CR17 should communicate to GoU a formal proposal which can be assessed. The proposal should include the information/studies that informed their decision to commit to the President that they can fund and recover their investment fully through toll revenues.

## Slide 20: Reasons provided to postpone the decision since our meeting with the president and despite the inconsistency of the Chinese proposal
Debt ceiling
Completion of UNRA road programme
Successful fees for IFC
What is the purpose: buying time for the Chinese to improve their offer as they complain UNRA doesn't want to share information with them?
THAT'S WHERE WE ARE FOLKS!!

## Slide 21: Some recommendations
Reflect special role of EU in Blending: if things go wrong, the EUD will be on the forefront as a political partner
Sign a FA or a MoU with the Government early enough whenever possible
Build a solid communication campaign early enough, especially if the legal basis or sectors or project design are innovative.
Involve colleagues in HQ regularly, so that a high-level support can be mobilized quickly as needed and that we can reflect on the adequacy of our processes.