## Slide 1: Fish Forward Lessons Learned - Finance
Stewart Page - Finance & Administration Manager
Sabine Gisch-Boie – Project Manager
WWF Austria 24.09.2020

## Slide 2: Fish Forward (Campaigning & Advocacy)
Responsible seafood consumption for the benefit of people, oceans and climate
17 Countries, 17 Partners
7 Mio Budget
3 + 0,5 years
Consumers
Corporates
Authorities
Small Scale Fishers in developing countries

## Slide 3: Structure
 | Output 0 | Output 1 | Output 2 | Output 3 | Output 4
 | Project Manage-ment | Fin & Admin | Consumers | Corporates | Authorities | Producers in developing countries
WWF Austria = Coordinator | x | x | x | x | x | x
11 EU Partners | x | x | x | x | x | 
5 Partners in Dev. Countries | x | x |  |  |  | x

## Slide 4: Success factors
Clear finance guidelines and templates (in case of doubt: Annex II, Special Conditions, PRAG, ask EC and your auditor to clarify)
At the start: individual calls with project managers and relevant team members
Trainings for project managers, finance & admin colleagues, Output Coordinators
Constant follow up and support (e.g. procurement, marketing budget plans, expenditure rates, issues with reporting, modifications / amendments)
Partners responsibilty for their own budget (eligibility) & clear roles

## Slide 5: Roles & Responsibilities
Finance and everything that goes along with it is the responsibility of every Fish Forward employee

## Slide 6: Audit Feedback (KPMG)
Auditors cost review percentage (Fish Forward 1)
2015: 100% of salaries and 96% of total direct costs
2016: 100% of salaries and 85% of total direct costs
2017: 100% of salaries and 81% of total direct costs

## Slide 7: Salary Costs
Key findings from KPMG audits:
Proving that reported costs match the available salary documentation
Proof of salary payments:
This was provided just for one month each year (October)
Complete and accurate supporting documents (salary statements & time-sheets)
Work contracts:
Up to date contracts needed for every project member. Extension documents if needed.

## Slide 8: Audit Feedback (KPMG)
Fish Forward Year 3 Main Requests:
  Salaries (documentation, timesheets, contracts etc)
  Procurement documentation for bigger purchases
  Proof of delivery documents
  Proof of payment for reverse charge VAT
  Agendas / minutes
  Proforma invoices, booking confirmations etc. not acceptable

## Slide 9: Lessons learned
1) Prepare detailed descriptions of payroll and salary documentation for each Partner
2) Expect varying levels of financial experience within your partner organisations
3) Consistency is key.
4) Regular communication vitally important
5) Asssume and prepare in advance for a detailed and thorough audit

## Slide 10: Q&A