## Slide 1
Results Oriented Monitoring
ROM reviews and Support for designing logframes
Inception Seminar for 2018 CfP DEAR Interventions #4 Monitoring, Evaluation and Learning
22 September 2020

## Slide 2
1. ROM Global

## Slide 3: The ROM Global
  Part of Results Oriented Monitoring (ROM) system
  “To improve the performance of EU-funded interventions by strengthening design, monitoring and evaluation systems at intervention and institutional level.”
  ROM services:
  ROM review
  Support for designing Logframes and Monitoring Systems
  Support to Results Data Collection

## Slide 4
2. ROM reviews

## Slide 5: Purpose and Methodology
  “To provide an external and objective assessment on the performance of selected ongoing DEVCO interventions.”
  Analysis of the intervention documentation
  Interviews with intervention stakeholders
  Standard set of Monitoring Questions

## Slide 6: Assessment Criteria
  4 DAC criteria :
  Relevance
  Efficiency
  Effectiveness
  Sustainability
  4 additional criteria:
  Coordination, complementary and EU added value
  Intervention logic, monitoring and learning
  Cross cutting issues
  Communication and visibility

## Slide 7: Implementation of ROM Review missions (1)
  Desk phase
  Provision of missing documentation
  Identification of key stakeholders – draft agenda of the mission
  Facilitation of the organisation of meetings

## Slide 8: Implementation of ROM Review missions (2)
  Field phase
  Briefing with the OM
  Briefing with the intervention management team
  Field visits and interviews
  Debriefing

## Slide 9: Implementation of ROM Review missions (3)
  Reporting phase
  Monitoring Questions document
  ROM report
  Lessons learning log

## Slide 10
3. Support for Designing Logframes and Monitoring Systems

## Slide 11: Purpose
  “To improve the development and formulation of intervention logics, and of their corresponding Logframes and M&E and reporting systems for EU-funded interventions.”
  Needs:
  Coherence with programming (Action Documents)
  ROM Review recommendations
  Results Reporting
  OPSYS

## Slide 12: Coverage and Scope
  Type of intervention: project modality
  Budget: > 1,000,000 EUR
  Timing: - before contract signature
  - before an extension signature
  - just after contract signature (i.e. grants)
  2 components:
  Revision of the Logframe and narrative intervention logic
  Advice on M&E system and reporting requirements

## Slide 13
Thank you!
Q&A
Useful links:
ROM services described for Implementing Partners: https://europa.eu/capacity4dev/rom/documents/rom-services-described-implementing-partners-0
ROM Handbook:
https://europa.eu/capacity4dev/rom/documents/rom-handbook-v61-june-2020