## Slide 1
The Evaluation Unit of DG for Development and Co-operation EuropeAid
invites you to the
Seminar presenting results and recommendations of the evaluation of
European Commission Support to Decentralisation processes
What have been the results of the EC approaches in supporting Decentralisation processes in partners countries? What are the lessons learned and future perspectives?
What are EU strengths and weaknesses in supporting decentralisation processes?
How has the EC ensured a complementary use of its various instruments in supporting Decentralisation processes?
Questions
Evaluation of
European Commission Support to Decentralisation processes
To download the full report:
http://ec.europa.eu/europeaid/how/evaluation/evaluation_reports/2012/1300_docs_en.htm

## Slide 2
Thematic global evaluation of the Commission support to decentralisation processes
Seminar
Brussels, 12 March 2012
Contract n° EVA 2007 (EuropeAid/122888/C/SER/Multi) – 2009/226838

## Slide 3
  Part 1: Evaluation approach and methodology
  Part 2: Main findings
  Part 3: Main conclusions & recommendations.
Structure of the presentation

## Slide 4
Part I: Evaluation approach and methodology

## Slide 5
The purpose of the evaluation is to gain key relevant lessons and to provide recommendations to help for opportune and timely support to decentralisation processes; it shall cover aid delivery over the period 2000-2009 taking into account the different entry points: top-down, bottom-up, sectoral).
Overall purpose of the evaluation

## Slide 6
Key steps of the evaluation process

## Slide 7
Decentralisation: it is a process involving the transfer of a range of powers, competences and resources from the central government to elected local (sub national) governments. Decentralisation entails three inextricably linked dimensions:
  Political: it involves a new distribution of powers according to the subsidiarity principle, with the objective of strengthening democratic legitimacy
  Administrative: it involves a reorganization and clear assignment of tasks and functions between territorial levels to improve the effectiveness, efficiency and transparency of the administration over all national territory
  Fiscal: it involves a reallocation of public expenditure to local and territorial authorities and enables them to generate their own revenue according to their assigned tasks
Local democratic governance: it is a decision-making and implementation process of public policy that, around local governments (elected in contexts of decentralisation), encourages an equal participation of all stakeholders of a territory (State, citizen civil society, private sector), reinforces accountability towards citizens and responsiveness to social demands in seeking for the general interest.
(European Charter on development cooperation in support of local governance 2008 – and 2009 Programming fiche on decentralisation)
Definition of decentralisation

## Slide 8
Intervention logic

## Slide 9
Evaluation Questions
Code EQ | Evaluation question
EQ1: Policy framework | To what extent has the EC managed to establish a policy framework that facilitates programming & implementation of the EC support to decentralisation?
EQ2: Institutional capacity | To what extent has the EC developed its overall institutional capacity to support decentralisation processes?
EQ3: National context | To what extent has EC support to decentralisation processes been conceived in the way that it is responsive to national contexts and aligned with national regulations and policies?
EQ4: 3Cs | To what extent has the EC ensured coordination and complementarity with other donors, active in the decentralisation arena, and ensured coherence with EC policies and activities?
EQ5: Transfer of functions & resources | To what extent has EC support contributed to the decentralisation of powers, functions and resources to local governments in partner countries?
EQ6: Stakeholders’ capacities | To what extent has EC support to decentralisation contributed to strengthening the capacities of stakeholders involved in the decentralisation processes in partner countries?
EQ7: Local governance | To what extent has EC support to decentralisation processes contributed to improving local governance, especially regarding participation, accountability and transparency?
EQ8: Service delivery | To what extent has EC support to decentralisation processes contributed to enhancing and sustaining service delivery at local level?

## Slide 10
Overview of tools used in the desk study and the field phase
Tool | What was done? | What for?
Web- survey (to a sample of EU Delegations) | A structured questionnaire including quantitative and qualitative elements was developed and validated by the Evaluation Unit. It was prepared as a web-survey, and information on the survey was sent to the 22 desk study countries selected. The survey was managed in-house. | Obtaining of the views of the Delegations on relevant EQs, JCs and indicators, as well as on main weaknesses and strengths of on-going EC support. Allows for triangulation of some of the findings from the field visits and other tools used in the desk study. The information also fed into the responses to the EQs.
Interviews, both structured and unstructured | A round of interviews was held with relevant EC staff in Brussels; Numerous interviews were held during the field visits. Interviewees were selected on the specific added value they were supposed to provide concerning specific EQs or issues. The interviews were mainly of a structured and semi-structured nature. Besides face-to-face interviews, a few telephone interviews were made. | Obtaining of the views of the stakeholders concerned on relevant EQs, JCs and indicators, as well as on main weaknesses and strengths of programmes and policies. The information fed into the responses given to the EQs, in the Desk Report, in the Country Notes and in the Final Report.
Literature review and analysis of statistics | Literature review included: Project documentation (incl. Financial agreements, progress report, etc.). Relevant evaluation reports (EC and other donors), incl. Country Strategy Evaluations. Sector studies. Major documents related to the countries, obtained before / during the field visits. Statistics produced by international organisations. | To complement primary and other sources. This information fed into the responses to the EQs.
ROM analysis | Downloads were made for the desk study countries from the CRIS database, including monitoring reports, programme documents, evaluations. Selected interventions were analysed and analysis was included in the desk report. | To allow for triangulation of some of the findings from the field visits and, for instance, the questionnaire survey.
Analysis of Country Strategy Papers | In the CSPs, the information was researched in relation to a number of criteria and indicators, especially regarding EQ1 to 4. | This information fed into the responses given to the EQs.

## Slide 11
Data collection and processing process

## Slide 12
List of country cases selected for the desk phase & the field visits
Region / Country | 
Africa (desk phase:11 / field phase: 6) | 
Benin | Congo (Democratic Republic of)
Kenya | Madagascar
Mali | Rwanda
Senegal | Sierra Leone
South Africa | Tanzania
Uganda | 
Asia (2/1) | 
Cambodia | The Philippines
Caribbean (1/0) | 
Haiti | 
ENP (2/1) | 
Jordan | Lebanon
Latin America (5/2) | 
Colombia | Guatemala
Honduras | Nicaragua
Peru | 
Pacific (1/0) | 
Papua New Guinea | 

## Slide 13
Coverage of selected country cases
Criteria | Total direct support (mEUR) | Direct support in sample (mEUR) | %
Region |  |  | 
All regions | 789.3 | 581.3 | 74%
Africa | 586.4 | 449.9 | 77%
Latin America | 78.3 | 68.6 | 88%
ENP | 60.7 | 42.8 | 71%
Asia | 33.2 | 13.5 | 41%
Other | 30.8 | 6.4 | 21%
Entry point |  |  | 
Bottom-up | 580.2 | 422.9 | 73%
Top-down | 209.1 | 158.4 | 76%
Financing modality |  |  | 
Sector Budget Support (SBS) | 113.4 | 113.4 | 100%

## Slide 14
  Evaluation of a thematic area under development with a very broad range of interventions that aim at complex changes, beyond synthesis of individual interventions. Addressed by structured approach: agreed common intervention logic and related Evaluation Questions.
  Main focus on "direct" support to decentralisation reforms but also considering support in "decentralised context".
  Challenge to construct inventory as no systematic DAC coding of interventions.
  Limitations of information available in desk phase: primarily analyses of existing documentation of CSPs, documentation of interventions and survey to delegations – limited available information on wider results and impacts related to decentralisation reforms.
  Detailed analyses in ten countries where fieldwork was undertaken – but constrained by available time.
Challenges and limitations

## Slide 15
The report consists of 2 volumes: Main report & Annexes.
VOLUME I: MAIN REPORT
  1. Introduction
  2. Methodology
  3. Answers to the Evaluation Questions
  4. Conclusions and Recommendations.
VOLUME IIA: ANNEX 1 - DETAILED INFORMATION MATRIX.
VOLUME IIB: ANNEX 2 TO 10
  1. Annex 2: Terms of Reference
  2. Annex 3: Inventory
  3. Annex 4: Results of the survey to EU Delegations
  4. Annex 5: MTRs & JARs analysis
  5. Annex 6: CSP analysis
  6. Annex 7: CSE analysis
  7. Annex 8: ROM analysis
  8. Annex 9: Evaluation Matrix
  9. Annex 10: List of People Interviewed.
VOLUME IIC: ANNEXE 11 - COUNTRY NOTES.
Structure of the final report

## Slide 16
Part II: Main findings

## Slide 17
Inventory of EC support - Evolution over the evaluation period

## Slide 18
Inventory of EC support - Geographical breakdown
Region | EC direct support to decentralisation (in million EUR) | Total support in the region (in million EUR) | Ratio of support to decentralisation compared to total support in region | Share of total EC support to decentralisation
ACP |  |  |  | 
Africa | 586 | 25.203 | 2,3% | 74%
Caribbean | 26 | 2.095 | 1,2% | 3%
Pacific | 4 | 590 | 0,7% | 1%
Latin America | 78 | 3.196 | 2,4% | 10%
Asia | 33 | 6.024 | 0,6% | 4%
ENP | 61 | 9.587 | 0,6% | 8%
TOTAL | 789 | 46,827 | 1.7% | 100%

## Slide 19
The EC has placed increased attention on decentralisation and local government reforms in its cooperation with third countries.
  Increased volumes of support, - although relatively focused on small number of Francophone African countries,
  Increasing attention to decentralisation EC reference documents,
  Gradual development of entry points towards more strategic interventions and greater mix of aid modalities.
EC policies, programming guides and reference documents have become increasingly comprehensive and, in recent years, also clearer and more coherent.
  The EC Reference Document (no 2, 2007), “Supporting Decentralisation and Local Governance in Third Countries”, is the most widely used guidance document.
  The European Charter on development co-operation in support of local governance (2008), and 2009 decentralisation programming fiche – more clear – but not widely disseminated.
  The EC policies are relative clear in their emphasis on local governments (rather than e.g. CDD).
The extent to which EC support addresses decentralisation in a particular country depends primarily on the local context, rather than on a global policy or strategy.
Evaluation Question 1: Policy Framework

## Slide 20
Overall institutional environment within the EC has improved - e.g. flexibility of EC operational procedures but scope for strengthening internal co-ordination and incentives to innovate.
The staff resources assigned to work on decentralisation are still modest, and a large majority did not attend the thematic training organised by the EC:
  Specialist staff in HQ grew to 3-4 persons but has recently been reduced to one person,
  Staff in EUDs acquires some knowledge on decentralisation reforms locally – but only limited knowledge through EC.
The framework for monitoring and internalisation of experience related to EC support to decentralisation is still insufficient, even though some initiatives have been launched.
Evaluation Question 2: Institutional Capacity

## Slide 21
EC support to decentralisation is generally responsive to national contexts, policies and regulation.
responsiveness to national contexts is determined by the particular stage of decentralisation reform processes in partner countries, but also by the depth of background analyses carried out.
Policy dialogue on decentralisation has intensified and has become more structured, but results mixed.
The choice of entry points and aid delivery methods generally reflects the evolution of national contexts.
Aid modalities per se are not decisive factors of success in the support to decentralisation.
Evaluation Question 3: National context

## Slide 22
The EC contribution to establishing and implementing co-ordination mechanisms with EU member states and other major donors has significantly improved over the period evaluated.
Complementarity of EC interventions with other donors has been promoted by strong dialogue during programming stages, a clear division of labour, and jointly-financed programmes in the decentralisation area.
The coherence between EC support to decentralisation and other policies, programmes and activities has improved over the period evaluated but still remains generally weak.
Evaluation Question 4: 3Cs

## Slide 23
Evaluation Questions 5-8 Results in partner countries

## Slide 24
Summary of focus and results of EC support in case study countries
 | National policies | National legislations | LG resources | LG autonomy | Capacity - central | Capacity - local | Capacity - NSA | Participation | Accountability | Transparency
Benin |  |  | + | 0 | + |  |  |  | 0 | 
Honduras |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
Lebanon |  |  | - |  |  |  |  |  |  | 
Mali |  | + |  | 0 |  | + | 0 |  |  | 
Peru |  |  |  |  | 0 |  |  |  | 0 | 0
Philippines |  |  |  |  |  |  |  |  |  | 
Rwanda |  |  |  |  |  |  |  |  |  | 
Sierra Leone | + |  | + |  | + | + |  | + | + | +
South Africa |  |  | + |  |  | + |  |  |  | 
Tanzania | + |  | + |  |  | + |  | + | + | +
Overall assessment |  |  | + | 0 |  | + |  | + |  | 
Colour | Level of EC support - Scale | Description
 | significantly | Interventions' objectives or activities do explicitly at significant degree address the result area and the concerned interventions are of relative significance compared to overall EC support to decentralisation.
 | partly | Interventions' objectives or activities only partially or marginally address the result area and/or the concerned interventions are relative small compared to overall EC support to decentralisation.
 | not at all | EC support in the country does not at all address the result area.

## Slide 25
The EC support has aided the development of national decentralisation policies/ strategies and relevant legislations only in a few cases, and, in these countries, results have remained modest.
The EC has contributed to the increase of local governments’ fiscal resources in several countries, but only to a limited extent to the increase of human resources.
Overall, the EC support has made some small contribution to local governments' autonomy, mainly through its support to inter-governmental fiscal transfer systems.
Evaluation Question 5: Transfer of functions and resources

## Slide 26
The EC contribution to improved management and administrative capacities of key central government bodies involved in decentralisation policy formulation and implementation has been limited.
EC support has made significant contributions to improved capacities of local governments for management of decentralised administrative, fiscal and political responsibilities/powers.
The EC has worked extensively with local NGOs and community-based organisations for the improvement of service delivery, but, overall, the EC support has not significantly helped to improve the capacities of all relevant non-state actors on issues directly related to decentralisation.
Evaluation Question 6: Stakeholder capacities

## Slide 27
EC support has, overall, resulted in only limited improvement in terms of local accountability.
The EC has contributed to increased transparency in fund allocation and utilisation in only a few selected countries.
Evaluation Question 7: Local governance
The EC has contributed to increased local participation in local government affairs, especially through support to the development of specific procedures for local development planning. The EC has generally not supported improved systems for local government elections.

## Slide 28
The EC has contributed to increased financial resources and improved allocation of resources for local service provision,
The contribution of the EC support to improved operation and maintenance of locally-provided services remains limited.
Most of the EC support to decentralisation has contributed to expansion of local infrastructures (aimed at improving health access, education and roads), but the effects of the support on the quality of locally-provided services is limited.
Evaluation Question 8: Service delivery

## Slide 29
EC support for decentralisation has been highly relevant – reflecting the growing needs in partner countries.
EC support most effective in fiscal aspects of decentralisation reforms, as well as building selected capacities of LG staff and contributing to improved access to services. Less effective in achieving deeper legal reforms, LG staff devolution, extending the degree of LG autonomy (a reflection of the political nature of the reforms) and quality aspects of local service delivery.
Efficiency of EC support has improved as it has become more adaptable to different aid modalities.
Sustainability of support is highest when aligned to national owned reform programmes that are based on realistic political assessments. “Bottom up” support still to demonstrate long term sustainability of reform initiatives.
The EC’s value added has been most evident in countries where size of contributions have made a difference. However, value added has in many countries also been constrained by the limited technical expertise/human resources available in both EUDs and HQ.
EUDs have been key drivers for increased co-ordination and complementarity among MS.
Overall assessment of the EC strategy

## Slide 30
Part III: Main conclusions & recommendations

## Slide 31
Overview of main links between EQs, Conclusions and Recommendations

## Slide 32
Cluster 1: EU policy framework

## Slide 33
Cluster 1: EU policy framework – Main conclusions
Conclusion 1: This conclusion is based mainly on EQ1, EQ2, EQ3, EQ4. | The EU policy framework for support to decentralisation in third partner countries has developed in a positive manner in response to general trends of decentralisation reforms in partner countries. However, the framework is not yet underpinned by operational guidelines and clear strategic intervention responses that plainly embed support for decentralisation within broader public sector reform approaches.
Conclusion 2: This conclusion is based mainly on EQ1, EQ2. | The EU has a unique but unrealised potential for global support to decentralisation in third partner countries, working locally, worldwide in outreach, supporting international networks and building on global experiences.

## Slide 34
Cluster 1: EU policy framework – Main recommendations
Recommendation 1: Based on conclusions 1, 2, 3 and 8. | Clarify and strengthen the EU’s global role in support to decentralisation by clearly anchoring that support within partner countries’ wider public sector reform agenda, by acting proactively, and by clarifying the comparative advantages of the EU. Consider establishment of separate technical unit under DEVCO.D with expertise in public sector reform (civil service reform, public sector management and decentralisation/local government systems). Enhance EU analytical and technical capacities in support of decentralisation and local governance. Enhancing dialogue with partner countries and EU Member States.
Main implementation responsibility: | Any relevant persons at HQ in charge of designing the relevant aspects of the EU policy framework.

## Slide 35
Cluster 1: EU policy framework – Main recommendations
Recommendation 2: Based on conclusions 1 and 9. | Operationalise and disseminate EU policy framework. Develop operational guidelines for work EC support to decentralisation (fiscal decentralisation and sector programme support + adjust existing common donor guides on e.g. Political economy analyses to EC); Strengthening processes of dissemination of policies and guidelines: integration into general EC guidelines, disseminate through e-learning and seminars.
Main implementation responsibility: | Decentralisation sector specialists at HQ. EU desk officers in DG DEVCO. Other EU services in charge of specific expertise (e.g. thematic budget lines, Aid Delivery Methods, o-QSG).

## Slide 36
Cluster 2: Response to specific country contexts

## Slide 37
Cluster 2: Response to specific country contexts – Main conclusions
Conclusion 3: This conclusion is based mainly on EQ3, EQ4, EQ5. | EC support to decentralisation in third partner countries has successfully increased its alignment with partner country policies and priorities. However, the EC has not promoted decentralisation reform policies very proactively, and EC policy advocacy for decentralisation support has generally been modest – possibly too modest.
Conclusion 4: This conclusion is based mainly on EQ5. | Decentralisation reforms that implicate significant transfers of powers and resources to elected local governments are highly political. In several cases, the EC has not yet gained sufficient insight into the “politics of reform”.
Conclusion 5: This conclusion is based mainly on EQ5, EQ6, EQ7. | The different stages of decentralisation reform and maturity of LG systems in partner countries require very different EC responses. The EC has been most successful in countries at the very initial stage of reform processes.

## Slide 38
Cluster 2: Response to specific country contexts – Main conclusions
Conclusion 6: This conclusion is based mainly on EQ8 – and partly on EQ5, EQ6 and EQ7. | EC support for decentralisation reforms has contributed to improved local service delivery in various ways: indirectly, by establishing a broadly enabling environment; and, more directly, by providing additional resources for local services. The latter has mainly contributed to increased access to services but less to improvements in the quality of services.
Conclusion 7: This conclusion is based mainly on EQ4 – and partly on EQ7. | The EC has been relatively active in supporting institutional arrangements for decentralisation reform support co-ordination. However, these are yet to be fully partner-led.

## Slide 39
Cluster 2: Response to specific country contexts – Main recommendations
Recommendation 3: Based on conclusions 2, 3, 4 and 7. | Strengthen and broaden country ownership and co-ordination mechanisms for support to decentralisation reforms, but retain proactive EU advocacy role Deepen country analyses – including of the “politics of reform”; Deepen country dialogue beyond relevant lead ministry; Strengthen capacities of local actors to analyse and influence reform processes.
Main implementation responsibility: | EUDs.

## Slide 40
Cluster 2: Response to specific country contexts – Main recommendations
Recommendation 4: Based on conclusions 4, 5 and 10. | Strengthen EU’s country-specific and comprehensive responses to decentralisation in all partner countries. Deepen country analyses – including of the “politics of reform”; Encourage partner countries efforts for comprehensive reform strategies; Identify relevant entry points for EC support: Non-existent or very weak LG structures and no explicit decentralisation reform agenda (frequently found in (post) conflict countries); Explicit decentralisation reform agenda in early stages; Explicit decentralisation reforms in mature stages; Mature LG structure without explicit decentralisation reform agenda.
Main implementation responsibility: | EUDs.

## Slide 41
Cluster 2: Response to specific country contexts – Main recommendations
Recommendation 5: Based on conclusions 6. | Strengthen qualitative aspects of local government service delivery in EU support for decentralisation reforms Support the analysis of quality aspects of local service delivery under the management of local governments. Identify areas of local government legislation, procedures and capacities that impact on quality of local service delivery. Emphasize aspects of central government fiscal transfers for recurrent aspects of service delivery as well as the use of local revenue generation and user fee contributions. Emphasise operation and maintenance issues as a key concern in interventions supporting decentralisation processes. Assist partner countries in building systems for monitoring of local service delivery.
Main implementation responsibility: | EUDs. EU desk officers in DG DEVCO and any other relevant persons involved in the decisions on the EU approach in partner countries.

## Slide 42
Cluster 3: Strategic focus

## Slide 43
Cluster 3: Strategic focus – Main conclusions
Conclusion 8: This conclusion is based mainly on EQ1, EQ5, EQ6, EQ7, EQ8. | EC support for decentralisation has been most successful when provided through national joint government-DP assisted programmes. However, this is yet to be fully reflected in overall EC policy and strategy.
Conclusion 9: This conclusion is based mainly on EQ4 (and EQ5, EQ6, EQ7, EQ8). | EC support through GBS and to various sectors (e.g. health, education) is supporting wider decentralisation reforms in only a very limited way.
Conclusion 10: This conclusion is based mainly on EQ5, EQ6, EQ7, EQ8. | EC support for decentralisation reforms typically target only selected areas of reform, yet it is important to ensure that all relevant areas of the decentralisation reform agenda progress in a balanced way.

## Slide 44
Cluster 3: Strategic focus – Main conclusions
Conclusion 11: This conclusion is based mainly on EQ7. | EC support for the bottom-up demand for accountability has rarely been linked with wider systemic decentralisation reforms.
Conclusion 12: This conclusion is based mainly on EQ5, EQ6, EQ8. | In all of its major decentralisation support programmes, the EC has included elements of reform of the Intergovernmental Fiscal Transfer (IGFT) systems. These reforms have, in general, proved successful entry points both for systemic reform of how LGs are financed and as ways of capacity building and supporting immediate improvements of LG services.

## Slide 45
Cluster 3: Strategic focus – Main recommendations
Recommendation 6: Based on conclusions 12. | Prioritise EU support for IGFT and LG fiscal reforms. Prioritise support for IGFT in country programmes as part of division of labour with partner countries and other DPs supporting decentralisation reforms; Continuously monitor and disseminate experiences learned - develop overview of “good practices”.
Main implementation responsibility: | EUDs. Depending on the regions, EU desk officers in DG DEVCO and any other relevant persons involved in the decisions on the EU approach in partner countries.

## Slide 46
Cluster 3: Strategic focus – Main recommendations
Recommendation 7: Based on conclusions 2, 3, 7 and 8. | Strengthen efforts for donor harmonisation in support of decentralisation in partner countries and globally. • Strengthen country ownership of reform efforts and increase understanding of the political dynamics of such reforms. • Engage actively in the work of DeLog. • Implement agreed actions of the document “Busan and Beyond: Localising Paris Principles for More Effective Support to Decentralisation and Local Governance Re-forms”. • Continuously monitor and disseminate experiences learned.
Main implementation responsibility: | Relevant staff at HQ and EUDs. Depending on the regions, EU desk officers in DG DEVCO and any other relevant persons involved in the decisions on the EU approach in partner countries.

## Slide 47
Cluster 3: Strategic focus – Main recommendations
Recommendation 8: Based on conclusions 7 and 11. | Strengthen partner countries’ monitoring of decentralisation reforms. Policy progress: legislative benchmarks, transfers of functions, etc. Capacities at LG level: organisational performance in areas of planning, PFM, etc. Service delivery results – impact on both access to services as well as quality of services. Governance outcomes: citizen participation, accountability transparency, corruption indicators, etc. Use of peer review mechanisms and support relevant international databases.
Main implementation responsibility: | EUDs. Depending on the regions, EU desk officers in DG DEVCO and any other relevant persons involved in the decisions on the EU approach in partner countries.

## Slide 48
Cluster 4: Operational management

## Slide 49
Cluster 4: Operational management – Main conclusions
Conclusion 13: This conclusion is based mainly on EQ2. | Throughout the entire period evaluated, EC specialist decentralisation reform expertise has been limited to two-four persons at HQ, and has recently been reduced to only one person. This is inadequate for the required tasks, and is very low compared to expertise in other development organisations.
Conclusion 14: This conclusion is based mainly on EQ1, EQ2. | The EC’s monitoring of its support for decentralisation has been weak, although there have been occasional qualitative learning exercises.

## Slide 50
Cluster 4: Operational management – Main recommendations
Recommendation 9: Based on conclusions 9 and 13. | Strengthen EU staff expertise on decentralisation reforms. Establish a strong central unit (part of wider public sector reform expertise) that has broad geographical expertise on various aspects of decentralization reforms – LG finance reforms in particular. Provision of short-term training to other staff in EUDs and HQ.
Main implementation responsibility: | Relevant persons at HQ (mainly DG DEVCO).

## Slide 51
Cluster 4: Operational management – Main recommendations
Recommendation 10: Based on conclusion 14. | Strengthen EU monitoring and evaluation of decentralisation support. Systems for (DAC) coding programming interventions in support of decentralisation. Effective sharing of country specific evaluation of decentralisation support within the EC. Encouragement of international and regional systems for decentralisation monitoring. This will include systems for basic statistical information as well as governance peer reviews (modelled for instance on the European Charter of Local Self Government). Future (global) evaluations on decentralisation as joint exercises with MS and focus on specific sub-themes (e.g. fiscal decentralisation, national decentralisation reform programmes etc).
Main implementation responsibility: | Decentralisation sector specialists in HQ. Evaluation Unit.