## Slide 1: Summary of main outcomes of discussions in the « Disaster risk reduction – Coastal zone management » groups
Session 23, day 2, 13 September 2012

## Slide 2: Challenges and responses common to CZM and DRR (1)
Challenges | Responses / Success factors
Complex and often ineffective coordination mechanisms due to the large number of stakeholders to be involved | Establish coordination mechanisms with a clear leadership, while ensuring that the leading organisation has the resources and influence required to effectively play its role GCCA programme staff to play a more proactive role in facilitating coordination among donors and institutions
Institutional reforms may not be sustainable | Avoid the kind of reforms that overburden agencies with added responsibilities without providing commensurate resources
Need for coordination between CZM, DRR and CC | Build bridges between them in the context of overarching coordination mechanisms (but in practice this is not easy...)

## Slide 3: Challenges and responses common to CZM and DRR (2)
Challenges | Responses / Success factors
Legal framework not supportive or not enforced | Start by supporting the development of land use plans – and where they exist, their effective enforcement
CZM and DRR require large quantities of data as well as specialised skills | Start by setting up systems to collect and consolidate all the existing data in a single repository – Go for GIS-based solutions allowing to superimpose different types of data in relation to specific areas Collect baseline data Develop collaborative mechanisms / partnerships between national / regional / international experts (public, private, academic, non-state, ...) Use MoUs to support the sharing of data Hire in-country coordinators to facilitate access to local / traditional knowledge

## Slide 4: Challenges and responses common to CZM and DRR (3)
Challenges | Responses / Success factors
Limited availability of qualified technical staff (e.g. engineers, data management specialists) | Identify and prioritise needs in sector capacity building plan – Mobilise budget according to needs Optimise the use of available resources and avoid overlaps (integrated approach => cost savings) Hire TA / external services as needed throughout project duration Make sure national expertise (e.g. local engineers) is used
Stakeholder engagement essential but not receiving enough attention | Make more systematic use of stakeholder consultations Engage stakeholders more directly and systematically Ensure community buy-in of field projects

## Slide 5: Challenges and responses common to CZM and DRR (4)
Challenges | Responses / Success factors
Community participation hindered by the lack of a proper enabling environment (e.g. land tenure issues) | Address issues that may hinder community participation, such as land tenure issues, through appropriate (e.g. administrative) arrangements
Project design issues, e.g. lack of coincidence with planting cycles / seasons | Hire extra (short-term) staff and intensify activities during planting season Generally, adapt project design and time frames to integrate practical considerations Proper studies and planning required to inform project design
Infrastructure vs. ecosystem-based approaches | Use both in combination, based on an assessment of what is likely to be the most effective and the most sustainable – Long-run costs to be considered

## Slide 6: Challenges and responses common to CZM and DRR (5)
Challenges | Responses / Success factors
Countries overburdened by donor interventions | Strengthen donor coordination and harmonisation of systems and priorities Identify and prioritise activities in view of their integration into national policy frameworks
Lack of effective coordination / collaboration in GCCA programme implementation | Ensure representation of key personnel / organisations concerned in relevant project committees Wider consultation during project design to facilitate a more coordinated and integrated approach during implementation
Excessive donor visibility requirements lead to territorial attitudes among project staff | ???

## Slide 7: Challenges and responses specific to CZM (1)
Challenges | Responses / Success factors
ICZM is a complex process with many facets | Contribute to selective elements of the process (e.g. Senegal: High Authority in charge of CZM not yet set up, but the GCCA programme prepares the ground for its establishment by consolidating data collection and management systems that will support its role once it becomes operational) Test mechanisms such as consultation and engagement of communities and local stakeholders at a small scale first (through field projects)
Delays in the adoption of a suitable legal framework for ICZM | Use GCCA-financed communication and advocacy activities to encourage policy makers to move to the adoption of a law on coastal zone management

## Slide 8: Challenges and responses specific to CZM (2)
Challenges | Responses / Success factors
Resistance to “retreat” options | Locate new physical and social infrastructure away from low-lying coastal areas to provide incentives for gradual resettlement When resettlement becomes unavoidable, accompany it with support measures – but this is can be expensive...
Sand extraction from beaches compounds the effects of sea level rise, resulting in severe coastal erosion | Develop inland sand quarries (if possible in the vicinity of major human settlements) If inland sand extraction not an option, dredge sand from the sea bed away from the coast Promote building techniques that make less or no use of sand