## Slide 1: Joint Programming
How are we doing?
Andy Benfield, 27/11/2012

## Slide 2
Progress

## Slide 3
1. Joint Country Analysis
2. Joint EU Programming Document
Response to national plan, aligned to its duration. Format up to HoMs but including: priorities, common positions, DoL, indicative sector funding
3. Individual bilateral implementation plans
(not strategies)
Up to you.

## Slide 4
Afghanistan Bangladesh Ethiopia Ghana Guatemala
Laos Mali Moldova Rwanda Tunisia Ukraine

## Slide 5
E t h i o p i a
We have a Joint Cooperation Strategy…
Additional work on sync, DoL, €, country strategies
“Paves the way”, “lays the building blocks”, Roadmap coming up
GoE now on board

## Slide 6
G h a n a
Have a GoG-DP Compact, incl. analysis
Preparing a Joint Framework Document
Joint implementation plan?
Incorporating bilateral country strategies?
DoL, first steps to sync (new strategies in 2011)
GoG on board

## Slide 7
G u a t e m a l a
Joint analysis & draft JP doc done
DoL & allocations
Common positions, aid effectiveness, monitoring
Sync agreed (elections +1)

## Slide 8
L a o s
Meetings & Retreat got traction
Joint analysis done
Transitional 2014-15, Full 2016-20
DoL & Sync from 2016

## Slide 9
M a l i
Wait and see – groundwork done
Joint positions
National vs sector cycles

## Slide 10
R w a n d a
Strong Gov
GoR wants 3 x JPs
Existing DoL
EU doing joint analysis
Sync – planning vs. financing
Waiting for new national strategy
Strengthens policy dialogue?

## Slide 11
B a n g l a d e s h
We have a Joint Cooperation Strategy
Need a capitals decision for sync & DoL
End of 2015?

## Slide 12
T u n i s i a
A great idea, but we need instructions from HQ…
Post-Arab Spring MS
Some support “has to stay as a bilateral activity without coordination with other partners”
Elections next year, so maybe 2014?
By end of 2012: Road map? Start joint analysis? Define support needs?

## Slide 13
A f g h a n i s t a n
It’s complicated…
JP sounds difficult, time-consuming but…what does it actually mean?
Want capitals consensus, guidance & lessons learned
2015-6?
Already have joint initiatives, common voice

## Slide 14
M o l d o v a
We’re different
“Would need more reflection and political will from MS capitals”
Weak GoM leadership
“If and when the guidelines are clearer”
Request for roadmap

## Slide 15
U k r a i n e
“Please remove us from the list”
“Difficult to see where the fundamental building blocks needed to implement such a programme are located”
Not until Government can lead, decent national plan
Will work on coordination, DoL, maybe joint analysis

## Slide 16
Ethiopia
Ghana
Guatemala
Laos
Mali
Rwanda
Bangladesh
Tunisia
Afghanistan
Moldova
Ukraine

## Slide 17
Support

## Slide 18
Clarify

## Slide 19: Reference

## Slide 20: Reference
“Will increase coherence, impact and leverage vis-à-vis other donors”
“Essential to move ahead on JP…should resolve the problem of DoL”
“Decentralise decision making, ensure light structures”
“Adapt to situation on the ground, not Brussels-led”
“Country-led approach, HoMs should play key role”

## Slide 21
1: Brussels will decide what we do
2: EU MS not present on the ground will decide what we do
3: We’ll have to use EU templates, procedures & timetables
4: I’ll have to scrap my bilateral implementation plan
5: All our projects will have to be implemented jointly & simultaneously
Reassure

## Slide 22
P a r t n e r C o u n t r y
Ownership & alignment 
Predictability & transparency 
Aid fragmentation 
Transaction costs 
Cash doesn’t 
D o n o r s
Influence 
Ability & willingness to do DoL 
Pressure to do everything myself 
Bang per buck 
Rationale

## Slide 23
Chart: 
| 1992.0 | 1993.0 | 1994.0 | 1995.0 | 1996.0 | 1997.0 | 1998.0 | 1999.0 | 2000.0 | 2001.0 | 2002.0 | 2003.0 | 2004.0 | 2005.0 | 2006.0 | 2007.0 | 2008.0 | 2009.0 | 2010.0 | 2011.0
EU | 34 | 29 | 23 | 30 | 32 | 27 | 28 | 23 | 23 | 21 | 20 | 21 | 19 | 21 | 22 | 20 | 20 | 20 | 18 | 16
China | 0 | 0 | 2 | 1 | 2 | 2 | 3 | 1 | 1 | 3 | 1 | 1 | 6 | 8 | 7 | 12 | 10 | 11 | 13 | 17
Cambodia: EU vs. China: Share of Aid
Rationale

## Slide 24
Practicalities – JP doc

## Slide 25
 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
GoL | NSEDP-7 |  |  |  |  | NSEDP-8 |  |  |  | 
EU | << |  |  |  |  |  |  |  |  | 
Finland |  |  |  |  |  |  |  |  |  | 
France | << |  |  |  |  |  |  |  |  | 
Germany |  |  |  |  |  |  |  |  |  | 
Hungary |  |  |  |  |  |  |  |  |  | 
Ireland |  |  |  |  |  |  |  |  |  | 
L'bourg |  |  |  |  |  |  |  |  |  | 
Practicalities - sync

## Slide 26
Practicalities - DoL

## Slide 27
Practicalities – knowledge sharing

## Slide 28
Challenges
Knowledge of what it means & involves
Need for practical examples
Knowledge of capitals’ commitments
Cycles & sectors set by HQs?
Planning vs. financing
Control, visibility
Concerns about workload

## Slide 29
1. Comments on countries?
2. Experiences to share?
3. How can we improve our general support? (guidelines, FAQs/LLs, website, share instructions, JP study update?)
4. Pre and post mission liaison?
5. What does a focus on results mean for DoL?
Over to You

## Slide 30: Joint Programming
Policy & Practice
Thank you! For more please see:
http://capacity4dev.ec.europa.eu/joint-programming/
consultancy@andybenfield.com