Potential Challenges and Suggested Mitigation Strategies

| Challenge | Degree | Mitigation Strategy |
| --- | --- | --- |
| Obtaining reliable data for planning & monitoring | High | - Strengthen national capacity - Triangulate data to check quality - Use non-state data sources (as a secondary option) - Gather more information in the form of feedback at the local level - Improve data sharing among donors |
| Agreeing a division of labour | High | - Base division of labour agreement on solid analysis of current fragmentation and comparative advantages, including of non-EU donors - While using three sectors per donor as a guide, also take into account other factors when deciding whether aid to a sector is complementary or fragmentary, such as sector profile (size, needs and current interventions) and approach pursued (contributing to a joint programme vs. establishing a bilateral one) - Low risk sectors: trade, environment, infrastructure, macro-economic support, private sector development - Higher risk sectors: agriculture / rural development, education, governance, health, UXOs - Where several donors want to work in the same sector, establishing a new joint initiative may offer an appropriate solution, e.g. support to civil society, UXOs |
| Potential lack of reliability in GoL timing which donors will be synchronising to | Medium | - Sensitisation of GoL to the synchronisation and the risk of holding up aid should the national strategy be delayed - Regular dialogue with GoL to check on progress and any potential problems - Encouragement of non-EU donors to also synchronise to the national cycle in order to increase the incentives for GoL to stay on schedule |
| Impact of the financial crisis on predictability of ODA | Medium | - Ensure back-up donors (including non-EU) are in place where possible - Make sure any funding cuts / exits are notified to GoL and donors as early as possible - Require a higher percentage of counterpart funding in initiatives |
| Challenge | Degree | Mitigation Strategy |
| Lack of control over some aid at the local level, e.g. vertical / thematic programmes | Medium | - Limit joint programming to aid that is controlled. - Request capitals to reduce uncontrolled aid / only provide it to the donor in question’s agreed focal sectors in Laos / channel it through existing initiatives on the ground |
| Capacity and power of local donor offices to take the process forward | Medium | - Ensure clear lines of communication and decision-making between capitals and field offices as well as a common understanding of joint programming - Sensitise capitals to the need to provide technical assistance for tasks such as analysis and the drafting of the joint strategy document |
| Ensuring GoL buy-in | Medium | - Market the advantages for GoL including reduced transaction costs, more coherent support and alignment to national timing and goals - Keep GoL updated throughout the process and invite their feedback |
| Approach to other donors | Low | - Keep other donors informed on the process (including at Round Table meetings) and invite them to participate once a common approach has been agreed among the EU donors - Suggest that all donors synchronise to the national planning cycle - Agree common EU positions within Sector Working Groups - Stay informed on how this issue is managed in other countries |
| Ensuring support of home Governments (both present and future) | Low | - Market the advantages of joint programming in terms of value for money, holistic coverage, providing new opportunities for political dialogue and leverage, and increasing European weight vis-a-vis non-traditional donors |
| Maintaining flexibility | Low | - Mid-term review of programme with potential to adjust approach, sectors and financial allocations if required - Establishment of a joint contingency fund to finance unforeseen needs |
| Synchronising timing | Low | - De-linking of planning and financing cycles - Acceptance that implementation of individual initiatives may span boundaries between strategy periods |
| Change in Lao Government | Low | - Maintain dialogue to keep abreast of any potential instability |