# Examples of complementary evaluation questions

(AFD document)

The following questions are indicative. Most of them are coming from the European Commission  or from the Evaluation Unit of the DGCID (General Directorate for International Cooperation and Development) of the French Ministry of Foreign Affairs.

They can support the evaluation manager in refining his/her expectations in the evaluation process. Nevertheless, taking into account the scope of the evaluation and the technical limits that could prevent bringing quality answers to an unreasonable number of evaluation questions, it is recommended to limit the number of questions requested in the ToR of the evaluation.

## 1. Relevance related questions

The degree of relevance of the project//programme can be assessed using the following questions:

- Are the groups / beneficiaries targeted by the project the real beneficiaries of the project ?

- If necessary: To what extent has the management of the project adjusted the project design (including the intervention logic) in order to make it more relevant?

- Are the elements mentioned in the current project intervention logic appropriate and relevant? (elements to be considered: inputs, activities, results, project purpose, overall objective, assumptions)

- Do the project purpose and the overall objectives correspond to existing policies and sector programmes of the partner government? Do they support these policies and programmes?

- To what extent the conclusions and recommendations made during previous monitoring or evaluations have been taken into account to strengthen project relevance?

## 2. Effectiveness related questions

The degree of effectiveness of the project/programme during its implementation can be assessed using the following questions:

- Do all targeted beneficiaries have access to the project results and services?

- Are targeted beneficiaries using and benefiting from the project results and services?

- Through the current implementation strategy, is the project purpose likely to be achieved (to the extent planned by the objectively verifiable indicators) ?

  - To what extent the project has been adapted or has been designed to be adapted according to external conditions constantly evolving (assumptions) so that the flow of benefits to the beneficiaries remains continuous.

  - If the target groups/beneficiaries have suffered from unexpected negative effects from the project, has the project management taken appropriate measures?

  - To what extent have unexpected positive effects influenced the quality of results and services offered by the project?

- To what extent the conclusions and recommendations made during previous monitoring or evaluations have been taken into account to enhance the achievement of the project purpose?

## 3. Efficiency related questions

Efficiency can be assessed using the following questions :

- Availability of means and resources

  - Are means and resources delivered or made available by all parties in charge within the expected timeframe so that all planned activities can be implemented?

  - Are means delivered or made available by all parties in charge at the expected cost (or less)?

  - Are resources appropriately monitored to allow for an efficient implementation of activities?

  - Are project resources managed in a way that is transparent and liable enough to promote a fair and sustainable development?

  - To what extent the conclusions and recommendations made during previous monitoring or evaluations have been taken into account to make project means and resources more appropriate?

- Implementation of activities

  - Are activity and resources schedules made available and are they used by the project management?

  - To what extent are activities implemented according to plan?

  - Are activities subjected to a regular and satisfying monitoring? Are correcting measures taken when necessary (when new activities have to be implemented because of new needs emerging or because of activities cancellation).

  - To what extent the conclusions and recommendations made during previous monitoring or evaluations have been taken into account to improve the quality of activity implementation?

- Obtaining results

  - Have the objectively verifiable indicators (objectives and targets mentioned in the logical framework matrix) been reached according to plan?

  - Could all expected results be achieved?

  - What is the quality of results obtained so far?

  - Is the achievement of results properly and regularly monitored ? Are correcting measures taken when necessary?

  - To what extent the conclusions and recommendations made during previous monitoring or evaluations have been taken into account to improve the achievement and quality of results?

- Partner contribution / involvement

  - Are inter-institutional bodies appropriate to allow for an efficient project implementation

  - Could all partners involved bring their contribution to the project?

  - Is the communication between decision makers of the partner government, the funding agency and the project management satisfying and regular enough?

## 4. Impact related questions

- Considering the current implementation conditions and process, is the project likely to have a positive impact on a wider scale?

- Are the assumption related to the project purpose and overall objectives likely to be verified so that the impact of the project will not be hindered by external factors? (Sector and donor coordination should also be specifically assessed in that sense)

- To what extent is the project monitoring staff

  - assessing the positive and/or negative impacts of the project on the sector/ and/or society

  - able to take appropriate measures to increase positive impacts and reduce negative impacts of the project?

- To what extent the conclusions and recommendations made during previous monitoring or evaluations have been taken into account to improve the project impact?

## 5. Sustainability related questions

- Financial / economic sustainability

  - If an institutional support to project services and results is needed, are the necessary funds going to be made available?

  - Are the services proposed at the end of project implementation period having an affordable cost for the final beneficiaries?

  - Do persons and institutions in charge fulfil their economic and financial responsibilities?

  - Could project benefits be maintained in case of any fluctuation of economic factors (commodity prices, exchange rates…)?

  - Are the beneficiaries (and relevant authorities / institutions) able to cover the running and maintenance costs related to the technologies introduced by the project?

  - Has any exit strategy been identified and implemented?

- Current degree of ownership on the project by beneficiaries and potential evolution when external aid will be over?

  - To what extent is the project integrated into community/local bodies?

  - To what extent have beneficiaries and other stakeholders participated to the planning process?

  - To what extent have relevant target groups and beneficiaries been actively involved in the decision making process concerning project orientation and implementation?

  - Are target groups / beneficiaries likely to continue using the proposed services once the external aid is over?

- What kind of political support has been provided and what is the level of interaction between the project and policy makers?

  - What kind of support has been received from the national, sector and budgetary policies?

  - Did changes in policies and priorities have an impact on the project? Does the project adjust itself to it and does it take into account the need for a long term support?

  - To what extent has the project been supported by the private and public sectors? How does the project contribute to the democratisation process (promoting participation, accountability and Human rights)?

  - To what extent is the project strengthening the role of non state actors as partners in policy making and policy implementation?

- To what extent does the project contribute to institutional and administrative capacity strengthening ?

  - Is the project integrated into institutional patterns that will persist after project completion?

  - Are project partners adequately trained to ensure project take over (taking over technical, financial and administrative matters)?

  - What is the degree of availability of qualified human resources able to implement the project, compared to initial plans?

  - Are there good relationships with institutions that are new or already in place? Are these relationships able to maintain a sustainable flow of benefits?

  - Has any exit strategy been identified and implemented?

## 6. Questions on cross-cutting issues

- Does the project take into account socio-cultural aspects ?

  - Is the project in line with the perception local populations have of their needs?

  - What is the level of participation of beneficiaries in the project design and implementation?

  - Does the project respect local habits? Have the changes brought by the project been accepted?

  - Are there good relationships between project management, beneficiaries and their representatives?

- How does the project take into account gender equality ?

  - Do project content and methodology reflect a gender-sensitive approach?

  - Has the project been designed according to a gender-sensitive analysis of target groups and beneficiaries?

  - Have the practical and strategic interests of men and women been taken into account in designing project strategy?

  - Do the respective interests of men and women reflect into project implementation at the level of target groups, institutions and policy?

  - Is the gender equality likely to be enhanced after project completion?

  - To what extent a gender-sensitive approach is likely to lead to a wider impact of the project?

- Are technologies introduced and used by the project appropriate enough ?

  - Are these technologies flexible and understandable enough?

  - To what extent are these technologies drawing their inspiration from current knowledge and capacities?

  - Do these technologies contribute to the strengthening of local knowledge and capacities?

  - Do these technologies manage to maximise the use of local resources?

- To what extent are environmental issues taken into account?

  - Does the project respect environmental needs?

  - Does the project manage to take its environmental responsibilities?

  - Are beneficiaries and stakeholders informed of the environmental responsibilities  falling to the project?

  - Have environmental damages been incurred by the project (or are there environmental damages likely to be incurred)? What kind of protective measures have been taken?

  - To what extent is the project respecting traditional environment-friendly practices that have been successfully experimented?

http://ec.europa.eu/europeaid/index_fr.htm

www.diplomatie.gouv.fr/fr/ministere_817/missions-organisation_823/structure-administration-centrale_808/direction-generale-cooperation-internationale-du-developpement_3146/index.html