Evaluation Questions

This document proposes an indicative list of issues which deserve to be studied in a project/programme evaluation. The evaluation should focus on a limited number of precise issues/questions. It should ensure that there is a balance of evaluation criteria.

Further guidance on evaluation questions for the following sectores - health, education, transports, rural development, water and sanitation - is available on (Intra net) the following link

http://www.cc.cec/dgintranet/europeaid/activities/evaluation/sec_en.htm

The appropriate evaluation questions and sub questions, based on this set of issues, should be elaborated for each project/ programme evaluation case.

## 3.1 Problems and needs (Relevance)

The extent to which the objectives of the development intervention (projects/ programme) are consistent with beneficiaries' requirements, country needs, global priorities and partners' and EC's policies.

The analysis of relevance will focus on the following questions in relation to the design of the project:

- the extent to which the project has been consistent with, and supportive of, the policy and programme framework within which the project is placed, in particular the EC’s Country Strategy Paper and National Indicative Programme, and the Partner Government’s development policy and sector policies

- the quality of the analyses of lessons learnt from past experience, and of sustainability issues;

- the project's coherence with current/on going initiatives;

- the quality of the problem analysis and the project's intervention logic and logical framework matrix, appropriateness of the objectively verifiable indicators of achievement;

- the extent to which stated objectives correctly address the identified problems and social needs, clarity and internal consistency of the stated objectives;

- the extent to which the nature of the problems originally identified have changed

- the extent to which objectives have been updated in order to adapt to changes in the context;

- the degree of flexibility and adaptability to facilitate rapid responses to changes in circumstances;

- the quality of the identification of key stakeholders and target groups (including gender analysis and analysis of vulnerable groups) and of institutional capacity issues;

- the stakeholder participation in the design and in the management/implementation of the project, the level of local ownership, absorption and implementation capacity;

- the quality of the analysis of strategic options, of the justification of the recommended implementation strategy, and of management and coordination arrangements;

- the realism in the choice and quantity of inputs (financial, human and administrative resources)

- the analysis of assumptions and risks;

- the appropriateness of the recommended monitoring and evaluation arrangements ;

## 3.2 Achievement of purpose (Effectiveness)

The effectiveness criterion, concerns how far the project’s results were attained, and the project’s specific objective(s) achieved, or are expected to be achieved.

The analysis of Effectiveness will therefore focus on such issues as:

- whether the planned benefits have been delivered and received, as perceived by all key stakeholders (including women and men and specific vulnerable groups);

- whether intended beneficiaries participated in the intervention

- in institutional reform projects, whether behavioural patterns have changed in the beneficiary organisations or groups at various levels; and how far the changed institutional arrangements and characteristics have produced the planned improvements (e.g. in communications, productivity, ability to generate actions which lead to economic and social development);

- if the assumptions and risk assessments at results level turned out to be inadequate or invalid, or unforeseen external factors intervened, how flexibly management has adapted to ensure that the results would still achieve the purpose; and how well has it been supported in this by key stakeholders including Government, Commission (HQ and locally), etc.;

- whether the balance of responsibilities between the various stakeholders was appropriate, which accompanying measures have been taken by the partner authorities;

- how unintended results have affected the benefits received positively or negatively and 	could have been foreseen and managed.;

- whether any shortcomings  were due to a failure to take account of cross-cutting or over-arching issues such as gender, environment and poverty during implementation;

## 3.3 Sound management and value for money (Efficiency)

The efficiency criterion concerns how well the various activities transformed the available resources into the intended results (sometimes referred to as outputs), in terms of quantity, quality and timeliness. Comparison should be made against what was planned.

The assessment of Efficiency will therefore focus on such issues as:

- the quality of day-to-day management, for example in:

  - operational work planning and implementation (input delivery, activity management and delivery of outputs),and management of the budget (including cost control and whether an inadequate budget was a factor);

  - management of personnel, information, property, etc,

  - whether management of risk has been adequate, i.e. whether flexibility has been demonstrated in response to changes in circumstances;

  - relations/coordination with local authorities, institutions, beneficiaries, other donors;

  - the quality of information management and reporting, and the extent to which key stakeholders have been kept adequately informed of project activities (including beneficiaries/target groups);

  - respect for deadlines;

    - Extent to which the costs of the project have been justified by the benefits whether or not expressed in monetary terms in comparison with similar projects or known alternative approaches, taking account of contextual differences and eliminating market distortions.

- Partner country contributions from local institutions and government (e.g offices, experts, reports, tax exemption, as set out in the LogFrame resource schedule), target beneficiaries and other local parties: have they  been provided as planned?

- Commission HQ/Delegation inputs (e.g. procurement, training, contracting, either direct or via consultants/bureaux): have they been provided as planned?;

- Technical assistance: how well did it help to provide appropriate solutions and develop local capacities to define and produce results?

- Quality of monitoring: its existence (or not), accuracy and flexibility, and the use made of it; adequacy of baseline information;

- Did any unplanned outputs arise from the activities so far?

## 3.4 Achievement of wider effects (Impact)

The term impact denotes the relationship between the project’s specific and overall objectives.

At Impact level the final or ex-post evaluation will make an analysis of the following aspects:

- Extent to which the objectives of the project have been achieved as intended in particular the project planned overall objective.

- whether the effects of the project:

- have been facilitated/constrained by external factors

- have produced any unintended or unexpected impacts, and if so how have these affected the overall impact.

- have been facilitated/constrained by project/programme management, by co-ordination arrangements, by the participation of relevant stakeholders

- have contributed to economic and social development

- have contributed to poverty reduction

- have made a difference in terms of cross-cutting issues like gender equality, environment, good governance, conflict prevention etc.

- were spread between economic growth, salaries and wages, foreign exchange, and budget.

## 3.5 Likely continuation of achieved results (Sustainability)

The sustainability criterion relates to whether the positive outcomes of the project and the flow of benefits are likely to continue after external funding ends or non funding support interventions (such as: policy dialogue, coordination).

The final evaluation will make an assessment of the prospects for the sustainability of benefits on basis of the following issues:

- the ownership of objectives and achievements, e.g. how far all stakeholders were consulted on the objectives from the outset, and whether they agreed with them and continue to remain in agreement;

- policy support and the responsibility of the beneficiary institutions, e.g. how far donor policy and national policy are corresponding,  the potential effects of any policy changes; how far the relevant national, sectoral and budgetary policies and priorities are affecting the project positively or adversely; and the level of support from governmental, public, business and civil society organizations.

- institutional capacity, e.g. of the Government (e.g. through policy and budgetary support) and counterpart institutions; the extent to which the project is embedded in local institutional structures; if it involved creating a new institution, how far good relations with existing institutions have been established; whether the institution appears likely to be capable of  continuing the flow of benefits after the project ends (is it well-led, with adequate and trained staff, sufficient budget and equipment?); whether counterparts have been properly prepared for taking over, technically, financially and managerially;

- the adequacy of the project budget for its purpose particularly phasing out prospects;

- socio-cultural factors, e.g. whether the project is in tune with local perceptions of needs and of ways of producing and sharing benefits; whether it respects local power- structures, status systems and beliefs, and if it sought to change any of those, how well-accepted are the changes both by the target group and by others; how well it is based on an analysis of such factors, including target group/ beneficiary participation in design and implementation; and the quality of relations between the external project staff and local communities.

- financial sustainability, e.g. whether the products or services being provided are affordable for the intended beneficiaries and are likely to remained so after funding will end; whether enough funds are available to cover all costs (including recurrent costs), and continued to do so after funding will end; and economic sustainability, i.e. how well do the benefits (returns) compare to those on similar undertakings once market distortions are eliminated.

- technical (technology) issues, e.g. whether (i) the technology, knowledge, process or service  introduced or provided fits in with existing needs, culture, traditions, skills or knowledge; (ii) alternative technologies are being considered, where possible; and (iii) the degree in which the  beneficiaries have been able to adapt to and maintain the technology acquired without further assistance.

- Wherever relevant, cross-cutting issues such as gender equity, environmental impact and good governance; were appropriately accounted for and managed from the outset of the project.

## 3.6 Mutual reinforcement (coherence)

The extent to which activities undertaken allow the European Commission to achieve its development policy objectives without internal contradiction or without contradiction with other Community policies. Extent to which they complement partner country's policies and other donors' interventions.

Considering other related activities undertaken by Government or other donors, at the same level or at a higher level:

- likeliness that results and impacts will mutually reinforce one another

- likeliness that results and impacts will  duplicate or conflict with one another

Connection to higher level policies (coherence)

Extent to which the project/programme (its objectives, targeted beneficiaries, timing, etc .):

- is likely to contribute to / contradict other EC policies

- is in line with evolving strategies of the EC and its partners

## 3.7 EC value added

Connection to the interventions of Member States. Extent to which the project/programme (its objectives, targeted beneficiaries, timing, etc .)

- is complementary to the intervention of EU Member States in the region/country/area

- is co-ordinated with the intervention of EU Member States in the region/country/area

- is creating actual synergy (or duplication) with the intervention of EU Member States

- involves concerted efforts by EU Member States and the EC to optimise synergies and avoid duplication.

/tmp/in/input.doc