## Slide 1: EXPERIENCE OF THE ETHIOPIAN PRODUCTIVE SAFETY NET PROGRAMME
Presented at the AIDCO seminar on:
"AIDCO DEL - Food Security South and East Africa "
3-7 November 2008, Maputo
Prepared by EC Delegation to Ethiopia
RDFS Section

## Slide 2: Outline
Ethiopia & the EC
Overview of the PSNP
Outcomes after 4 years implementation: achievements and constraints
Analysis of main aspects of the programme:
  Public works
  Programme size and cost
  Chronic and transitory needs
  Graduation
  Institutional arrangements

## Slide 3: Main production systems in Ethiopia

## Slide 4: EC support to FS in Ethiopia
1996-2000: Food Aid and Food Security BL > 370M€ including 1M MT in Food Aid
IX EDF and FSBL: 98M€
X EDF:
  A Envelope: 100 M € (42 in pipeline)
  B Envelope: 20 M €: 2008 Additional support
  20 M €: Agricultural markets and livestock development
  10 M €: NRM sector

## Slide 5: PSNP overview
Timeframe: | January 2005 - December 2009
Coverage: | 5 million to 7.3 beneficiaries, 7 Regions out of 10, 286 districts out of 500
Cost: | 220 mln Euro / year (cash+food)
Objectives: | Shift from emergency to a predictable system; smoothing food consumption & protecting assets; stimulating markets; enhancing environment
Components: | Public Work programme (PW) Direct Support Links to “OFSP” / HH packages program
Notes: PW ~ 6.3 million benef.
DS ~ 1 million benef

## Slide 6: PSNP overview
Principles: | Predictable transfers & needs (6 m/year) Cash first principle Beneficiaries “graduate” off the PSNP when they achieve “food sufficiency”
Multi Donors Trust Fund managed by the WB. Donors: WB, EC, DFID, Canadian CIDA, Swedish SIDA, Irish Coop., USAID, WFP, Dutch coop. | 
Institutional framework: Ministry of Agriculture: FS Dept., EW Dept., NR Dept. Ministry of Finance | 
Notes: MoARD: technical management and implementation, food management and distribution
MoFED: financial management

## Slide 7: Coverage of PSNP

## Slide 8: Achieving PSNP outcomes
Year-on-year improvement in the timeliness & predictability of transfers
National structures have increased their capacity
PSNP beneficiaries are protecting assets, and in some cases increasing income
Approx 34,000 PW projects implemented annually, of which most have management mechanisms and are technically satisfactory
PW projects stimulate access to services and markets and enhance environments
Notes: In terms of outcomes, the programme showed to be on track and proved to be able to support asset protection…
National structures have adapted and increased their capacity to deliver the programme at all levels.
The programme implemented a quite impressive number of PW projects, and the PW review and assessment missions provided elements to state that most of them have management mechanisms, are technically satisfactory, contribute stimulating access to social services and markets and enhancing environments

## Slide 9: Summary of constraints
Food and cash transfer undermined by persistent problems in both management and delivery
High food prices inflation eroded purchasing power of cash transfers eroded. Exacerbated by drought in part of the country
Weak M&E system and technical reporting
Transitory needs: contingency budget insufficient. Better coordination with the emergency mechanism required

## Slide 10: Summary of constraints
PW screening for environmental & social criteria of PW still weak
Management capacity still low
Improvement in coordination within Gvt system required
Enhanced coordination and synergies for graduation needed, with OFSP and with other programmes and investments
Low “graduation” figures
Notes: Management capacity of PW, agreed structures not put in place
Despite significant capacity building initiatives, problems persist and are addressed on an ad hoc basis

## Slide 11: Institutional Arrangements
MoFED
NRD
FSPD
EWRD
MoARD
PW
Overall Coord of the FSP
Food & Relief
Extension
Field implem (DAs)
Cash transfers
Joint Coord. Committee
Donors
Regions
NR Sector
DM&FS Sector
Agr Dev Sector
(Quarterly)
Task Forces
Joint Reviews
RRM

## Slide 12: Institutional Arrangements
Need to ensure inter-departmental and inter-ministerial coordination (Ministries, Regions, Zones, Woreda, Kebele)
High-level Gvt management team for PSNP (State Ministers of MOARD; MOFED; Regional Representation) needed
Higher forum for policy issues needed

## Slide 13: Investments for graduation at scale
Graduation: the goal PSNP contribute to
HH graduated to date low (26.000 HH)
Stronger evidence base to inform effective approach and investments needed
Linkages with the growth agenda, institutional arrangement and adequate resourcing required
Notes: Therefore GoE and development partners have embarked on a process to design another five year phase of the programme

## Slide 14: Investments for graduation at scale
DS
PW
Productive Safety Net Programme
Other Food Security Programme
Resettlement Programme
Food Insecure Households
Food Security
GoE Food Security Programme
Enabling
environment

## Slide 15: Investments for graduation at scale
0-1 month good gap
Graduation from PSNP
Food Security
Graduation from FSP
Graduation from Poverty
OFSP Only
Time
Food Security Status
Food insufficiency
Food sufficiency
PSNP + OFSP
Notes: On going FSP review

## Slide 16: Programme size and cost
The size of the Programme may need to respond to:
  the chronic caseload (difficult targeting, exclusion errors)
  the potential/temporary increase of chronically food insecure households arising from drought and/or food price inflation, and
  population growth

## Slide 17: Programme size and cost
Wage rate increased to 10 birr; trigger in January
Mixed transfer of 3 months food and 3 months cash
‘Variable levels of support’
Linkages with the emergency system
Notes: Since 2007 food inflation has become an issue also for the management of the PSNP and 2008 in particular has been a difficult one also due to the drought in part of the country.
High food-price inflation has reintroduced an imbalance in the value between cash and food transfers, and undermines the cash-first principle, making cash transfers obviously much less attractive for the PSNP beneficiaries.
Increase the wr to 10 Birr, and this decision will be revisited in January 2009 to assess if food prices have fallen to the anticipated level or whether a further upward adjustment of the wage rate is necessary. (The anticipated level is defined as maize prices between 300-350 birr per quintal on average in PSNP markets. explicit references in the Aide memoire to the need for the Programme to closely monitor prices and food availability in PSNP woreda markets. Sources for the data include the FSPD Information Centre and EWRD price data.)
As a risk mitigation measure, the Programme will provide three months of cash and then three months of food transfers, as appropriate and when the actual condition to smoothly implement the shift are fulfilled.

## Slide 18: Programme size and cost
 | 2005 | 2006 | 2006/07 | 2007/08 | 2008/09 | 2009/10
 | Jan-Dec | Jan-Jun | Jul-Jun | Jul-Jun | Jul-Jun | Jul-Jun
Cash | 65 | 102 | 157 | 217 | 250 | 183
Food | 219 | 245 | 310 | 336 | 400 | 305
Cash: M USD
Food: MT x 1000

## Slide 19: Public Works
PSNP PW are important investment in rural areas
Projects integrated into wider woreda planning and management process
Maintenance ensured in most cases (problems with roads and small irrigation schemes)
Some SWC projects are having positive environmental impact
Inadequate database on PW and on performance of PW project for measurement of indicators (M&E)
Notes: PSNP PW are an important investment in rural areas; they are the main component of the programme and also in financial terms PSNP represents a relevant part of the resources available at woreda level.

## Slide 20: Transitory needs
Three instruments:
  Contingency budget (20% of PSNP budget)
  Risk financing Facility
  Emergency system
In 2008, delays in the response caused by:
  confusion over the availability of resources,
  weak coordination between the responsible bodies
  lack of food in the national reserve - EFSRA
Notes: CB: continued use of the contingency to cover additional chronically food insecure individuals,

## Slide 21: Transitory needs
1. Pre-PSNP
Relief system to meet chronic and transitory needs
Saved lives but not livelihoods; inappropriate for chronic food insecurity
2. Now
Chronic needs: PSNP
Transitory needs:
PSNP contingency
Risk Financing
Relief system.
Still unharmonized response to transitory needs
3. Future
Chronic needs: PSNP
Transitory needs:
Harmonized and sequenced instruments.
Clear rules, roles and responsibilities
PSNP | PSNP CB+RF | Relief
Chronic | Transitory

## Slide 22: Thank You

## Slide 23: USAID Assessment – October 2008

## Slide 24: EFSRA
Lack of stock within the EFSRA impacted both the Emergency response and the PSNP
Dialogue with GoE and donors to reconfirm the original purpose and function

## Slide 25: To add
1. EC's support to interventions in food security in Ethiopia before the PSNP
2. EC's overall resource contribution to the PSNP
3. List of donors that support the PSNP
4. Type of resources transferred to beneficiaries through the programme (cash/food and amount)
5. Management structure of the PSNP - FSPD responsible for physical activities while MoFED responsible for financial management