## Slide 1: Supporting change through Capacity Development
Module 3:
Fit to the context and existing capacity
Where do we start from?

## Slide 2: Quality Criteria are guiding CD support
Quality EC
Capacity
Development
2.
Adequate demand, and ownership
1.
Fit to the context and existing capacity
4.
3.
Clear link to results and outcomes
5.
Appropriate
PIAs
Harmonised support
Notes: The first three slides of this module are to present an overview of the QCs and how it relates to other instruments

## Slide 3: How the QC are applied in PCM
The EC has developed tools for monitoring the quality of implementation, which provide the framework for good design
  The QSG (Quality Grid)
  The ROM
  The annual EAMR
  RAC evaluation
The novelty of the EC approach lies in translating the Development Effectiveness principles into quality criteria to be mainstreamed into the EC Project Cycle and be monitored regularly

## Slide 4: CD Quality Grid requirement: 1. Fit to the context and existing capacity
1.1 Are there critical constraints in the context which could make TC ineffective and impede achieving the purpose of the TC? If yes, how will they be addressed?
1.2 Has the existing capacity of the concerned partner(s) organisation(s) been assessed? Is it confirmed that the objectives and the scope of the TC support match the existing capacity to lead, manage and absorb the support?
1.3 How have similar programmes and types of TC worked in the current context? Please indicate which, if any, and why they have been successful.
Notes: More than one option possible (see section 2.2 and 4.1 of the Guidelines)

## Slide 5: Why is this criteria important?
Don’t waste resources
Best fit to context and capacity
Avoid ‘parallelism’
Notes: Parallelism = too many overlapping (and sometimes competing) programmes
Sometimes these context analyses are done by technical staff/TA with sector knowledge, not always involving political-economy expertise, making the resulting conclusions less relevant for subsequent programming

## Slide 6: Assessment - a key task:
Initial assessment
Design
Re-assessment
Re-design
And so on
  Throughout the life of programme, not just design
  To ensure relevance, determine feasibility, allow for adaptation, monitor progress
  Ensure linkages with the (policy) dialogue
Notes: Context assessment and its linkages with programme design and implementation is a recurrent issue in the cooperation between partner and donor. Technical and policy dialogue are the vehicles.

## Slide 7: Assessing Context
Contextual factors beyond influence
Contextual factors and actors within influence
Wider impact
Outcomes
Outputs
Capacity
Recurrent inputs
CD processes
CD support
Internal resources

## Slide 8: Three context assessment tools
Political Economy Analysis:
  Methodology for analysing the “space” for reform
  Specific guidance available: PPCM and Cap4Dev practice group
  Will generate drivers, opportunities and constraints
Opportunity Framework:
  A way to look at broad geo-political and socio-economic processes providing reform “windows”
Stakeholder Mapping
  Sector Governance mapping produced by EC in sector guidance
  Multiple tools and methods available on internet/ resource books
  Power/influence, formal/informal
BUT NO SUBSTITUTE FOR SUSTAINED ENGAGEMENT AND BUILDING OF SOUND RELATIONSHIPS
Notes: Also mention the role of culture as a topic under PEA
Change this slide

## Slide 9: Assessing Capacity
Contextual factors beyond influence
Contextual factors and actors within influence
Wider impact
Outcomes
Outputs
Capacity
Recurrent inputs
CD processes
CD support
Internal resources

## Slide 10: Assessing Capacity: multiple purposes
  As a design tool to build results framework for an intervention
  As a self-administered health check for organisational learning and ownership for change
  As a way to engage in a dialogue on need for change; find out who is doing what and where to start
  As a monitoring tool to track progress over time
  As a performance management tool to incentivise performance improvement
  As a tool to determine compliance and eligibility against set norms and standards

## Slide 11: Examples of assessment tools
Purpose | Instruments/tools
Organisational/ Sector Assessment | EC Toolkit for CD ECDPM 5Cs McKinsey’s 7s, Weisbord’s 6 boxes and OCAT IDRC Organisational Assessment EU 7 key areas of sector assessment
PFM reform and compliance / Governance assessment | EU 4 pillars PEFA ACBF Capacity Indicators CPIA/ World Bank Political-Economy Analysis
Customised theme or sector specific | UNOPS/ OECD Procurement Assessment County Capacity Readiness Assessment UNDP Disaster Risk Reduction …and many many more.
Notes: Provide hand-out with links to these tools.

## Slide 12: “Functional” and “political” dimension of capacity
 | Functional dimension | “Political” dimension
Main unit of analysis? Driving forces? Image of man? Change? Change efforts? | Focus on functional task-and-work system A sense of norms, intrinsic motivation Employees caring for the organisation Participative reasoning, finding best technical solution, orderly Internal systems, structures, skills, technology etc | Focus on power- and-loyalty systems Sanctions and rewards, incentives Individuals caring for themselves and their in-groups Internal conflict, coalition with powerful external agents, unpredictable Incentives, change of key staff, outsmarting opposition

## Slide 13: Some Good Practice Tips
  Keep it simple, avoid over-analysing, especially early on and risk to undermine trust and confidence
  Avoid focusing just on gaps and weaknesses; build on strengths and understand why things are the way they are
  Use and build on existing information, avoid intrusiveness
  Encourage self-assessment to promote ownership/ learning
  Watch out for assessment fatigue, timing crucial
Depending on purpose, opportunity, stage of process; analysis can range from simple, “quick and dirty” through to comprehensive and analytical
Analysis is also agenda setting
Notes: Remember: ANALYSIS is ALSO AGENDA SETTING; The ToR by its very nature shapes the type of problem being identified and in this context can be seen as political rather than technical: that is what problem is identified might appear a technical decision to the EU but if the partner disagrees then it will be seen as a political decision, e.g. analytical questions like ‘do you have sufficient capacity for …’ or ‘Is the coffee sector competitive enough’, ‘are European dairy farmers internationally competitive’: these are not neutral technical questions, they include political elements.

## Slide 14: An incremental approach to assessment
Where we are now
Extension and improvement would look like …
And then the next level would be …
Our capacity vision
Can provide the basis for specifying capacity results
Would maybe provide the basis for specifying the overall capacity objective

## Slide 15: What Role for the EC/ DPs?
  Invest in dialogue and relationship building
  Help build a constituency for change
  Provide technical expertise with respect to techniques and approaches
  Facilitate and support self-assessment
  Help establish baseline data about current capacity to enable effective monitoring and evaluation of results
  Explore opportunities to harmonise and align through coordination with other donors

## Slide 16: Your experiences with:
Context assessment as a continuous effort
Linking up with longer term development goals
Finding (neg. or pos.) incentives for CD
Cultural/historical influences on CD
Finding a constituency for change
Assessing the informal/political context