## Explanations
EXPLANATIONS on the FILE
1. ENRTP SCA Project Development
Objective: Monitor ENRTP project development
Tipping point: When projects are formally approved by the EC (through an e-mail of confirmation), they move to Sheet Nb.2. ENRTP Implementation Monitoring
Responsible staff: Sandrine Marquès
Status of document: Internal & Confidential OfO/EC
Column:
A | UNEP or MEA acronym: DELC, DTIE, BCONV, RCONV, SCONV, BRS (for synergy projects of Basel, Rotterdam, Stockholm Conventions), CBD, CITES, CMS, MAP
B | UNEP Sub-Programme or MEA equivalent: For UNEP: CC, DC, EG, EM, HSHW, RE. For MEA Secretariat: tbd
C | Project title: Insert project title as recorded in UNEP Project document (narrative part)
D | Project acronym: Insert project acronym (if existent) as recoreded in UNEP Project document (narrative part)
E | ENRTP Priority (1, 2, 3, 3.1, 3.3): Insert ENRTP Priority 1, 2, 3, 3.1, 3.3 under which a UNEP/MEA project is fitting into. For information:
Priority 1 - Climate Change and Sustainable Energy (Scope: Regional/Country):
1.1 Climate change adaptation (including the Global Climate Change Alliance)
1.2 Climate change mitigation in particular REDD, LEDS and technology transfer
1.3 Sustainable energy
Priority 2 – Environment for Development (Scope: Regional/Country):
2.1 Biodiversity, forest conservation and desertification
2.2 Forest governance and Forest Law Enforcement, Governance and Trade (FLEGT)
2.3 Green economy (including Strategic Approach to International Chemicals Management (SAICM) and Global Mercury Partnership)
Priority 3 – Strengthening environment and climate governance (Scope: Global):
3.1 External environment policy
3.2 External climate policy
3.3 Support for mainstreaming and promoting governance and transparency for natural resource management including water
F | Internal PMU Project Nb: Insert the internal PMU project number as allocated when developing the consolidated list of prioritized UNEP and MEA projects
G | EC DG: Insert CLIMA, DEVCO, ENV
H | UNEP/MEA Project Manager: Insert email address and first and last name if it is not evident from the email address; Insert email addresses of people to be put "CC" for email correspondence
I | EC Project Manager: Insert email address and first and last name if it is not evident from the email address; Insert email addresses of people to be put "CC" for email correspondence
J | UNEP/MEA requested amount (EUR): Amount covering all the costs related to the life-cycle of the project requested by the project manager to the EC
K | EC Funding allocation Year 1 (EUR): Insert the EC funding allocation for budget year 1 in EUR as allocated by the EC DG
L | EC Funding allocation Year 2 (EUR): Insert the EC funding allocation for budget year 2 in EUR as allocated by the EC DG
M | EC Funding allocation Year 3 (EUR): Insert the EC funding allocation for budget year 3 in EUR as allocated by the EC DG
N | Total EC Funding allocation (EUR): Insert the aggregation of the EC funding allocations for all budget years in EUR
O | Status of Project (A1, A2, B1, B2): Insert one of the four status:
A1: Project concept note is approved and project is selected for funding under the SCAs à Agreement on development of full-fledged proposal
A2: Project concept note is approved in principle but still there are some aspects to be addressed à Technical discussions at the level of UNEP project managers or relevant MEA's Secretariat and EC project
managers in view of finalizing project concept note and directly moving to the full-fledged proposal after approval through written procedure
B1: PSC requested additional discussion to confirm joint interest for a project à Development and submission of project concept to subsequent PSC meeting
B2: Project is either not of joint interest or not a top priority as compared to other priorities (considering the scarcity of available funding) and is rejected à End of the process
P | Status of Project development (concept note, full-fledged proposal): Insert CN, RCN (refined concept note), FFP
Q | UNEP Coordinator comments: UNEP ENRTP coordinator’s comments
R | EC PMU comments: Comments from ENRTP coordinators in DG ENV, DG CLIMA, DG DEVCO
2. ENRTP Implementation Monitoring
Objective: Monitor ENRTP funded UNEP and MEA, as foreseen in the ENRTP PMU terms of reference
Responsible staff: Sandrine Marquès
Status of document: Internal & Confidential OfO/EC
Column:
A | UNEP or MEA: Insert acronyms of the UNEP Divisions and MEA Secretariats
B | POW: Insert link with UNEP POW and equivalent for MEA Secretariats
C | PIMS Reference: Insert the PIMS reference allocated to a UNEP project
D | IMIS code: Insert the IMIS code allocated to a UNEP or to a MEA Secretariat project
E | Date of IMIS Code creation: Insert date of creation of the IMIS code in the UNEP system
F | UNEP/MEA Sub-Programme: For UNEP: CC, DC, EG, EM, HSHW, RE. For MEA Secretariat: tbd
G | Title of project: Insert project title as recorded in UNEP Project document (narrative part)
H | Project acronym: Insert project acronym (if existent) as recoreded in UNEP Project document (narrative part)
I | Geographical Scope: Insert either global, regional, country
J | UNEP/MEA Division: Insert acronyms of UNEP Divisions and of MEA Secretariats
K | UNEP/MEA Branch: Insert acronym of UNEP Branch and equivalent for MEA Secretariat if available
L | UNEP/MEA Project officer: Insert email address and first and last name if it is not evident from the email address; Insert email addresses of people to be put "CC" for email correspondence
M | UNEP/MEA FMO: Insert email address and first and last name if it is not evident from the email address
N | European Commission Directorate General: Insert ENV or DEVCO
O | EC Financial Mechanism: Direct grant
P | EC Funding Instrument: ENRTP
Q | European Commission Project Manager: Insert email address and first and last name if it is not evident from the email address; Insert email addresses of people to be put "CC" for email correspondence
R | EC Source (EU Delegation vs. HQs Brussels): HQs
S | UNEP Participation Status (Applicant, Partner): Insert either Applicant or Partner
T | Partners: NA
U | Duration (as mentioned in ENRTP project document or otherwise in contract): Insert project duration in months
V | Date of EC approval (email): Insert the date at which the email marking EC's approval was received (DD/MM/YY)
W | Starting Date (as mentioned in ENRTP project document or otherwise in contract): Indicate the starting date as mentioned in the UNEP Project document (narrative part)
X | End Date (as mentioned in ENRTP project document or otherwise in contract): Indicate the end date as mentioned in the UNEP Project document (narrative part)
Y | Actual End Date: Indicate the actual end date for project closure
Z | Total Eligible Cost of the Project (EUR): Indicate the total eligible cost of the project resulting from check of cost eligibility
AA | EC Co-Financing (%): Indicate the percentage reflecting the EC's financial contribution to the project budget
AB | EC Amount Granted (EUR): Indicate the EC's financial contribution allocated to the project
DEPOSIT FROM EC TO UNEP:
AC | ENRTP SCA Trust Fund: Insert ECL (DG ENV TF) or EUL (DG DEVCO TF)
AD | DG (ENV or DEVCO): Insert DEVCO or ENV
AE | Amount (EUR): Insert amount of the EC DG’s deposit paid to and recorded on the UNEP bank account
AF | Date of record of EC deposit in UNEP bank account: Insert date of the record of the EC DG’s deposit paid to the UNEP bank account
AG | Exchange rate EUR-USD: Insert the official exchange rate EUR-USD defined by UNEP for a specific EC DG deposit paid to the UNEP bank account
AH | Exchange rate USD-EUR: Insert the official exchange rate USD-EUR defined by UNEP for a specific EC DG’s deposit paid to the UNEP bank account
YEARS 1/2/3:
AI | Sub-allotment/fund transfer from UNEP TF to UNEP/MEA project (EUR): For MEA Secretariats’ trust funds: Fund transfer is in line with the yearly budget allocation in EUR made by the EC DG.
For UNEP and the MEA Secretariats: To be defined.
For sub-allotment, OfO indicated that "in consideration of the risk of exchange rate fluctuations and in accordance with standard practice for maintaining the operating reserve for trust funds, 85% of the PSC-approved
budget will be allocated in US dollars at the exchange rate at the time of the deposit of these resources (1EUR = 0.75USD) to ensure you are protected against possible losses. Every 6 months, ASC will review the situation
based on the current exchange rate and recommend revising the allotments, if appropriate."
AJ | ?: Column to be completed upon the completion of the column ‘Sub-allotment/fund transfer from UNEP TF to UNEP/MEA project (EUR)’ (If 85% paid, what about the outstanding 15%?)
AK | UNEP Coordinator comments: UNEP ENRTP coordinator’s comments
AL | Annual Progress Report – Narrative: Insert Received of Delayed
AM | Annual Progress Report – Financial: Insert Received of Delayed
AN | Annual Progress Report – Summary: Insert Received of Delayed
AO | Status of Annual Progress Report: Insert Pending EC feedback, Approved, Delayed

## 1.ENRTP SCA Project Development
UNEP or MEA (acronym) | UNEP SUB-PROGRAMME or MEA equivalent | PROJECT TITLE | PROJECT ACRONYM | ENRTP Priority (1, 2 or 3) | Internal PMU Project Nb | EC DG | UNEP/MEA Project Manager | EC Project Manager | UNEP/MEA requested amount (EUR) | EC Funding allocation Year 1 (EUR) | EC Funding allocation Year 2 (EUR) | EC Funding allocation Year 3 (EUR) | Total EC Funding allocation (EUR) | Status of project (A1, A2, B1, B2) | Status of Project development (concept note or full-fledged) | UNEP Coordinator Comments | EC PMU Comments

## 2.ENRTP SCA Implem. monitoring
[29 empty] | Deposit from EC to UNEP |  |  |  |  | YEAR 1 | [6 empty] | YEAR 2 | [6 empty] | YEAR 3
UNEP or MEA | POW Reference | PIMS Reference | IMIS Code | Date of IMIS code creation | UNEP/MEA SUB-PROGRAMME | PROJECT TITLE | PROJECT ACRONYM | PROJECT GEOGRAPHICAL SCOPE | UNEP/MEA DIVISION | UNEP/MEA BRANCH | UNEP/MEA PROJECT OFFICER | UNEP/MEA FMO | EUROPEAN COMMISSION Directorate General | EC FINANCIAL MECHANISM | EC FUNDING INSTRUMENT | EUROPEAN COMMISSION PROJECT MANAGER | EC SOURCE (EU Delegation vs. HQ Brussels) | UNEP PARTICIPATION STATUS (Applicant/Partner) | PARTNERS | DURATION (as mentioned in ENRTP project document or otherwise in contract) | Date of EC approval (e-mail) | STARTING DATE (as mentioned in ENRTP project document or otherwise in contract) | END DATE (as mentioned in ENRTP project document or otherwise in contract) | ACTUAL END DATE | TOTAL ELIGIBLE COST OF THE PROJECT (Euros) | EC CO-FINANCING (%) | EC AMOUNT GRANTED (Euros) | ENRTP SCA Trust Fund | DG (ENV or DEVCO) | Amount (EUR) | Date of record of EC deposit in UNEP bank account | Exchange rate EUR-USD | Exchange rate USD-EUR | Suballotment / fund transfer from UNEP TF to UNEP/MEA project (EUR) | ? | UNEP Coordinator Comments | Annual Progress Report - Narrative | Annual Progress Report - Financial | Annual Progress Report - Summary | Status of Annual Progress Report (Pending EC feedback/Approved/Delayed) | Suballotment / fund transfer from UNEP TF to UNEP/MEA project (EUR) | ? | UNEP Coordinator Comments | Annual Progress Report - Narrative | Annual Progress Report - Financial | Annual Progress Report - Summary | Status of Annual Progress Report (Pending EC feedback/Approved/Delayed) | Suballotment / fund transfer from UNEP TF to UNEP/MEA project (EUR) | ? | UNEP Coordinator Comments | Annual Progress Report - Narrative | Annual Progress Report - Financial | Annual Progress Report - Summary | Status of Annual Progress Report (Pending EC feedback/Approved/Delayed) | Suballotment / fund transfer from UNEP TF to UNEP/MEA project (EUR)