## Slide 1: Evaluation of the Legality Assurance System of Indonesia – Lessons learnt
FLEGT Ad-hoc Coordination Meeting

## Slide 2
Annex 8 of the Indonesia VPA describes 80 questions to be assessed before FLEGT licensing can start
  Questions cover
    Legality Definition, Control of the supply chain, Verification, Independent Monitoring, Licensing
  Questions were interpreted as Criteria for the evaluation
Indonesia and EU agreed to a joint process
  2 EU and 2 IDN independent experts
    EFI: EU experts; UK: IDN experts - 70-90 days each in 2013
    EU Del and IDN established focal points
  Iterative process: 3 phases in 2013
    desk review; field work (5 provinces), stakeholder inputs
    Intensive review, but still not all elements could be checked
  Joint internal report -> formal agreement on findings
Process of evaluation

## Slide 3
Importance of Evaluation Annex in the VPA
  Powerful tool to systematically address all elements of the VPA
Evaluation as an iterative process and not a one-off exercise
  Evaluation to start already early during implementation and to be phased
  Must be based on mutual trust
  Requires significant time/resources and dialogue/steering by EU Del and EFI
  Helps to maintain momentum during implementation and raises stakeholder understanding
Lessons learnt

## Slide 4
Results help structuring VPA implementation
  Based on the findings and recommendations EU and IDN developed an Action plan for VPA implementation that maps out the path to FLEGT licensing
  Helped IDN side to act on sensitive issues not yet integrated in their national TLAS (e.g. segregation) or not yet achieved in implementation
  Civil society role strengthened
Strategic communication is key
  Progress and results of the evaluation need to be communicated carefully to avoid undermining improvement efforts and market perception (EU TR)
Lessons learnt

## Slide 5
Evaluation reopened several VPA Annexes
  Specific measures to be added to national TLAS (SVLK)
  Multi-stakeholder legality standards review initiated
  IDN plans to revise its national TLAS legislation in March 2014
  JIC afterwards to review some of the VPA Annexes (Legality definition, TLAS, product scope) -> revised versions
  Next evaluation (May/June 2014) will assess progress of implementation of the Action Plan
  Final evaluation will inform Joint Implementation Committee to discuss start of FLEGT licensing -> formal process
Lessons learnt