## Sheet1
Bolivia - Progress towards Joint Programming in 2017
Date | Action | Status | Comments
March 6th | EU-Delegations-HoC meeting with European Commission (EC) and European External Action Service (EEAS) officials in Brussels to de-brief on the recent joint programming consultancy mission, present next steps, and request that EU HQ sensitises counterparts in European capitals to the process. | Done
March 20th | Meeting of EC/EEAS with Spanish officials in Madrid to review next steps as per this Roadmap (NB this meeting will take place before or after a joint programming training that has already been scheduled for this date). | Done
April 5th | Draft European Coordinated Response finalised | Done
April 15 th | Draft Roadmap for Joint Programming in Bolivia completed. | Done
Date tbc | Grupo de Socios para el Desarrollo de Bolivia (GruS – the local donor coordination structure) mapping of development partners’ work should be completed. | Pending | Delays by World Bank. Will be carried out by our own means
April 22 th | Positive response letter from GoB on joint programming should have been received. | Done
April 25th | HoMs letter to be sent to GoB enclosing the European Coordinated Response and requesting written GoB endorsement for moving to full European joint programming from 2017. | Done
Late April | Joint Communication to be sent by HoMs to European capitals, briefing on the process, attaching this Roadmap and the GoB endorsement letter, and highlighting the specific actions that now need to be taken by capitals (see section 4 below). | Done | Individually by each Member State
Late April | Bolivian case and Roadmap to be presented at the EU Technical Seminar on Joint Programming in Brussels. | Done
Early May | Meeting of capitals’ Bolivia desks (either physically in Brussels or via video conference) to discuss the Roadmap and the next steps that need to be taken by each. The idea is to start a dialogue that will include administrative, budgeting and legal units of each EEMM for the development of joint programming. | Done | 2013-09-01
May | Bolivian case to be submitted to the EU Director Generals meeting as an example of good practice with a request for their endorsement of the Roadmap. | ?? | Depends from HQs, Del. believes it was done at global level, not individually for Bolivia.
End of 2013 | Review of donor mapping that has been carried out by GruS in combination with an examination of European donors’ stated future plans to see where possible gaps and overlaps may arise in future. |  | Will have to be carried out by EU in early 2014.
Note: next steps are to update the roadmap (before year end), including actions foreseen during 2014 and 2015 and start preparations
for workshop on division of labour jointly with goverment
Participating countries: Germany, Belgium, Denmark, Spain, France, Italy, Sweden (expected to leave Bolivia in 3 years), Switzerland, EU.
No other similar processes in Bolivia. However, all donors have been informed of the process and invited to join. Regular updates foreseen.
Government fully committed to the process and "formally" ready to lead it (in reality the drive comes rather from us so far