## Slide 1
The Caribbean Community Climate Change Centre and the CARICOM Secretariat
Second Regional Technical Meeting
5, 6 and 7th May, 2014
ACP House – Brussels
Impact and Vulnerabilities
The Caribbean Regional Programme

## Slide 2: Programmatic Areas
Component 1: Enhancing the predictive powers of regional climate models and the region’s ability to design and implement cost-effective adaptation activities;
Component 2: Improved climate monitoring, data retrieval and space-based tools for disaster risk reduction;
Component 3: Refined vulnerability and risk assessment methodologies that are more contextually relevant, and build local capacity to better assess the current and future vulnerabilities and risks of specific states and communities within those states;
Component 4: Reduce the states vulnerability to climate change through embarking on adaption pilots;
Component 5: Built regional and national capacities for carbon financing; and
Component 6: Project management.

## Slide 5: Achievements (July 2013 to Present)
Component 1: Enhancing the predictive powers of regional climate models and the region’s ability to design and implement cost-effective adaptation activities
  Annual Meeting of Climate Modellers Group Held in the Dominican Republic in April 2014
  Four (4) Caribbean Climate Modelling Experts underwent training attachments at the Hadley Centre in the UK in October 2013 (2 from UWI and 2 from INSMET).
  Developing a data management system (on-going)
  The Cuban Institute of Meteorology (INSMET) prepared and delivered training in the use of agriculture and water sector models in Jan 2014

## Slide 6: Achievements (July 2013 to Present)
      Up to 10 sector-based impact assessment studies are to be completed leading to the preparation of NAS and APs (Sept 2013 – August 2014) (On-going)
    Water – St. Kitts and Antigua and Barbuda
    Agriculture – Suriname and Barbados
    Tourism – Dominican Republic and Saint Lucia
    Health – St. Vincent and the Grenadines

## Slide 7: Achievements (July 2013 to Present)
Component 3: Refine vulnerability and risk assessment methodologies that are more contextually relevant, and build local capacity to better assess the current and future vulnerabilities and risks of specific States and communities within those States:
  Procuring technical assistance for the conduct of the VCAs in up to 10 States: (i) VCAs underway in Antigua and Barbuda, St. Kitts and Nevis, DR. (ii) Out to tender in Suriname and Barbados, and (iii) Tendered and received no response in Saint Lucia and Suriname
  Carrying out a Cocoa-Agroforestry Project in Saint Lucia To reduce their vulnerability and risk to climate hazards by building resilience of farmers (on-going)
  Conducted two training workshops (four days each) in October 2013 in Belize and Barbados respectively on the use of Caribbean Climate Online Risk and Adaptation TooL (CCORAL)

## Slide 8: Challenges Faced
Impact Studies and Vulnerability Assessments
  Difficulty in recruiting the requisite consultants and a limited pool from which to choose
  Some countries were slow in identifying the sector in which they wanted the impact studies conducted

## Slide 9: Outcomes and Future Perspectives
Enhanced information provision for greater resilience building
Enhanced capacity to deal with the challenges and take advantage of opportunities provided by CV and CC
Enhanced coping capacity for vulnerable communities in times of disaster
Create and maintain opportunities to bring together financial decision makers, scientists, and service providers
The region needs to continue to invest in improved data management and early warning systems, enforce building codes, invest in human capital, develop competent and ﬂexible institutions, and tackle the root causes of poverty

## Slide 10: Opportunities for collaboration and Communication
Participation in regional project coordination meetings provide opportunities to share experiences and pursue initiatives that are mutually beneficial
Create a user-friendly information repository and portal that provides easy access to information relevant to project partners and beneficiaries.
Create and maintain opportunities to bring together project proponents, beneficiaries and partners

## Slide 11
Thank You
Caribbean Community Climate Change Centre
www.caribbeanclimate.bz