## Slide 1
Second Regional Technical Meeting
5, 6 and 7th May, 2014
ACP House – Brussels
Presentation to the 2nd RTM by
Mclay Kanyangarara & Mweusi Karake
COMESA

## Slide 2: Programme on Climate Change adaptation and mitigation in the COMESA-EAC-SADC region Africa Group
Presentation to the 2nd RTM by
Mclay Kanyangarara & Mweusi Karake
COMESA
ACP house Brussels 5-7 may 2014

## Slide 3: Background
COMESA is Africa’s largest economic grouping, with 19 MS and a population of over 430 million
The COMESA Climate Change Unit coordinates the programme on climate change mitigation and adaptation in the COMESA-EAC-SADC region.
The five-year initiative that started in July 2010 is a successor to the COMESA climate change initiative that had been running since December 2008.
This presentation covers the period after the 1st RTM in Belize in June 2013

## Slide 4: Theme 1: Impact and Vulnerability
CSA pilots in 5 countries, Botswana Lesotho, Uganda, Zambia and Zimbabwe
Targeting most vulnerable & rural schools
Impact Assessment (VAA) done in first 8 ESA countries
More pilots & scaling out to be carried
Future: VAA to be scaled up

## Slide 5: Theme 2: Integrated Disaster Risk Reduction and adaptation
June to November 2013: COMESA completed baseline analysis ( 2009-2013) for 10 countries namely: Ethiopia, Kenya, Madagascar, Malawi, Mauritius, Rwanda, Sudan, Uganda, Zambia and Zimbabwe.
Major finding was: The role played by women and need for women focus CSA
Deserter Risk Reduction (DRR) started in EA
DRR being implemented in Southern Africa in partnership with FAO

## Slide 6: Integrated Disaster Risk Reduction and adaptation cont
ACTIONS
CSA pilots & Scaling up in 14 M/S
CSA piloted in schools, Zimbabwe 2013, Uganda 2014
11 Partnerships entered into for the sustainability of interventions in the MS
Honey farming and harvesting training, forestry pilots in Zambia.
NCCRS processes scaled out

## Slide 7: Integrated Disaster Risk Reduction and adaptation cont
Regional CSA forum held in Arusha Feb 2014
In March 2014, Co-sponsored and Organized 1st African Congress on CA over 40 African countries attended- over350 delegates attended
ALL COMESA MS have integrated CC in national plans or strategies.
Kenya, Ethiopia, Mauritius, Rwanda enacted laws on CC & Green Economy

## Slide 8: Integrated Disaster Risk Reduction and adaptation cont
Launched partnerships with the Eastern and Southern Africa Small Scale Farmers Forum & developed an SMS application that will be providing Small Scale Farmers with information on markets, and weather tips
Launched partnerships with The East and Southern Africa Agribusiness Network & developed Unstructured Supplementary Service Data (USSD) that will provide CA/CSA farming tips

## Slide 9: Theme 3: Low Carbon development
Part of the discussion at the COP 19 side event
COMESA Carbon Fund set up
A pipeline of low carbon projects in the COMESA region developed
Assessment of the Carbon Markets and Carbon Credits carried out
Under both the Feb & March 2014 conferences best practices exchanged
Due to increased advocacy, MS continue to submit carbon qualifying projects for funding as at 2013 - 10 member states had been evaluated increased their total climate finance resources from US$560m in 2011 to over $830m in 2013

## Slide 10: Theme 3: Low Carbon development cont.
Supported Mt Karisimbi regional climate observatory Carbon Analyser project,
7 sub-grantees engaged to promote CSA in at least 14 countries
Regional Strategy on Mainstreaming Gender in Agriculture and Climate Change completed
in July 2013, over 60 trainees, among them extension officers, NGOs, and education officers trained in practical methods of incorporating a gender perspective in field-based CA practices

## Slide 11: Theme 3: Low Carbon development cont.
In March 2014 a COMESA delegation visited China in order to engage with institutions dealing with renewable energy, in particular small hydro with the view to promote them in the COMESA region.
14 w2e projects identified for investment
A number of countries have adopted specific Low carbon measures e.g. Kenya- Private Mini-hydro, Rwanda compulsory compact fluorescent bulbs and LED public lights, Zambia pre-paid water metres

## Slide 12: Challenges
The Major challenges at RECs / MS level has been finance
Traditional beliefs/Inadequate awareness
Lack of capacity and resources
Size of farms per house hold - often too small
Land tenure
Proliferation of uncoordinated initiatives

## Slide 13: Communication
COMESA-EAC-SADC have established a communication channel-common email
Common folder
Media network with common email
Created Face book with a Q&A facility

## Slide 14: Questions & Comments are welcome
Thank you for your attention
Merci pour votre attention
Asanteni Sana Kwa Kunisikiliza
ClimateChange@comesa.int
mkanyangarara@comesa.int
mkarake@comesa.int