## Slide 1
CCCCC
Second Regional Technical Meeting
5, 6 and 7th May, 2014
ACP House – Brussels
Disaster Risk Reduction and Adaptation
Caribbean

## Slide 2: Adaptation and DRR (2012/13)
Component 1
ENHANCING THE PREDICTIVE POWERS OF REGIONAL CLIMATE MODELS AND THE REGION’S ABILITY TO DESIGN AND IMPLEMENT COST-EFFECTIVE ADAPTATION ACTIVITIES
Component 2
SC1 Identification of weather and coral reef monitoring station requirements; COM
SC2 Procurement of weather and coral reef monitoring stations equipment; COM
SC3 Installation of weather and coral reef monitoring stations; ON (Feb-Dec 2013)
SC4 Linkage/networking of weather stations and coral reef monitoring stations; ONG ON (Jan – June 2013)
SC5 Data and information management and use ON (Jan – June 2013)
SC6 Application of Climate Models in Impact Studies
ten (10) national and sector specific impact studies that will lead to the development of National Adaptation Strategies (NAS) and Action Plans (AP) for the sector in the particular country.
IMPROVED CLIMATE MONITORING, DATA RETRIEVAL AND SPACE-BASED TOOLS FOR DISASTER RISK REDUCTION
ONGOING (Jan 2013 – June 2014)
Notes:   Component 1: This component seeks to build capacity of the region to further refine the downscaling of global climate models to deliver outputs based greater geographic resolutions in order to provide more accurate and reliable data sets and expand the overall knowledge base on climate change impacts and associated physical, social and economic vulnerabilities.
  Component 2: The objective of this component is to build and expand in-country and regional infrastructure and capacity to generate and manage climate-related data and information that can assist policy and decision makers in national and regional planning and development processes.

## Slide 3: Adaptation and DRR (2012/13)
Component 4
Reduce the states’ vulnerability to climate change through embarking on adaptation pilots
SC1 Preparation of National Climate Change and Adaptation Policies ON (Feb – Sept 2013)
SC3 Produce project feasibility documents for pilots; ON (Jan – July 2013)
SC4 Implement adaptation pilots ON (July 2013 – June 2014)
SC2 Identification and presentation of adaptation options; COM
Notes:   Component 4: The objective of this component is to develop and replicate pilot adaptation projects in selected countries. The pilots adaptation actions will assist communities in the selected countries to reduce their vulnerabilities to the effects of climate change.

## Slide 4: Actions taken
Component 1
Component 2
Installation of CREWS stations by contractor will be completed by first half of 2014.
The specifics of linkages (weather and CREW(S) stations) are being worked on by the CCCCC along with the cooperation and assistance of regional and national agencies
Impact Studies to be completed by October 2014
Process of developing the capability to monitor, archive and share data with national and regional agencies is ongoing

## Slide 5: Actions taken
Component 4
Two countries, Belize and Suriname, requested support to prepare national climate change and adaptation policies and strategies respectively
Five countries, Antigua and Barbuda (water/agriculture), Barbados (water), Belize (water and agro-processing), Grenada (water) and Saint Lucia (agro-forestry) have identified adaptation actions (pilots) for implementation.
A feasibility study was completed for the installation of salt water reverse osmosis plants in Grenada by in-house CCCCC technical personnel while the environmental and social impact assessment has been completed
Procurement of goods and technical assistance to support implementation of the adaptation pilots have commenced.
Notes: 1: TORs have been prepared and agreed with the national agencies and procurement of technical assistance is underway. In Belize the national climate change policy and strategy is being funded jointly with the third national communication project
3: The Grenada adaptation initiative is being funded by the project and DIFID.

## Slide 6: Challenges faced
Vulnerability Assessments and Adaptation Strategies faced issues of time and cost (multiplier effect)
  Time lag in the VCA regional training workshops and assessments delayed the preparation of the AS
  Lack of bids led to re-tendering of assessments and studies
  To keep within the timeframe, the VCAs and AS had to be bundled and at increased cost (this could only occur where both were in the same sector)
Lack of early buy-in from some of the national agencies prolonged the response time
Communication shortfalls between countries and the PIU

## Slide 7: Outcomes and Future Perspectives
An M&E system should be in place to provide data and information to assist adaptation and decision-making by policy makers
Project will have implemented a number of pilot and full adaptation projects (incld. community-level adaptation)
  These renewable energy projects promote a disaster risk management ethic
Future adaptation partnerships through successful initiatives assists the Region in becoming more resilient

## Slide 8: Opportunities for collaboration and Communication
Participation in regional project coordination meetings provide opportunities to share experiences and cooperate in adaptation initiatives that are successful
Within the Region countries share national experiences through workshops and training sessions, as well as in the annual project planning and coordination meetings
The CCCCC Communication Strategy helps to disseminate the message to the wider Caribbean

## Slide 9
Thank You
Sharon Lindo, CCCCC
slindo@caribbeanclimate.bz