## Slide 1: Case study
Public Finance Management (PFM) Reform Support Programme for Tajikistan

## Slide 2: The project (1/2)
Specific objective: ensure that the Ministry of Finance (MoF) of Tajikistan and the other relevant authorities achieve a more effective and efficient PFM system.
Expected results:
I. Improved macroeconomic, fiscal and revenue/tax policy formulation and management, and enhanced capacity and flexibility to respond to changing economic circumstances
II. A budget framework for GoT is developed and established
III. The MoF can undertake informed discussion and allocation of budget resources to sub-national levels of government
IV. The Tajik Financial Institute (TFI) delivers sustainable training and education to students in public finance.
V. Operational Internal Audit (IA) regime expanded in Tajikistan, thereby reinforcing Internal Control (IC)

## Slide 3: The project (2/2)
All five results are supported by cross-cutting activities relating to:
(i) The provision of capacity building and technical assistance to MoF to monitor progress in implementation of the PFM conditions in the budget support programme and assist MoF in fulfilling these conditions; and
(ii) The organisation in consultation with other donors of a PEFA assessment to coincide with the assessment of measurable indicators at end of project.

## Slide 4: QC 1:Fitting with the context
Positive aspects:
Steady economic growth supported by macro-economic, social and political stability
National Development Strategy (2006-2015) + Poverty reduction strategies (every 3 years)
Institutional embeddedness of these plans by the Presidency and line Ministries
Reform ownership by the government: in charge of implementation and regular update of sectoral sub-strategies
Challenges (assessment of institutional capacity):
Insufficient linkages between budget and policies: limited role of line ministries in sectoral policy formulation,
Weak payroll control and audit
Lack of middle management to organise scarce human resources
No capacity in MoF to meet emergent needs for high quality economic studies/analyses No effective system of advanced training and re-training of public officials
Weaknesses to communicate the budget to Parliament and the public

## Slide 5: QC 2: Adequate demand, commitment and ownership: CD pulling factors
Existing PFM strategy setting out a multi-annual agenda and framework of reform;
Strong receptiveness to change in the policy dialogue at political and technical level;
Commitment and ownership proved by progress in key areas of reform;
Process of dialogue, consultation and coordination meetings with key beneficiaries, other donors, other stakeholders and within the working group “Governance” of the Development Coordination Council has been consolidated;
The capacity of the partner organisations is known from current and previous interventions;
TA is generally seen by the stakeholders as an inseperable part of the action: emphasis is put on the use of already existingknowledge to roll out the process.

## Slide 6: QC 3: clear link to results
Measurable indicators identified linked to economic growth and institutional performance
Partner country's inputs identified: senior staff of MoF will be involved in the steering of TA
Innovative ways of TC support: local expertise, pilot initiatives rolling out lessons learnt, training of trainers, workshops held by public civil servants

## Slide 7: QC 4: harmonised support
Consultations have taken place before and after implementation with other donors and with partner's authorities
Existing division of labour among donors in PFM: ADB: tax administrtaion, USAID: local governments and trust funds, FMIS-SCO: external audit, UNDP and WB: public administration, EU: remainder

## Slide 8: QC 5: appropriate PIA
Centralised management-primary accountability appointed to EUD
Nevertheless:
PFM secretariat is hosted in a MoF department
Concerned govt. bodies will bear responsibility as memebrs of the Steering Committee
Civil servants will contribute directly to implementation but no salary top-ups