EuropeAid/129522/C/SER/Multi Contract number 2010/232-231

Air Quality Governance in the ENPI East Countries

Institutional requirements at the implementation of environmental permitting reform

10 October 2013

| Version |  | Date | Description | Prepared by | Reviewed by |  |
| --- | --- | --- | --- | --- | --- | --- |
| 2 |  | 10 October 2013 | Task 2.1.3 Institutional requirements | Short-term experts of Component 2 | Aiga Kāla, Key Expert 2 – Air Quality Assessment and Management Vladimir Morozov, Key Expert 3 – Industry/IPPC |  |

# SUMMARY

Project Title:	Air Quality Governance in ENPI East Countries

Contract Number:	2010/232-231

Countries:	Armenia, Azerbaijan, Belarus, Georgia, the Republic of Moldova, the Russian Federation, Ukraine

Lead Contractor

Name	MWH

Address	Nysdam Office Park
Avenue Reine Astrid, 92
B-1310 La Hulpe
Belgium

Tel. number	+32 2 655 2230

Fax number	+32 2 655 2280

Contact person	Aïda Yassine, Project Manager

Signature

Date of report:	10 October 2013

Experts:

Monika Přibylová, International Non-Key IPPC Expert (Subtasks 2.1.3.1 - 2.1.3.3, 2.1.3.5 - 2.1.3.6)

Bjørn Bauer, International Non-Key Expert on Integrated Inspection (Subtask 2.1.3.4)

Michael Begak, International Non-Key IPPC Expert (Subtasks 2.1.3.1, 2.1.3.6)

Oleg Bely, Local Non-Key IPPC Expert (Subtasks 2.1.3.1 - 2.1.3.2, 2.1.3.4)

Tatiana Guseva, Local Non-Key IPPC Expert (Subtasks 2.1.3.1 - 2.1.3.3, 2.1.3.5 - 2.1.3.6)

Viktar Khodzin, Local Non-Key IPPC Expert (Subtasks 2.1.3.1 - 2.1.3.6)

Content

SUMMARY	3

1.	BACKGROUND	7

2.	the scope of new or changed functions and responsibilities	8

2.1.	Background information on functions and responsibilities within environmental regulatory system	8

2.1.1.	Differences between existing and new environmental permitting system	8

2.1.2.	Stakeholders and their roles in the new regulatory systems	9

2.2.	New functions and responsibilities	11

2.2.1.	Functions and responsibilities related to integrated permitting regime	11

2.2.2.	Check list of key tasks needed for implementation of the integrated permitting regime	13

2.2.3.	Phasing Considerations	15

2.2.4.	Functions related to registration regime	15

2.3.	The current situation of institutional changes related to environmental permitting reform in the project countries	16

3.	recommendations for the specialized Environmental permitting department	20

3.1.	The role of Environmental permitting department in environmental regulatory system	20

3.1.2	Relation of EP department with stakeholders of the integrated permitting system	20

3.1.3	Work scope of EP department	22

3.2.	Organisational, human and technical requirements	24

3.2.1.	Organisational requirements and scheme	24

3.2.2.	Human resources	25

3.2.3.	Technical equipment	26

3.3.	Phases of developing and operating EP department	26

3.4.	The current situation with setting up the EP department in the project countries	28

3.4.1.	Relevant public administration body for the EP department in Belarus	28

3.4.2.	Ways of ensuring effective coordination of competent administrative authorities within integrated permitting procedure	28

3.5.	Conclusions and recommendations	28

4.	recommendations for the competent ADministrative Authorities and registration authorities	30

4.1.	The role of CAA in environmental regulatory system	30

4.1.1.	Relation of competent administrative authorities with stakeholders of the integrated permitting system	30

4.1.2.	Work scope of CAA	32

4.1.3.	Organisational requirements for CAA	33

4.1.4.	Recommendations for the project countries	34

4.2.	The role of registration authorities in environmental regulatory system	34

4.3.3.	Relation of registration authorities with stakeholders of the environmental regulatory system	34

4.3.4.	Work scope of registration authorities	35

4.3.5.	Organisation requirements for registration authorities	36

4.3.	Conclusions	37

4.3.1.	Conclusions for the CAA	37

4.3.2.	Conclusions for the registration authorities	37

5.	recommendations for the Integrated Environmental Inspection authorities	39

5.1.	The role of Integrated Environmental Inspection in the Regulatory Cycle	39

5.1.1.	Setting up the Integrated Environmental Inspection Authority	40

5.2.	Organisational recommendations	42

5.2.1.	Human resources recommendations	43

6.	recommendations for the BAT expert support body	44

6.1.	The role of BAT support body in environmental regulatory system	44

6.1.1.	Relation of BAT support body with stakeholders of the integrated permitting system	44

6.1.1.	Work scope of BAT support body	45

6.2.	Institutional and organizational requirements	47

6.2.1.	Options for institutional setup	47

6.2.2.	Organization structure	47

6.2.3.	Human resources	48

6.2.4.	Management and financial requirements	49

6.2.5.	Technical requirements	50

6.3.	Phases of developing and operating BAT support body	51

6.4.	Conclusions and recommendations	52

6.4.1.	Where to place the BAT body?	53

6.4.2.	Scope of BAT support body activities	53

7.	recommendations for the GBR PERMITTING AUTHORITY	54

7.1.	The role of GBR permitting authority in environmental regulatory system	54

7.1.1.	Relation of GBR authority with stakeholders of the GBR permitting system	54

7.1.2.	Work scope of GBR authority	56

7.2.	Organisational and human requirements	58

7.2.1.	Organisational requirements	58

7.2.2.	Human resources	59

7.3.	Phases of developing and operating GBR authority	60

7.4.	Recommendations for the project countries	61

7.4.1.	Where to place the GBR authority	61

7.5.	Conclusions and recommendations	61

ANNEX 1. INSTITUTIONAL ARRANGEMENTS FOR IPPC IN BELARUS AND RUSSIA (in Russian)

List of abbreviations

BAT – Best Available Techniques

BREF – BAT Reference document

CAA – Competent Administrative Authorities, i.e. authorities who are issuing environmental media based permits and in the integrated regime their competence will be transformed to consultation on the application and on the draft integrated permit

EECCA – Eastern Europe, Caucasus and Central Asia

EIA – Environmental Impact Assessment

EIPPCB – European IPPC Bureau

ENPI – The European Neighbourhood and Partnership Instrument (ENPI) that supports the European Neighbourhood Policy (ENP)

EP – environmental permitting

EU – European Union

GBR – General Binding Rules

IED – Industrial Emissions Directive

IEIA – Integrated Environmental Inspection Authority

IPPC – Integrated Pollution Prevention and Control

NGO – nongovernmental organisation

OECD – Organisation for Economic Cooperation and Development

R&D – Research and Development

RAA – Relevant Administrative Authorities

RIA	 – Regulatory Impact Assessment

SEPG – sectoral environmental protection guidelines

SMEs – Small and Medium size Enterprises

TWG – Technical Working Group

# BACKGROUND

This report is prepared in the frame of Air Quality Governance project, Component 2 - Activities addressing the Industrial Sector, including Energy, Task 2.1 Support towards the implementation of integrated permitting, Subtasks 2.1.3.1 - 2.1.3.6 dealing with Institutional requirements.

The aim of this report is to provide the overview of institutional changes related to environmental permitting reform and suggest how different authorities and institutions from the project countries can effectively deal with the transition towards new or modified environmental regulatory regimes. The countries participating in the Air-Q-Gov project include Armenia, Azerbaijan, Belarus, Georgia, the Republic of Moldova, the Russian Federation, and Ukraine.

The new or modified environmental regulatory regimes include:

- Integrated permitting regime based on EU IPPC regulatory system

- Regime of medium polluters permits (including single media permits and integrated GBR based permits), and

- Regime of environmental registration of low polluting activities

The report starts with the overview of new or changed permitting functions and responsibilities of permitting authorities and consulting bodies. The following chapter deals with such institutions and authorities as the specialized environmental permitting department, competent administrative authorities, inspection authorities, environmental registration authorities, the BAT support body and GBR permitting authorities.

The report is based on:

- EU legislation and guidance related to IPPC

- The experience with the implementation of the IPPC Directive and Industrial Emissions Directive, also in the new EU member states

- Conclusions and findings of similar IPPC projects and guides like OECD Integrated environmental permitting guidelines for EECCA countries, 2005 or the Handbook for Implementation of EU Environmental Legislation, 2008

- Experience and ongoing discussions on implementation of integrated permits and technological standards in the project countries.

The recommendations are in line with the Concept for transformation of environmental permitting system (project Subtask 2.1.2.1) and Legal and regulatory analysis (project Subtask 2.1.2.2) taking into account the discussion during IPPC and Permitting seminar, which took place on 14th  and 15th of May 2013 in the frame of this project.

The presented recommendations are based on a desk study and have not comprised assessment missions to the partner countries for investigation of the institutional schemes.

Each chapter of this report has its introduction and conclusions in order to enable using them separately depending on the need of the individual authorities/institutions from the project countries.

# the scope of new or changed functions and responsibilities

The recommendations for the revision of functions and responsibilities are elaborated under Subtask 2.1.3.1 under the Component 2 of the Air-Q-Gov project. They are intended as introduction to institutional changes related to environmental permitting reform to be implemented by the Ministries of the partner countries responsible for environment protection.

These recommendations were obtained from experience with implementation and enforcement of EU environmental legislation, in particular Directives 96/61/EC, 2008/1/EC on IPPC and 2010/75/EC on industrial emissions in some EU and accession countries as well as on the Handbook for Implementation of EU Environmental Legislation.

The scope of functions, responsibilities and competencies which needs to be ensured for operation of a countries environmental regulatory system concerns three regimes:

- Integrated permitting regime

- Regime of medium polluters permits (including single media permits and integrated GBR based permits) and

- Environmental registration of low polluting activities

Detailed description of the institutional, organisation and human requirements for the integrated permitting regime is described in chapters 3 – 6. Detailed description of the institutional, organisation and human requirements for the GBR based permitting regime is described in chapter 7, and details of the institutional, organisation and human requirements for the environmental registration regime is listed in chapter 4.

## Background information on functions and responsibilities within environmental regulatory system

## Differences between existing and new environmental permitting system

The basis for proposing and defining functions and responsibilities of the new environmental regulatory system is the difference between existing permitting system and the newly proposed system. The existing system requires obtaining various media specific permits and approvals for every company which more or less produce environmental pollution. So, a public administration has primarily four regular functions:

- Issuing and renewing of permits and approvals

- Inspection of sites to check compliance with permits’ conditions and other legal requirements

- Environmental pollution payments collection

- Environmental monitoring providing and public reports publishing.

These functions are carried out by numerous authorities under several ministries on national, regional or local levels.

The new environmental regulatory system foresees three regulatory regimes: integrated permitting and enforcement, existing environmental media based permitting, and environmental registration. Responsible Ministry should execute supreme state supervision for all three regimes and should act as a central body of state administration. It might also act as an appeal body within permitting procedures.

The integrated permitting regime implementation requires one authority responsible for issuing a permit and coordination of consultations with other relevant authorities. It also requires establishing of an organisation, which will be responsible for BAT information exchange and BAT guidance. To ensure the compliance with environmental regulations and enforcement it is necessary to carry out integrated inspections.

The existing regime for issuing separate environmental media based permits will remain the same, but since groups of large and low polluting installations will be regulated by the other regimes, the load of permitting work shall decrease.

Nevertheless it is proposed that in the medium – long term perspective, some of the sectors with single media permits can be transferred to GBR based permitting regime.

## Stakeholders and their roles in the new regulatory systems

In order to define functions and responsibilities, it is important to have in mind stakeholders and their roles in the regulatory system. The following table contains main stakeholders and their roles or interests in relation to the regulatory system.

Table 2.1 – Principal stakeholders and their roles in the environmental regulatory system

| Stakeholder | Role or interest |
| --- | --- |
| National government — generally Ministry of Environmental Protection | - Preparation of new legal acts and amendments to existing legislation - Appointment of competent authorities - Establishment and control of competent authorities - Preparation of methodological support documents and technical guidance - Determination of functions and structure and establishment of BAT support body (BAT centre) - Dissemination of information related to the regulatory system - Overall responsibility for implementation of the permitting reform |
| Competent authority (can work at different public administration levels: national, regional, municipal) | - Identification of installations for the integrated permitting regime and environmental registration regime and registration in the National Register - Elaboration of the templates of applications, permits and procedures for permitting and registration procedures - Coordination of consultations between different administrative authorities in the field of integrated permitting - Integrated permitting, single-media and GBR permitting and environmental registration - Compliance monitoring and enforcement - Need for support and technical guidance - Data collation and reporting |
| Other Ministries (Industry, Agriculture, Economy, Finance) | - Supporting information exchange on BAT - Estimation of the resources needed for environmental modernization of enterprises, long- and short-term strategies - Estimation of the possibilities of state support for enterprises modernization |
| Supervisory bodies (sanitary-epidemiological, water resources, hydrometeorological, forest, agriculture) | - Participation in permitting procedures via interdepartmental exchange network - Setting of permit conditions for protection of environment and public health - Assessment of possible transboundary impact (Hydrometerological service) |
| Industry and agriculture installations — including state-owned and private sector | - Participation in development of legal acts, by-laws and regulations - Assessment of compliance costs as this will be a significant factor in performance improvement - Interest to minimize prosecutions and payments - Improvement of public image and maintaining/ improvement of competitiveness |
| Private sector providing services to regulated installations — retailers and businesses, manufacturing | - Opportunities for business in supplying environmentally-friendly equipment or environmental consultancy |
| Professional and technical institutions — linked to industrial or commercial sectors | - Representation of industry opinion - Provision of technical support and guidance |
| Public | - Impact on public health due to industrial pollution - Interest in optimisation of environmental costs, which may eventually be passed on general public as consumers of goods etc. |
| Municipalities | - Participation or co-organisation of public hearings - Interest in keeping good environmental conditions within its territories |
| NGOs | - Representation of public interest - Highlighting environmental issues - Exerting pressure on government and industry |
| Universities and academic institutions | - Research into improved environmental technology and techniques - Research into effects of pollution |
| International organisations | - Provision of technical guidance and information, e.g. the European IPPC Bureau in Seville - Sources of reference on environmental standards - Provision of grant support for technical assistance to improve environmental performance |

## New functions and responsibilities

This part contains the list and overall description of functions and responsibilities needed for implementation of the integrated permitting regime and registration regime by the relevant institutions. Functions for both regimes are divided into preparatory and implementation phases. Functions and responsibilities are listed in relation to the institution or authority which should be responsible for them.

### Functions and responsibilities related to integrated permitting regime

Preparatory phase

The main function of national governmental bodies in the preparatory phase is establishing the legal and institutional basis for integrated permitting regime implementation. National government bodies include primarily the Ministry of Environmental Protection which will be responsible for the following functions:

- Prepare and issue relevant legislation

- Establish competent authority/ies for permitting and enforcement

- Establish coordination mechanism for consultation of the application for integrated permit with relevant authorities

- Establish BAT support body

- Appoint suitable personnel to staff competent authority/ies

- Establish a system for transboundary consultation

- Adjust a data collection system

- Establish a system for integrated permit appeals

When the permitting authority is formally established it will prepare itself for the permitting function. The following responsibilities and tasks are proposed for practical preparation of the permitting authority for implementation of the integrated permitting procedure:

- Set up appropriate staff structure

- Training of the personnel

- Establish integrated permitting system and procedure within the organizational structure and participate in consultation about the relevant legislation

- Establish mechanism for public involvement in permitting procedure

- Establish system for permit review and variation

- Establish system for public access to permits and information about permitting procedure (e.g. electronic public register).

In case the enforcing authority is separate from the permitting authority, it is proposed to carry out the following tasks in order to adjust for integrated inspections and cooperation with permitting authority:

- Prepare system and procedure for integrated or coordinated inspections

- Training of the  inspectors

- Clarify any role of the inspection authority during the permitting procedure (e.g. through consultation) and procedures for permit reviews.

In case the enforcing and permitting functions are within one authority, then this authority shall carry out the above listed task for permitting and enforcing authority, nevertheless it is recommended that there are different persons responsible for granting permit and performing the inspection to minimize the risk of hiding noncompliance.

The BAT support body will be responsible for the following tasks:

- Set up appropriate institutional and staff structure in order to establish cooperation with industry and environmental experts

- Start adoption of EU BREFs on national level or developing national BAT guidance

- Establish the system for tracking BAT.

Implementation phase

The Ministry of Environmental Protection shall have the following functions and responsibilities:

- Provide the system for registration of polluting enterprises in the State Register.

- Ensure methodological support to all administration bodies and BAT support body in relation to the interpretation of the legislation.

- Act as appeal body against permit decisions under the integrated permitting system and possibly the appeal body for the enforcement decisions (in case the Ministry has this responsibility assigned by the relevant legislation)

- Check the implementation by permitting and enforcement authorities and revise the permitting and enforcement system if adjustments needed (e.g. legal and institutional issues).

The permitting competent authority will be responsible for:

- Operating the integrated permitting system mainly the issuing of permits and their enforcement;

- Conducting regular, planned permit review and variation of permit conditions

- Considering potential transboundary effects of sites under integrated permitting and initiating consultation if necessary within the framework of international co-operation

- Maintain and operate a system for public access to documents from permitting procedure

- Cooperation with enforcing authority (if separate) and BAT support body

- Collect a fee for issuing an integrated permit (if any).

The enforcing competent authority will be responsible for:

- integrated or coordinated inspections of installations which fall under integrated permitting

- cooperation with permitting authority and BAT support body

- operating appropriate monitoring system for verification of the self-monitoring or monitoring done by authorised laboratories if relevant

- Collect fines for non-compliance with the legislation and integrated permits or pollution payments if they are foreseen by legislation.

The BAT support body will be responsible for:

- Providing and updating guidance documents on BAT;

- Maintaining the system for tracking BAT

- Cooperation with industry, permitting authorities and international organisations/networks related to BAT.

### Check list of key tasks needed for implementation of the integrated permitting regime

Since the integrated permitting regime implementation requires many complex changes in relation to environmental regulation this part contains the checklist of key tasks in the preparatory and implementation phases organized in chronological order. They are derived from the Handbook for Implementation of EU Environmental Legislation, chapter 7, part: The IPPC Directive.

Preparatory phase tasks

- Appoint a competent authority (or authorities) to implement and enforce the requirements of the integrated permitting regime as specified in the environmental permitting law

- Determine the interrelationship between EIA and integrated permitting procedures and the proper timing and positioning of these procedures in the line of permitting procedures for large, environmentally significant investments

- The competent authorities, by survey or other means, should identify the installations to which the integrated permitting regime applies throughout the territory

- Determine what relevant types of permitting procedures should be merged into the integrated permitting procedure

- Based on proper legal arrangements, the competent authority should establish liaison arrangements with authorities responsible for the permitting of installations in respect of other legislation

- For each installation, or more generally for main industrial sectors, the competent authority should establish BAT. This may be undertaken through consultation with the industries or industrial sectors or by external research and also taking into consideration BREFs. BAT must be appropriate for the prevailing conditions at the site and take into account the likely costs and benefits as well as applying a precautionary and preventative approach

- The government should take a decision on whether to adopt general rules for specified categories of installations as an alternative to individually determined permit conditions (e.g. farms or landfills)

- Establish emission limit values for all emissions and for all installations having regard to BAT for the installation, so that these may be incorporated as legally binding conditions in permits

- Establish a means of acquiring information on developments in BAT (through BREFs and BAT conclusions) and ensure that the competent authorities are kept informed

- Provide training for the technical staff of the competent authorities

- For integrated permit applications that may have transboundary effects, establish channels of communication with competent authorities in neighbouring country so that consultation may take place (if the consultations are envisaged by the legislation)

- Establish a consultation mechanism to publish applications for permits and to allow for public responses to permit proposals. Capacity-building efforts, such as informing the public on legal remedies and the use thereof, should be part of the public participation provisions.

Implementation phase tasks

- The competent authority should issue guidance on the procedure to be followed, including guidance on the information to be included in applications, and the definitions of BAT for the sector or the specific installation

- The competent authority should establish a procedure by which the proposals put forward in the application are examined for their ability to prevent pollution through the use of BAT and to ensure that no significant pollution is caused, that waste production is minimised or that there is adequate recycling or disposal in such a way that pollution is avoided, that energy is used efficiently, that accidents are prevented, and that the site will be returned to a satisfactory state on completion of activities

- As a result of the examination of the application, the competent authorities should propose emission limit values for releases from the site into all environmental media. Other competent authorities should be consulted, where more than one such authority is involved

- Proposals of permit conditions should be available to the public early in the procedure for a period of time to allow them to comment to the competent authority. The public must have opportunities to participate in procedures for reviewing or updating permits and shall have access to legal remedies before a court of law or another independent and impartial body

- Establish a procedure for the inspection and monitoring of facilities to ensure compliance with permit conditions. The monitoring procedure may involve both the competent authority in inspecting and taking samples, and a degree of self-monitoring undertaken by the operator. The competent authority should decide the amount of self-monitoring which is appropriate for particular installations, and it should specify the conditions to be upheld by the operator in carrying out self-monitoring. An audit procedure should be applied to such results

- A legal obligation should be placed on the operators of installations to inform the component authorities of any changes planned in their operation so that the competent authority can update the permit conditions or in the case of substantial change the competent authorities can issue prior authorisation. Guidance on what constitutes substantial change should be issued to operators

- A legally binding review period should be set requiring the periodic review of authorisations by the competent authority

- The competent authority should implement an enforcement regime for installations which fail to use BAT or which breach their emission limit values or which implement changes without informing the competent authority. This should include the ability to revoke the operating permit, and apply penalties to the operators of the installation.

### Phasing Considerations

Experience within EU Member States with implementing the integrated permitting regime (the IPPC Directive) suggests that the most demanding and time-consuming tasks associated with implementing this regime are:

Phase 1 (period of 3 - 4 years):

- Establishing and developing the institutional structure for integrated permitting of installations, including the enforcement regime by the legal, institutional and financial means

- Surveying and identifying the installations to which the integrated permitting regulation applies

- Establishing a reporting and database system.

Phase 2 (period of 4 - 8 years):

- Establishing BAT reference guidance and methodology for determining emission limit values (ELV). In case the existing ELV prescribed by the legislation will be used for setting integrated permitting conditions, there need to be the clear procedure on the relation between BAT technical standards values and the prescribed ELV

- Implementing the permitting procedures, including preparation of applications, public consultation and issuing permits.

Phase 3 (period of 5 - 10 years):

- Detailed planning, design, permitting and construction of new or upgraded installations to conform to the new environmental standards.

### Functions related to registration regime

Preparatory phase

The main function of national state administration bodies in the preparatory phase is establishing the legal and institutional basis for registration regime implementation. The Ministry of Environmental Protection will be responsible for the following tasks:

- Prepare and issue relevant legislation

- Establish the competent authority for registration

- Set up a system for development of sectoral environmental protection guidelines (SEPG) for low polluting activities

- Appoint suitable personnel to the competent authority staff

- Establish the basis for the electronic registration system.

The development of SEPG can be ensured by state or private organization e.g. the BAT support body. The SEPG should be summary of the basic environmental protection requirements and recommendations applicable to the specific sector e.g. car repair shops, small heating boilers, dry cleaning, hotels etc. The aim of SEPG is to provide all environmental requirements and recommendations in one document for the low polluting installations, which are likely to be SME’s, because without environmental permits, it is unlikely they will be checking in various pieces of legislation which are applicable to them and they should not disregard environmental protection just because they do not have any permit. It is recommendable to have the SEPG ready before the start of issuing the registrations.

The registration authority needs to carry out the following task in order to get ready for registration issuing:

- Select and train personnel responsible for the registration procedure

- Get access and test the electronic registration system

- Establish cooperation with the body responsible for SEPG development.

Implementation phase

The Ministry of Environmental Protection shall have the following functions and responsibilities:

- Ensure methodological support to registration authorities in relation to the interpretation of the legislation

- Maintain the system of developing, consulting and updating GBR

- Check the implementation by registration authorities and revise the system if adjustments needed (e.g. legal and institutional).

The registration authority will be responsible for issuing registrations and recording new and updated registrations in the national electronic system.

Enforcement authority shall have access to the registration system and will be responsible for verifying the categorization of low polluting activities in case of questions or disputes.

## The current situation of institutional changes related to environmental permitting reform in the project countries

In spite of significant differences between the project countries both in institutional division and scope of practical environmental regulation, managerial functions remain the same and system approach and consistency of regulation require presence of all above described institutional elements that certainly can be named differently but have to implement needed functions and responsibilities.

From all seven partner countries Armenia, Georgia and the Republic of Moldova have not a significant number of installations regulated by integrated permitting. Reforming of environmental permitting in Azerbaijan is still in its initial stage, and the Russian Federation consists of too many very different actors, Belarus and Ukraine could be considered as best suitable cases for analysis of the recommended institutional requirements.

Unfortunately Ukrainian Ministry of Environment and Natural Resources went very recently through drastic reforms that make no sense of any practical recommendations. While cancellation of 27 regional agencies of the Ministry from 17 May 2013 after their decades of work from the very first days of independent Ukraine can be somehow explained by goals of administrative reform and by similar experience of EU countries where regional governments deal with environmental permits; transfer of function of permitting authorities from regions to the Ministry headquarters in Kiev for all major pollutants, the IED Annex I installations without any further institutional changes cannot be explained at all.

Therefore only Belarus remains as the country of relevant practical institutional analysis, moreover it now passes through transitional period of full-scale implementation of integrated permits before 2016.

Overview of existing Belarus permitting system and institutional arrangements for IPPC is presented as Annex 1 to this report.

Issuing procedures of integrated permits in the country are based on existing structure of the Ministry of Natural Resources and Environmental Protection and its 6 regional agencies and Minsk city agency. Preliminary work on IPPC implementation was coordinated and headed by Department of Regulation of Impact on Ambient Air and Water Resources of the Ministry as a leading environmental permitting department.

Departments of the state environmental expertise will play role of Designated Administrator. Special BAT centre already operates from end of 2009.

Substantial institutional changes related to environmental permitting reform are going to be implemented in Russian Federation. The main actors will remain the same, but their functions and responsibilities will be changed.

The nowadays system of environmental permits granting is presented at the scheme 2.1.

Scheme 2.1 — Acting environmental permits granting system in Russian Federation

The enterprise is working out ELVs for ambient air emissions and water discharges in accordance with existing guidelines. The values of ELVs are determined on the basis of maximum admissible concentrations (PDK) compliance on the border of sanitary protection zone (for air) and in the chosen section line of the water body (for water). The values of ELVs have to be coordinated with water department and sanitary department at the territory. If there are no objections and the PDKs are not exceeded, the permit is granted by the territorial body of Rosprirodnadzor. If not, the temporary permit can be granted, if the enterprise is able to present the plan of its environmental performance enhancement.

The system is rather non-transparent, the set of water quality standards are unrealistic and not achievable in practice.

The proposed structure of integrated environmental permitting system on the basis of BAT technical standards is presented at the scheme 2.2.

Scheme 2.2 — Proposed integrated environmental permits granting system in the Russian Federation

The proposed system of environmental permits envisages the determination of the ELVs values on the basis of BAT-oriented technical standards. The environmental and public health requirements will be taken into account by the calculation of environmental (health) risk levels.

If the ELVs correspond to the technical standards and risks are acceptable, the territorial body of Rosprirodnadzor grants the integrated environmental permit.

The main differences of the new approach, with the exception of mentioned above ELVs determination, are:

- “one stop shop” principle

- organization of the special inter-departmental commission of the representatives of control (regulative) bodies and executive power of the region.

The Commission plays the main role in the procedure of environmental permitting implementation. In fact its decision is key one in the case when the ELVs do not correspond to technical standards, or the risks are too high. The procedures of the Commission work and decision making are not clear yet and have to be determined later.

# recommendations for the specialized Environmental permitting department

The recommendations for the specialized Environmental Permitting (EP) department are elaborated for the project countries’ Ministries competent for environmental protection. They are elaborated under Subtask 2.1.3.2 under the component 2 of the Air-Q-Gov project.

It is assumed that functions and responsibilities of the specialised Environmental permitting department will cover only permitting under the integrated permitting regime. The enforcement of integrated permits will be carried out by specialized enforcement authority (e.g. environmental inspectorate) as elaborated in chapter 5, and BAT support will be arranged by specialized BAT centre as described in the chapter 6.

## The role of Environmental permitting department in environmental regulatory system

The integrated permitting regime implementation requires one authority responsible for issuing the permits and coordination of consultations with other relevant authorities.

The existing regime with separate media based permits will retain the same functions, but since groups of large and low polluters will be regulated by the other regimes, the load of permitting work shall decrease.

Main function of EP department is to ensure smooth and effective permitting procedure. The following subchapter describes relations of the EP department with stakeholders and tasks of the department.

### Relation of EP department with stakeholders of the integrated permitting system

In order to set suitable and relevant functions and tasks of the EP department, it is important to consider stakeholders’ interests and relations in the integrated permitting regime. The following table contains overview of the relevant stakeholders and their roles or interests in relation to the permitting regime.

Table 3.1 – Principal stakeholders and their roles in the integrated permitting regime

| Stakeholder | Role or interest |
| --- | --- |
| Ministry of Environmental protection | - Preparation and official interpretation of the of legislation - Establishment and control of institutional structure (competent authorities and BAT support body) in the frame of the integrated permitting regime - Methodological support and technical guidance - Dissemination of information related to the regulatory system - Appeal body (depending on the national administrative system) |
| Competent permitting authorities | - Identification of installations for the integrated permitting regime and registration in the National Register - Permitting procedure administration including the elaboration of procedural templates - Data collation and reporting |
| Competent administrative authorities (e.g. environmental and health authorities, local administration bodies) | - Consideration of the application for integrated permit - Issuing statements and proposing permit conditions |
| Inspection authority | - Compliance monitoring and enforcement (inspection) - Consultations within the permitting procedure |
| Operators of industry and agriculture companies under integrated regime + investors | - Assessment of compliance costs - To obtain the permits with feasible conditions - Interest to minimize prosecution and fines - Keen to protect public image and maintain competitiveness |
| Professional and technical institutions/BAT centre | - Representation of industry views - Provision of technical support and BAT guidance |
| NGOs and public | - Representation of public interest - Highlighting environmental issues - Exerting pressure on government and industry |

The following scheme presents relations between EP department and stakeholders in the integrated permitting regime.

Scheme 3.1: Relations between EP department and stakeholders

The red arrows show the main relations during the permitting procedure. These relations include submitting the application for permit to EP department, communication about the application with operator, competent administrative authorities and public, and issuing of the permit. The black arrows represent other relations needed for functioning of the integrated permitting regime such as preparation of BAT guidance, technical support by BAT centre, communication with Ministry and inspectorate. The first interrupted arrow indicates the communication between EP department and inspectorate during the permitting procedure, which is not mandatory and can depend on the technical aspects of setting permit conditions. The second interrupted arrow indicates possible technical support of BAT centre to EP department during permitting procedure, which can be used in case of complex installations or in case of lack of BAT guidance for the specific case. The double-sided arrows show that relation with all stakeholders needs to be mutual.

### Work scope of EP department

When the environmental permitting authority is formally established it shall prepare itself for the permitting function. The following responsibilities and tasks are proposed for practical preparation of the permitting authority for implementation of the integrated permitting procedure:

- Set up appropriate staff structure of the EP department (either by restructuring existing staff of the authority or hire new staff with relevant qualification in line with the available financial framework)

- Training of the personnel in relevant legislation, administrative procedures and through participation in pilot permitting projects

- Establish integrated permitting regime and procedure within the organizational structure and participate in consultation about the relevant legislation with the Ministry of Environmental Protection

- Establish administrative mechanism for consultations with competent administrative authorities and for public involvement in permitting and test the proposed mechanism in pilot permitting projects

- Establish system for permit review and variation including procedure for distinguishing minor changes and substantial changes of installations’ operation

- Establish system of the public access to permits and information about permitting procedure (e.g. electronic public register) in cooperation with the Ministry of Environmental Protection.

Implementation phase

The permitting authority will be responsible for:

- Administration of the integrated permitting procedure including providing consultations to operators prior official submission of an application

- Conducting regular, planned permit review and variation of permit conditions

- Considering potential transboundary effects of sites under integrated permitting and initiating consultation if necessary within the framework of international co-operation

- Maintain and operate a system for archiving documents of permitting procedures and for publishing relevant documents in order to ensure the public access

- Cooperation with enforcing authority (if separate) and BAT support body in case of need for technical support during assessing the permit application and setting up permit conditions

- Collect a fee for issuing an integrated permit (if any).

Integrated permitting procedure includes the following steps:

- Communication and consultation with applicants for integrated permit including site visits

- Coordination of requirements of related administration authorities – competent administrative authorities

- Publishing information about permitting procedure and decisions

- Public meetings

- Maintain database of installations under integrated regime and database of permitting procedure documents

- Installations sites visits

- Cooperation with the Ministry of Environmental Protection (e.g. on legal interpretation of the legislation and appeals)

- Cooperation with inspectors

- Cooperation with BAT support centre

- Collection of permit fees if any.

Some steps of this permitting procedure are identical or similar to the existing permitting procedures, but steps no. 2, 3, 8 and 9 are new additional steps which are required for the integrated procedure.

Step no. 2: Coordination of competent administrative authorities

The most complex and difficult is the coordination of competent administrative authorities, who are used to carry out their own procedures and issue permits or approvals, but under the integrated regime, their status is changed. Depending on the scope of integration, competent administrative authorities can include water resources, quality of ambient air protection, waste management, noise/health, nature protection, agriculture, and energy authorities. In order to ensure effective coordination, the instructions for the consultees and administrative steps have to be clearly defined and agreed.

Lack of instructions for the consultees was causing problems in the beginning of the implementation of the integrated permitting regime in many EU countries from central and Eastern Europe. The main part of these instructions is defining what part of application for permit needs the consultees’ review and consideration and what should be the content of the consultees’ statement (e.g. proposal or permit conditions with justification).

Step no. 3: Publishing information about permitting procedure and decisions

Publishing information about permitting procedure include publishing the following documents: non-technical summary of the permit application, permit application or permit conditions and decision about permit conditions. The most effective way to ensure publishing this information is to establish specialized electronic public database linked with the database of installations and permitting procedure documents. This combined administrative-public database can ensure that all information is stored in one place and can be used at the difference access levels.

Steps no. 8 and 9: Cooperation with BAT support centre and/or inspectors

Establishing cooperation with BAT centre depends on the activities of the BAT centre and on the technical knowledge of EP department permit writers. In case the permit writers have little technical knowledge and experience in order to consider the correctness of BAT assessment and proposed permit conditions in the applications, it may be useful to provide the technical support in the form of application review by technical experts from BAT centre or inspectorate. The result of the review can be the statement on BAT assessment and/or comments on proposed permit conditions which will be in the form of non-binding recommendation for the permit writer.

## Organisational, human and technical requirements

### Organisational requirements and scheme

The management and organization of the EP department will depend on the fact in which authority the permitting function will be placed. This will infer from the current distribution of permitting functions and should be stipulated by the law on environmental permitting. Generally there are the following possibilities of the permitting function delegation:

- Ministry of Environmental Protection at central level

- Ministry of Environmental Protection at regional level

- Environmental inspectorate

- Regional authorities

- Regional and county authorities

- Newly established national permitting agency.

Placing the integrated permitting in the central office of the Ministry of Environmental Protection is recommendable for small countries where the current permitting is ensured by the Ministry’s central office and where the number of installations falling under the integrated permitting regime will be up to 200.

Placing the integrated permitting in regional offices of the Ministry of Environmental Protection is recommended for bigger countries where the regional offices ensure currently permitting and where the number of installations falling under the integrated permitting regime will be more than 50 per region.

Placing the integrated permitting in the Environmental inspectorate is recommendable for countries where either the current permitting is ensured by the inspectorate or where environmental inspectors are the only technically capable resources to cope with integrated permitting.

Placing the integrated permitting in regional authorities is recommended for bigger countries where the regional authorities already have some experience with permitting and where the number of installations falling under the integrated permitting regime will be more than 50 per region.

Placing the integrated permitting in regional and county authorities is recommended for large countries where the regions and counties ensure currently some environmental permitting/approvals and where the number of installations falling under the integrated permitting regime will be over 200 per region. Based on European experience the combination of permitting by regional and county authorities is used in Poland and England. It is usually specified which category of industry/agriculture is administered in which level, e.g. farms and landfills can be permitted on county level since there are many of them and they are relatively simple installation for setting permit conditions.

The newly established national permitting agency is a possibility for integrated permitting for those countries which need to transform their current system and need to combine technical and administrative functions in one institution. Such an agency can combine several functions needed for implementation of integrated permitting (BAT technical support, permitting, enforcement and reporting).

The organizational scheme can be the same for any decentralized level (i.e. regional offices of the Ministry of Environmental Protection, regional authorities, counties or inspectorate). Based on experience in EU countries there is a need of approximately 5 permitting officers per 200 installations. Thus the EP department on regional or county level shall include permitting officers, administrative staff and a manager. There has to be link with IT department of the authority in order to ensure electronic administrative database and publishing relevant information ideally in Internet. In addition there should be established cooperation with media based departments which are responsible for air protection, water and waste permits. The model organization scheme is present on the following scheme.

Scheme 3.2: EP department’s organisational scheme with link to the structure of the authority on regional level

### Human resources

The administration of integrated permitting procedure requires staff with technical experience and administrative knowledge. The experience with operating EP departments in EU countries shows, that one permit writer can administer approximately 50 installations. To administer an installation means to issue the first integrated permit in line with the phase in schedule and afterwards to administer changes in issued permits and review of permits. As mentioned above it is assumed that the ordinary EP department will be responsible for about 200 installations. In such a case it is recommended that the EP department has five permitting officers, one administrative staff and one manager.

Permitting officers will primarily ensure the permitting procedure. They can be specialized depending on the main sectors which are present in their territory. The administrator will carry out administrative support related to incoming and outgoing correspondence, publishing relevant documents in Internet, arranging public meetings and administrative check of applications and issued permits.

The manager’s role will be extremely important in the preparatory stage since he/she will be responsible for establishing the cooperation with competent administrative authorities (other relevant authorities or relevant department within the administrative body) and handling difficult cases of applications for integrated permits. In the implementation stage he/she will be responsible for monitoring of the permitting procedures and checking the quality of issued permits.

Qualification of a permitting officer

The permitting officer needs to have the following qualification:

- Technical education (University degree)

- Minimum 3 years of experience from relevant industry sector (ideally as environmental manager or technician) and/or experience with environmental permitting or enforcement

- Computer literacy

- Knowledge of environmental legislation

- Good communication skills.

Depending on the experience and knowledge of the permitting officer the following training may be needed:

- Administrative procedures needed for processing the permitting procedure

- Environmental legislation (relevant aspects related to integrated permits)

- Environmental performance of relevant sectors and related BAT guidance

- Communication and negotiation skills.

It is also recommendable for the permitting officers to participate in any project focused on simulation of integrated permitting procedure as well as on site visits to plants within their region.

### Technical equipment

The EP department will need the following equipment for administration of the integrated permitting procedure:

- Office equipment (computers, printers, copy machine, phones, scanner)

- Access to meeting rooms for public meetings

- Permitting database with limited public access

- Electronic and physical archive for documents

- Car for site visits.

The permitting database is recommended to be organized on national basis allowing restricted access to individual permitting officers to insert documents and authorize them for public access. The advantage of common national database is sharing of knowledge about issued permits.

## Phases of developing and operating EP department

The implementation of integrated permitting regime requires carrying out several preparatory tasks, because it is necessary to transform and/or develop institutional, technical and administrative capacities. The following tasks should be performed in the first phase of preparation for integrated permitting by the EP department:

- Establishing and developing the institutional structure for integrated permitting of installations and ensure institutional and financial means

- Surveying and identifying installations under integrated permitting regime

- Establishing a reporting and database system.

The preparatory phase’s tasks should be carried out under the coordination of the central implementation body (i.e. Ministry of Environmental Protection). The identification of installations falling under integrated permitting regime is very important as it will be the basis for planning the next phase.

This phase can last 2 – 4 years depending on readiness of administrative bodies relevant to the permitting system.

The next phase should be carried out in accordance with the realistic implementation plan with consideration of the human, technical and financial capacities available in EP departments and industry. The main tasks of EP department in the second phase are:

- Establishing technical standards for BAT and determining emission limit values

- Implementing the permitting procedures, including preparation of applications, consultations and issuing permits.

This phase can last 4 - 8 years depending on the number of installations requiring the integrated permit, number of permitting officers and administrative demands of the permitting procedure.

After issuing of integrated permits for all installations under the integrated regime, the third phase comes. In this phase the tasks of the EP department include:

- Regular permit reviews and updates based on the legal requirements (period for permit revision or updates of related legislation)

- Consideration of changes announced by operators and related procedures for  permits update

- Implementation reporting to the central implementing body and cooperation with related authorities (e.g. inspectors).

This phase represent the “normal” operation of EP department. Experience of EU Member States with operating integrated permitting regime shows, the following frequency of announced changes by operators. Simple installations (e.g. farms and landfills) announce one change every 2 – 3 years. More complex installations (e.g. energy production) have at least one change per year and the most complex installations, or plants (e.g. chemical production) have 2 – 3 changes per year. Approximately 30% of all announced changes are not significant, so they do not require any permit update or only an administrative change. The remaining 70% require change of some permit conditions and thus the permitting procedure with consultations has to be carried out.

## The current situation with setting up the EP department in the project countries

### Relevant public administration body for the EP department in Belarus

The functions of EP department of the Ministry of Natural Resources and Environmental Protection of the Republic of Belarus are established by the Decision of President of 17.11.2011 № 528. The EP department has to:

- In 5 working days from the submission of application to inform the operator about the application completeness and its acceptability

- In 10 working days from the date of permit application submission to place the information about the application in Internet for collecting the comments from the public

The permit can be granted in 2 month or the application can be rejected. It is taken into account: The information provided to the public

- Compatibility of the presented data with legal requirements, environmental standards and permitted impacts, environmental targets established by the spatial planning programmes and other environmental protection plans and programmes in the region

- Compatibility of the planning activity to BAT

The Resolution of the Ministry of 20.12.2011 № 53 has established the templates for permit application and integrated environmental permit. Also the Guidance for applicant was worked out.

The preparatory work has been done and, in accordance with the Ministerial plans, the first integrated environmental permits will be granted at the end of 2013.

### Ways of ensuring effective coordination of competent administrative authorities within integrated permitting procedure

Beside routine coordination of different governmental institutions dealing with different aspects of environmental protection and environmental management the new element crucial for effective integrated permitting is creation and active work of sectoral technical working groups.

Period of strong Soviet system of numerous sectoral R&D Institutes gradually expires in all EECCA countries; they have to be substituted now by system of national sectoral TWGs with immediately established links with professional international networks like information exchange forum for IPPC (IED).

## Conclusions and recommendations

The Environmental Permitting department responsible for implementation of the integrated permitting regime can be established within the existing administrative authority responsible for issuing air, or water or waste permits. It is better to arrange separate department, but it is also possible to transform for example air pollution department into EP department. The existing permitting officers will have less work with media based permits, so some of the experienced and technically knowledgeable staff can be moved to the EP department. Alternatively the EP department can be established within new Environmental agency (covering also permitting function) in such a case, where there is a political will and financial means to do that.

The EP department has to be established a few years before the actual start of issuing integrated permits in order to ensure the preparatory tasks. The main preparatory tasks are cooperation in the inventory of installations and establishing administrative mechanism for consultations with authorities which are issuing media based permits and in the integrated regime their competence will be transformed to consultation on the draft integrated permit.

In the implementation phase the EP department will be responsible mainly for integrated permitting procedure and subsequent permit reviews and changes.

It is recommended to appoint 5 permitting officers for about 200 installations falling under the integrated regime. The EP department with 5 permitting officers will need also one manager and one administrative support staff.

The workload of the department during issuing the first integrated permits can be handled only with realistic phase in schedule, flexible administrative procedure and good cooperation with competent administrative authorities - authorities who are issuing media based permits and in the integrated regime their competence will be transformed to consultation on the draft integrated permit.

# recommendations for the competent ADministrative Authorities and registration authorities

The recommendations for the integrated permitting and registration authorities are elaborated for the project countries’ Ministries competent for environmental protection. They are elaborated under Subtask 2.1.3.3 under the component 2 of the Air-Q-Gov project.

Integrated permitting authorities include the permitting authority responsible for issuing integrated permits and competent administrative authorities (further mentioned as CAA) which participate in the permitting procedure through consultations and/or their statements. The recommendations for the specialized integrated permitting authority are described in the chapter 3. Therefore these recommendations focus primarily on CAA.

Registration authorities are the authorities designated by the Environmental Permitting law which will be administering regulatory system of environmental registration for the operation of low polluting activities.

The enforcement of integrated permits and possibly also of the registration will be carried out by specialized enforcement authority (e.g. environmental inspectorate). The recommendation for the enforcement and inspection activities will be described in the Recommendations for inspection authorities in chapter 5.

## The role of CAA in environmental regulatory system

The integrated permitting regime implementation ideally requires one authority responsible for issuing the permit and coordination of consultations with other relevant Competent Administrative Authorities (CAA).

The existing regime with separate media based permits will retain the same functions, but since groups of large and low polluters will be regulated by the other regimes, the load of permitting work shall decrease.

Since the role, work scope and organisational issues related to the specialized integrated permitting authority are described in the chapter 3, this part focuses on other authorities participating in the integrated permitting procedure and puts emphasis on the cooperation between the permitting authority and the CAA which participate in the permitting procedure through consultations and/or their statements. The following subchapter describes relations of CAA with stakeholders and tasks of these authorities.

### Relation of competent administrative authorities with stakeholders of the integrated permitting system

Competent Administrative Authorities (CAA) can include the following authorities depending on the scope of integration of the integrated permit set by the EP law and by national division of functions and competencies between various ministries and subordinated administrative bodies:

- Ambient air protection authority

- Water protection authority including river basin authorities and sewerage authorities if separate

- Waste management authority

- Nature protection authority

- Health authorities,

- Energy saving authority,

- Agriculture authorities (e.g. veterinary authority)

- Municipal and local administration bodies.

In case there are other relevant authorities which competencies are not covered by the permitting authorities, they should be included as well (e.g. EIA or accident prevention issues).

In order to set suitable and relevant functions and tasks of CAA, it is important to consider stakeholders’ interests and relations in the integrated permitting regime. The table 3.1 in the chapter 3 contains overview of the relevant stakeholders and their roles or interests in relation to the permitting regime.

The following scheme presents relations between CAA and stakeholders in the integrated permitting regime.

Scheme 4.1: Relations between CAA and stakeholders

The red arrows show the main relations during the permitting procedure. These relations include submitting the application for permit to the permitting authority, communication about the application with operator, CAA and public, and issuing of the permit. The black and blue arrows represent other relations needed for functioning of the integrated permitting regime such as preparation of BAT guidance, technical support by BAT centre, communication with Ministry and inspectorates. The first interrupted arrow indicates the communication between permitting authority and inspectorates during the permitting procedure, which may not be mandatory and can depend on the technical aspects of setting permit conditions. The second interrupted arrow indicates possible technical support of BAT centre to the permitting authority during permitting procedure, which can be used in case of complex installations or in case of lack of BAT guidance for the specific case.

The blue arrows show possibilities for communication of CAA with the operators and with the relevant inspection authority. The communication between CAA and operators can cover, for example, consultations on the draft application and draft permit conditions in difficult cases before or during the permitting procedure. The communication between CAA and relevant inspection authority can include consultations on the content of integrated permit and about suitability of the proposed permit conditions since the competent inspector shall have more practical knowledge about the existing operations.

The double-sided arrows show that relation with all stakeholders needs to be mutual.

### Work scope of CAA

When the environmental permitting law is approved and the permitting authority is formally established, it shall prepare itself for the permitting function as well as cooperate with CAA in their preparation for the consultation role. The following responsibilities and tasks are proposed for practical preparation of CAA for implementation of the integrated permitting procedure:

- Get in touch with the permitting authority on the relevant level

- Propose appropriate organization and staff structure for consultations during integrated permitting procedure

- Participate in the pilot project for simulation of the permitting procedure

- Establish administrative mechanism for consultations with the integrated permitting authority (prepare guidance with procedure for application review, list of decisions/approvals which are replaced by integrated permits within the competence of the relevant CAA)

- Training of the personnel.

Implementation phase

CAA will be responsible for:

- Consultations during and possibly also before the integrated permitting procedure

- Elaborate statements with proposal of permit conditions related to the competence of the specific CAA in the environmental protection

- Cooperation on variation of permit conditions in case the permitting authority requests for

- Cooperation with enforcing authority and BAT support body.

As it is described earlier integrated permitting procedure includes the following steps:

- Communication and consultation with applicants on integrated permit including site visits

- Coordination of requirements of related CAA

- Publishing information about permitting procedure and decisions

- Meetings about the draft permit conditions

- Maintain the database of installations under integrated regime and database of permitting procedure documents

- Site visits to installations

- Cooperation with the Ministry of Environmental Protection (e.g. on interpretation of legislation and appeals)

- Cooperation with inspectors

- Cooperation with BAT support centre

- Collection of permit fees if any.

CAA takes part in steps no. 2, 4, 5, 6, 7, 8 and 9. Some steps of this permitting procedure are identical or similar to the existing permitting procedures, but steps no. 2, 3, 8 and 9 are new additional steps which are required for the integrated procedure. The step no. 2, 8 and 9 are described in detailed further as they are relevant to CAA.

Step no. 2: Coordination between permitting authority and CAA

In order to ensure effective coordination, the instructions for the CAA and administrative steps have to be clearly defined and agreed. Ideally these instructions should be proposed by the permitting authorities and consulted with all relevant CAA before finalisation. It is very important to understand which CAA statements or their parts are binding for the permitting authority and which have a form of recommendations in order to have clear scope for the decision making of the permitting authority as well as for CAA.

Detailed administrative steps or sub-procedure in each CAA needs to be proposed and approved on the relevant organisational level of CAA.

Lack of instructions for CAA was causing problems in the beginning of the implementation of the integrated permitting regime in many EU countries from central and Eastern Europe.

Steps no. 8 and 9: Cooperation with BAT support centre and/or inspectors

Establishing cooperation with BAT centre depends on the activities of the BAT centre and on technical knowledge of the staff of CAA responsible for consultations. In case the CAA staff have little technical knowledge and experience in order to consider to the correctness of the relevant BAT assessment parts and proposed permit conditions in the applications, it may be useful to cooperate with the BAT centre or relevant inspectors. The result of the cooperation should be increased technical knowledge and good orientation in BAT guidance which will help in reviewing the application and setting up appropriated permit conditions and related justification in the CAA statement.

### Organisational requirements for CAA

The management and organization of the CAA staff which will carry out consultations during the permitting procedure will depend on the fact in which relation will be the concrete CAA with the integrated permitting authority. This will infer from the current distribution of permitting functions and should be stipulated by the law on environmental permitting. Generally there are the following possibilities of the relation with the permitting authority:

- CAA is in the same authority as the permitting authority (e.g. various departments within the Ministry of Environmental Protection at central or regional levels)

- CAA is subordinated organization to the permitting authority (e.g. authority with delegated powers from Ministry of Environmental Protection)

- CAA is different authority which is under the jurisdiction of other Ministry then the Ministry of Environmental protection (e.g. Health authorities, municipalities).

Concerning the organization of CAA staff responsible for consultations related to the permitting procedure, the staff does not need to be organizationally separated from the existing departments or units. Based on EU experience the CAA staff is usually appointed to deal with the requested statements, nevertheless this task is given to existing CAA employees, who are dealing with permits and approvals, which are replaced by the integrated permit. Since the existing administrative procedure for issuing individual permits and approvals is replaced with the consultations during integrated permitting for the large polluting installations and issuing of the statement with proposed permit conditions, there is no need to increase the CAA staff.

Nevertheless, in each CAA there should be appointed one coordinator, who will be the contact point for the integrated permitting authority and who should be responsible for coordination of the other appointed CAA staff in the agenda of integrated permitting consultations.

### Recommendations for the project countries

Ways of ensuring effective coordination of CAA within integrated permitting procedure in each project country should follow the same system approach with overall consideration of local features.

## The role of registration authorities in environmental regulatory system

The environmental regulation of low polluting installations is based on simple registration of these installations by the registration authority. In order to minimize the administrative burden for low polluting operations, the registration authorities should be decentralized. Ideally the registration authorities could be placed in the municipal authorities or in such authorities where the business registration of small and medium size companies takes place.

The removal of low polluting installations from the existing permitting and approval system will result in certain decrease of the workload of the existing permitting authorities.

The following subchapter describes relations of registration authorities with stakeholders and tasks of these authorities.

### Relation of registration authorities with stakeholders of the environmental regulatory system

In order to set suitable functions and tasks of the registration authorities, it is important to consider stakeholders’ interests and relations in the environmental registration regime. The following table contains overview of the relevant stakeholders and their roles or interests in relation to the regulatory regime.

Table 4.1 – Principal stakeholders and their roles in the registration regime

| Stakeholder | Role or interest |
| --- | --- |
| Ministry of Environmental Protection | - Preparation and official interpretation of the of legislation - Support the establishment of institutional structure of the environmental registration regime - Methodological support and technical guidance (i.e. ensure development of sectoral environmental protection guidelines (SEPG) - Dissemination of information related to the registration system |
| Registration authorities | - Registration procedure administration - Data collation and reporting |
| Expert body for GBR or contract based experts | - Development of SEPG for low polluting installations |
| Inspection authorities | - Verification of the categorization of low polluting operations in case of question from Registration authorities - Inspections in case of public complains |
| Operators of law polluting installations + investors | - To obtain the registration - Announce changes in operation in relation to the categorisation |
| NGOs and public | - The right to complain about possible nuisance from operations of low polluting installations |

The following scheme presents relations between registration authorities and stakeholders in the registration regime.

| Low polluting installations |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

Scheme 4.2: Relations between registration authorities and stakeholders

### Work scope of registration authorities

When the environmental permitting law is approved and the registration authorities are formally established they should prepare themselves for the registration function. The following responsibilities and tasks are proposed for practical preparation of the registration authority for implementation of the registration procedure:

- Propose appropriate organization and staff structure for the registration procedure during the transitory period and for the normal implementation period

- Establish administrative mechanism within the authority

- Appoint and train suitable personnel for the registration procedure

- Get access and test the electronic registration system

- Establish cooperation with the body responsible for SEPG development.

The development of SEPG can be ensured by state or private organization e.g. the BAT support body. It is necessary to have the SEPG ready before the start of issuing the registrations. The registration authority needs to know which SEPG are applicable to which type of operation in order to advise to the applicants for registration on the SEPG relevant for their operations.

The registration authorities shall have the following functions and responsibilities during implementation phase:

- Administration of the registration procedure for existing and new installations

- Recording new and updated registrations in the national electronic register and reporting on the progress

- Communication with environmental inspectors in case of unclear categorization of low polluting installation

- Be informed about the development of SEPG for low polluting installations.

The aim of progress reporting and communication with inspectors is to share information about progress and categorization of unclear cases with other registration authorities in order to share the experience especially in the first years after the start of the registration regime.

### Organisation requirements for registration authorities

The management and organization of the registration authorities’ staff which will carry out registration procedure will depend on the fact in which authority will the registration function be placed. This will infer from the current distribution of environmental permitting functions and business registration and should be stipulated by the law on environmental permitting. Generally there are the following possibilities where to place the registration function:

- Registration authority can be in the same authority as the existing permitting authority (e.g. within departments of the Ministry of Environmental Protection at central or regional level);

- Registration function will be delegated to regional, county or municipal authorities which are not issuing any environmental related permits in the existing system, but which are issuing the business registration.

In case the registration function is within the existing permitting authority, some of the permitting officers which have been dealing with issuing permits or approvals will be responsible for the registration administration. This solution has the advantage of technical and administrative knowledge in checking the correctness of the registration form. Nevertheless, in case this authority is not at the same time responsible for the business registration, the simplification of the administrative burden for the relevant operators will be limited, since the operator of low polluting installation will have visit another authority apart from business registration.

In case the registration function is in the municipal or country authority, it will be more convenient for the operators, but the staff of the authority will need to be more thoroughly trained in order to assess the information in the environmental registration form. Nevertheless, this can be overcome by proving the low environmental impact by existing operators through the last environmental or operational permits and arrange possible consultations with the relevant department at the Ministry of Environmental Protection responsible for the registration system.

In both cases the registration authority should be able to utilize the service of environmental inspectors in case of unclear cases of categorization for low or medium polluting operations.

Based on EU experience, the environmental regulation of low polluting activities is usually dealt with the municipal or county authority as it does not require extensive technical knowledge and the local people know any potential problem by living in an area together with an operator.

Concerning the workload at the transitory implementation phase, where the existing operators will be switching to the registration system and new operators will be registering as well, it is necessary to have a good plan in order to manage the administration without huge increase of the staff or delays. Ideally there should be the plan phased out of some sorting in accordance with industry sectors or place of the operation. Each group of operators will have specific period to ensure the registration. In case of using the sectoral approach, it is useful to adjust the time plan for registration with the time plan for developing SEPG for the relevant sectors.

The time needed for the transfer from the current system to the environmental registration for existing operations depends on the number of operators at the given territory and the number of registration officers.

## Conclusions

### Conclusions for the CAA

The integrated permitting regime requires establishing the integrated permitting authority responsible for issuing the permit and coordination of consultations with other relevant competent administrative authorities (CAA).

The main function of CAA is consultations about the draft permit conditions during the permitting procedure. In the preparatory phase the main task of CAA is to establish flexible administrative mechanism for consultations with the integrated permitting authority, which would allow CAA to apply the right to review the application for permit and express comments to the proposed permit conditions or to propose other permit conditions.

In the implementation phase the CAA main task will be consultation during the integrated permitting procedure and elaboration statements with proposal of permit conditions related to the competence of the specific CAA in the environmental protection.

Concerning the organizational point of view, the consultation function is given to existing CAA employees who are dealing with permits and approvals which are replaced by the integrated permit. Since the existing administrative procedure for issuing individual permits and approvals will be replaced with the consultations during integrated permitting for the large polluting installations and issuing of the statement with proposed permit conditions, there will be no need to increase the CAA staff.

### Conclusions for the registration authorities

The environmental regulation of low polluting installations is based on environmental registration of these installations by the registration authority. It is recommended to add the registration function to the regional/local authorities.

In the preparatory phase the main task of the registration authorities is to establish the administrative registration mechanism within the authority and test the electronic registration system.

Since the low polluting installations will be operated without other permits or approvals, it is recommended to develop a set of sectoral or general environmental protection guidelines (SEPG). Nevertheless the development of SEPC is not a reason for waiting with the start of the registration regime. The development of SEPC can be ensured by state or private organization e.g. the BAT support body.

In the implementation phase the registration authority main task will be the administration of the registration procedure for existing and new installations.

Concerning the workload at the transitory implementation phase, where the existing operators will be switching to the registration system, it is necessary to have a good plan in order to manage the administration without huge increase of the staff. The time needed for the transfer from the current system to the environmental registration for existing operations depends on the number of operators at the given territory and the number of registration officers.

# recommendations for the Integrated Environmental Inspection authorities

The recommendations are derived from experience with implementation of inspection regimes cycles in EU in relation to the EU Minimum Criteria for Environmental Inspection (2001/331/EC), the IMPEL Management Reference Book for Environmental Inspectorates (2003), the IPPC Directive (2008/1/EC), the IE Directive (2010/75/EC). Comprehensive manual for IPPC inspectors (Zagreb, 2009) can be found at the site:

http://www.mzoip.hr/doc/IPPC/BAT_Manual_IPPC_inspections.pdf

or at http://impel.eu/wp-content/uploads/2013/07/Step-by-step-guidance-for-IED-Inspections-June-2013-final-080713.pdf.

To be implemented for example in Belarus the recommendations are therefore have to be more not specifically related to county’s context and should be assessed further in a national environmental context.

Integrated Environmental Inspection holds the execution function of the regulatory cycle. It is the Inspectorates that ensure compliance with the environmental framework through regular compliance checks with the companies’ permits. If the inspection and enforcement of the legal framework is not effective, then the regulatory cycle tends to fail. Therefore the development of an effective inspection body and inspection scheme shall have high priority.

It is assumed that functions and responsibilities of the Inspection Authority are organized in national authorities with regional offices (Environmental Inspectorates) specialised in environmental control and enforcement, and that BAT support is arranged by a specialized BAT centre.

## The role of Integrated Environmental Inspection in the Regulatory Cycle

An integrated environmental inspection regime requires a dedicated authority responsible for controlling and promoting compliance with environmental permits through inspection - and eventually responsible for enforcement of environmental legislation and permits.

Moving from a separate media based inspection regime to integrated inspection is in many countries considered as a resource effective step towards achieving compliance with an increased number of inspections (with the same amount of allocated resources to the field).

The main function and responsibility of the Integrated Environmental Inspection unit is:

- To conduct a regular (e.g. 2-4 years) effective compliance check with the environmental permit

- To process enforcement procedures when non-compliances are identified

- To conduct follow up checks for non-compliant companies

- To formulate strategies and conduct inspection campaigns for selected sectors and themes

- To assure coordination and feed back to permitting authorities if e.g. the permit conditions are weak

- To maintain and update procedures for integrated environmental inspection in accordance with experience achieved and the development of the environmental legal framework.

The operators have to understand that the compliance control is the integral part of the whole Regulatory cycle. The distinctive phases of this cycle are shown at the scheme 5.1

Scheme 5.1 — Regulatory cycle. The phases of compliance promotion and compliance control are the integrated parts of it

### Setting up the Integrated Environmental Inspection Authority

Setting up effective environmental inspectorates is a complex task requiring a broad organisational approach. The following tasks are found relevant as part of the practical establishment of the Integrated Environmental Inspection Authority (IEIA):

Organizational task

- Define the goals, targets and scope of the IEIA

- Set up appropriate staff structure of the IEIA

- Training inspectors in procedures for integrated inspection, compliance check, compliance promotion and enforcement

- Establish appropriate monitoring and documentation mechanisms to record, file and track activities related to permits/companies

- Establish a risk assessment tool and prepare annual inspection plans to assure prioritization of inspection resources with key focus on high risk/large polluting companies

- Establish communication mechanism to assure update with the environmental legal framework

- Establish system for the administrative procedures and documentation in a way that public/companies can request access to decisions with regard to inspection and enforcement

- Establish an administrative routine for issuing of fines (payment should be directed to central authorities).

Inspection procedures

Inspections procedures can be divided at 3 stages: the preparatory one, inspection itself as working at the site, and the final one. The content of the stages is shown at the scheme 5.2.

Scheme 5.2. — The stages of the inspection

Integrated inspection procedures should include the following activities:

- Distribution of announcement letters to companies selected for inspection (if so chosen – also inspection visits without prior notification may take place)

- Site visits and communication with companies/permit holders

- Recommendations to set up self-monitoring programmes

- Recording of findings in company track files/database

- Execution of enforcement in case of non-compliance according to procedures stated in the legal framework

- Preparation of inspection campaigns

- Coordination with other authorities

- Cooperation with the Ministry of Environmental Protection (e.g. on legal interpretation)

- Cooperation with the Integrated Permitting Authorities

- Cooperation with BAT support centre.

If the inspectors have little technical knowledge and experience with BAT/BREFs, technical support from the BAT centre will be useful.

During the preparation of inspection the check-lists have to be worked out, the priority installations have to be blueprinted, the tables for comparing of performance levels and standards indicated in the permit. The necessary equipment has to be distinguished and prepared (for taking probes, making analysis, photo and video records).

On-site inspection has not to be only a supervisory one. The experienced inspector can work also as a consultant and has to do so.

The main principles of inspection and enforcement approaches are generally consider the following:

- Proportionality – enforcement actions will be proportionate to the risks posed to the environment and the seriousness of the breach of law;

- Consistency – similar approach in the use of powers and decisions in similar circumstances to achieve similar ends;

- Transparency – it helps the regulated community and others to understand what is expected of them and what they should expect from authorities;

- Firmness – a firm approach sets the limits of the flexibility in an enforcement strategy. The limits should be fair and stringent;

- Fairness – the public and the regulated community generally support fair actions and disagree with unfairness. Fairness helps to establish the rule of law and thus of environmental improvements.

## Organisational recommendations

The organization and management of the inspectorates depend not least on the relation to the permitting function – in some countries permitting and inspection functions are under the same authority, but in most countries the two functions have been divided between two authorities.

- The benefits of the one-legged organisation include effective coordination between permit issuing, formulation and control conditions, and input from regular inspections to permit writers

- The benefits of the two-legged organisation are not least the water proof doors between permitting and inspection functions not allowing inspectors to control a permit submitted by themselves.

The integrated inspection function should be placed in one of the following authority:

- Existing media based inspectorates

- Regional environmental authorities (focusing on larger polluting installations)

- Municipal environmental authorities (especially focusing on low polluting installations)

- Ministry of Environmental Protection, regional offices (if more than 50 enterprises with environmental permits in each region)

- Regional or municipal permitting units (especially relevant where the number of skilled staff is limited).

Based on experience in EU countries an inspector is able to plan, conduct, and report 30-40 inspections per year assuming that the distances to the installations are not prohibitive for achieving this target.

The need for inspection of an installation can only be judged from an assessment of its risk profile (sector, technical condition, compliance history, environmental system) and its operational performance. The average frequency for inspection in many EU countries is one inspection every second year per installation.

### Human resources recommendations

Integrated inspection requires staff with technical experience and very good knowledge of the regulatory cycle.

Inspectors can be organized as sector specialists with each their responsibility for defined sectors or technologies. This is usually a way forward to assure the appropriate capacity to assess the installations’ compliance. Effective inspection requires an in-depth understanding of the polluting installations’ processes, technologies, production constraints – pared with knowledge of relevant cleaner technologies and pollution prevention technologies, e.g. filter- or cleaning systems, ventilation, etc.

Qualification of an integrated environmental inspector

The inspector needs to have the following qualification:

- Technical education (university degree)

- Experience with the environmental regulatory cycle – permitting, inspection, enforcement

- Technical knowledge, BAT/BREF knowledge, pollution prevention knowledge

- Ability to advice installations in environmental progress for compliance

- Knowledge of environmental legislation

- Good communication skills.

# recommendations for the BAT expert support body

The recommendations for the BAT support body are elaborated for the project countries’ Ministries competent for environmental protection. They are elaborated under Subtask 2.1.3.2 of the Component 2 of the Air-Q-Gov project.

It is assumed that functions and responsibilities of the integrated permitting authority will cover permitting under the integrated permitting regime. The enforcement of integrated permits will be carried out by specialized enforcement authority (e.g. environmental inspectorate), and BAT support will be arranged by specialized BAT support body.

## The role of BAT support body in environmental regulatory system

The objective of BAT support body is to facilitate information exchange on BAT and ensure information and technical support in relation to integrated permitting regulation.

The role of BAT support body in the integrated permitting regime is technical and information support of regulatory stakeholders in implementation of BAT.

The following subchapters describe relations of the BAT support body with stakeholders, functions and tasks of the department.

### Relation of BAT support body with stakeholders of the integrated permitting system

In order to set suitable and relevant functions and tasks of the BAT support body, it is important to consider stakeholders’ interests and relations in the integrated permitting regime. The table 3.1 from the chapter 3 contains overview of the relevant stakeholders and their roles or interests in relation to the integrated permitting regime.

The following scheme presents relations between stakeholders in the integrated permitting regime.

Scheme 6.1: — Relations between BAT support body and stakeholders

The red arrows show the main focus of the BAT information and technical support during the permitting procedure. The black arrows represent other relations needed for functioning of the integrated permitting regime such as the communication between industry permitting authorities during the permitting procedure, communication with Ministry and inspectorate. The interrupted arrows indicate the communication between stakeholders which is not mandatory and depend on needs for cooperation and technical aspects of setting permit conditions. The double-sided arrows show that relation with all stakeholders needs to be mutual.

### Work scope of BAT support body

In line with the report on Recommendations for organization and operation of the BAT/cleaner technologies centres (Subtask 2.2.2.2) the BAT support body shall fulfil the following main functions:

- Development and revision of national BAT guidance (if necessary);

- Information exchange on BAT including collecting information about implementation of BAT guidance and investigation of emerging BAT

Depending on the technical expertise of the integrated permitting authorities and the financial abilities of the BAT support body, there are additional activities which can be implemented:

- Assessment and determining BAT for concrete installations during the integrated permitting

- Developing of the whole integrated permit applications for the industry

- Assessment of the integrated permit application for the permitting authority.

These additional functions can be alternatively ensured by other expert institutions or consultants.

The proposed scope of functions covers all support functions which are needed for the smooth and efficient implementation of the integrated permitting regime. Ministries of Environmental Protection in each country shall set the scope of functions based on its aims within the environmental permitting reform, the legal provisions of the integrated permitting regulation and the available financial means for BAT support body’s operation.

Detailed description of the BAT support body functions

Development of BAT guidance

The function of BAT guidance development or adjustment the EU BAT guidance on the national level is the most complex and most technically and financially demanding activity. Development of BAT guidance is usually organized through Technical Working Groups (TWG) which consists of industrial and environmental specialists and representatives of environmental authorities. The draft BAT guidance is consulted with all relevant stakeholders from industry concerned and environmental authorities. The development of BAT guidance requires at least one full time coordinator and a team of specialists for the period of the BAT guidance development or update. Once the development of the BAT guidance is finished, the work of the TWG is terminated or the coordinator of the TWG continues to work as the focal point for collecting information about implementation of BAT guidance, development of emerging BAT and revision of BAT guidance.

Information exchange on BAT

This function covers search for information on development of emerging BAT, collecting information about implementation of BAT guidance, advise on interpretation of the BAT guidance and BAT guidance revisions. It is usually ensured by secretariat or coordinator of the TWG responsible for the relevant guidance.

The information dissemination on BAT guidance should be handled through an Internet portal. The BAT support body can also issue booklets and brochures with brief information about BAT guidance and procedure how to obtain and use them. In the preparatory stage of implementing integrated permitting, the BAT support body and/or representatives of the TWG organize seminars and workshops for the relevant permitting and inspection authorities and industry to introduce the concept of BAT, the scope of BAT guidance and BAT assessment procedure.

Technical support in assessment or determining BAT

The function of technical expert support in assessment or determining BAT is needed for the permitting authorities, which do not have permitting officers with sufficient technical knowledge and experience. The integrated permitting procedure requires to assess the adequacy of technical and environmental information in the integrated permit application and to determine the integrated permit conditions based on the BAT guidance. The technical support in assessing or determining BAT can be usually ensured by the relevant government agency (permitting or technical support) or by external experts (consultants or representatives of the relevant industrial sector institute). The technical expertise related to BAT determination can be also required in the appeal procedure on the issued integrated permit.

Technical support for BAT comparison and developing the integrated permit application

This function is primarily aimed at supporting the industrial plants which fall under the IPPC regulation and which need to prepare the application for the integrated permit. The application for integrated permit requires comparing the existing or planned technology and operating methods with the recommended BAT. Thus the relevant industrial research institutes, consulting companies or individuals which carry out environmental audits or other environmental consulting services can deliver the required assistance to the integrated permit applicants. In case this function would be carried out by the BAT support body, it should be organized on commercial basis, i.e. paid by the industry.

The legal basis of the BAT support body

The key functions or competencies of the BAT support body should be specified in the relevant legal instrument e.g. the Law on environmental permitting system in order to allow for funding from state budget. In case the BAT body will be operated within the framework of the Ministry of Environmental Protection (e.g. organization subordinated to the Ministry) the functions or competencies can be set as the functions of the Ministry in the relevant legal act.

## Institutional and organizational requirements

### Options for institutional setup

The BAT support body can be established in one of the following ways:

- Select and appoint suitable existing organization which expertise and experience allows to implement the above mentioned BAT support body functions (this can be for example an organization subordinated to the Ministry of Environmental Protection or industrial R&D institute which cover several industrial sectors regulated by integrated permits – e.g. Cleaner Production Centre)

- Create a new organization which shall hire relevant industry experts

- Establish a certification procedure for authorizing external consultants, consulting companies or research institutes in order to provide operations of the BAT support body function externally.

Based on the experience across the EU, the most common option of institutional arrangement for the BAT support body functions is the first of the above listed options. In many old and new EU members states the existing support organization of the Ministry of Environmental Protection was appointed to carry out the functions of BAT information exchange.

### Organization structure

The organization structure needs to correspond to the appointed functions and available financing. Also the structure has to be able to cooperate with relevant BAT information exchange stakeholders.

The following structure is proposed to fulfil all the BAT support body functions. The BAT support body should consist of:

- BAT guidance development unit

- Unit for information exchange on BAT

- Technical expert support unit.

The unit responsible for national BAT guidance development can work as similar structure of the European IPPC Bureau, i.e. to employ coordinators of technical working groups (TWG) for developing and revising national BAT guidance and ensure the conditions for the TWGs work. The coordinators will be employed for the period of the BAT guidance development (about 2 years).

The unit responsible for the information exchange on BAT shall carry out the following activities: collecting information about implementation of BAT guidance, development of emerging BAT and dissemination of information about BAT guidance to relevant stakeholders. This unit will work also as the secretariat of the BAT body and provide information on the BAT body activities through Internet.

The unit of technical expert support on BAT assessment and integrated permit application will provide support both to the permitting authorities and to the industry. Nevertheless, the operation procedure for BAT assessment and integrated application development shall set the priority in providing support to permitting authorities and it shall resolve the potential conflict of interest in case the BAT body would prepare the integrated permit application and it would be requested to provide technical assessment of the same application for the permitting authority during the integrated permitting procedure.

Scheme 6.2. — BAT support body organisational scheme

### Human resources

Concerning the number of staff, it is recommended to ensure effective management by 4 management positions (1 director of the BAT support body and 3 managers — one for each unit). In the unit responsible for the development of BAT guidance the staff — TWGs coordinators — should be hired in accordance with the plan for developing national BAT guidance and availability of experts for work in TWGs. The coordinators shall have long term experience with working in the industrial sector for which they will be coordinating the BAT guidance development. TWG members shall have an advisory function and their input to the work of TWG should be funded from organizations which employ them, unless there is state budget available.

The unit providing information exchange on BAT shall employ 3 – 5 staff including IT specialist, coordinator and technical assistants.

The technical expert support unit shall hire technical experts for internal and/or external cooperation on BAT assessment and integrated permit application development and assessment. The number of the staff in this unit shall ensure sufficient support of the permitting authorities in issuing the integrated permit for the existing and new industrial plants in accordance with the transitory plan for bringing the existing industry to the integrated permit regulatory system. The technical support staff shall have sufficient knowledge and experience with operating technologies in the relevant industry, environmental assessment and legislation. The technical support for the industry can be ensured alternatively through external cooperation with relevant/authorizes experts.

Based on the experience with operating organizations ensuring the BAT information exchange and related technical support, it is recommended that the BAT support body shall employ about 50 experts for the transitory period of integrated environmental permitting system implementation.

Qualification of a TWG coordinator

The coordinator function is crucial for successful compilation of the BAT guidance, thus the coordinator needs to have the following qualification:

- Technical education (University degree)

- Minimum 8 years of experience from relevant industry sector (ideally as technical or environmental manager)

- Coordination and negotiation skills

- Computer literacy

- Knowledge of environmental legislation

- Good communication skills

- Knowledge of the environmental legislation related to the sector

- Good level of English

### Management and financial requirements

The management of the BAT support body shall agree with relevant Ministry the priorities and time schedules for providing the services e.g. time available for developing BAT guidance, assessment of an integrated permit application or BAT, assessment for the integrated permitting authority. The schedule for the BAT guidance development observance is very crucial, because the permit application for existing installations cannot be completed and checked without the guidance.

All units of the BAT support body shall work on the team cooperation basis. Thus the organization structure needs to be sufficiently flexible to allow cooperation across all units. The BAT guidance unit shall work on project basis.

In order to provide quality technical support in effective way the manuals and guidance for the regular activities should be developed. Manuals and guidance shall cover the following activities:

- Development and revision of national BAT guidance including compulsory minimum content of the BAT guidance

- Collecting information about implementation of BAT guidance and development of emerging BAT (e.g. criteria for placing a new technology in the BAT guidance)

- Assessing and determining BAT for concrete installation/plant during the integrated permitting procedure

- Developing of the integrated permit application for the industry

- Assessment of the integrated permit application for the permitting authority.

Financing options

The financial options depend first of all of the legal status of the BAT support body. In case the BAT support body will be established within the organization subordinated to some Ministry, it gives possibility to combine the state budget, private and grant funding.

Based on the European experience it is advisable to ensure funding from state budget for developing national BAT guidance, information exchange on BAT and providing technical expertise for supporting the permitting authorities (in first few years after introduction of the integrated permitting regime).

The Ministry of Environmental Protection and subsequently the established BAT support body can also apply for grants or projects funded from international organizations such as the European Commission, UNEP and World Bank in order to develop the national BAT guidance, pilot projects and related training. As similar projects for implementation of IPPC have been carried out in other countries of EECCA region, it is possible to consider preparation of common application with one or more EECCA countries for international funding for developing BAT guidance in Russian language.

An alternative or complementary option for funding is involvement of the industry, namely the industry associations, since it is within the interest of the industry to influence which technology, operation and management methods will be considered as BAT and which not. In some EU countries (e.g. Croatia), the state budget is not available for activities of BAT support body and therefore the industry itself – through the Croatian Chamber of Commerce is to organize the system of information exchange on BAT as well as selecting national sectoral experts for the cooperation with the European TWG for BAT reference documents revisions.

The function of providing technical expert support to industry should be financed by the industry as a consultancy service. The income from providing this service can be used for improving the other services of the BAT body.

In case the BAT body is responsible for the assessment of the integrated permit applications for the permitting authority, the BAT body will become participant of the permitting procedure and need to have a special financial budget for performing this activity.

### Technical requirements

The BAT support body will need the following equipment to perform their functions:

- Office equipment (computers, printers, copy machine, phones, scanner)

- Access to internet and meeting rooms

- BAT information service with partly public access

- Electronic and physical archive for documents

- Car for site visits

If the BAT support body is hosted by some existing organization, then there is a possibility to share and utilize some of the existing equipment.

Concerning the BAT IS – it is proposed to establish a specialized web portal which would contain:

- The finished BAT guidance

- Database/archive of the documents utilized for BAT guidance preparation

- Electronic forum of the members from TWGs, and

- Other information such as guide on how to use BAT guidance, etc.

The web portal should allow possibility for public questions and answers and/or FAQs.

The electronic forum should allow access to various stakeholders of integrated permitting regime with various access rights. The different levels of restricted access can be arranged through authorization names/passwords. This would be the most efficient way of controlling the documents flow on one central system.

## Phases of developing and operating BAT support body

Preparatory phase

When the integrated permitting system is approved by the law is it necessary to establish the BAT body in order to prepare itself for the support functions. The following responsibilities and tasks are proposed for practical preparation of the BAT support body:

- Set up appropriate financial and staff structure

- Hire and train personnel

- Establish manuals and guidance for performing the main functions (e.g. manual and template for BAT guidance)

- Start preparation of BAT guidance for the priority sectors in line with the phase out schedule for bringing individual sectors under the integrated regime

- Develop website for publication of BAT guidance and possibly also as a platform of information exchange on BAT in cooperation with the Ministry of Environmental Protection

- Establish communication with the permitting authorities and other stakeholders based on the scope of functions.

This phase should last 1 year which depends on the available budget and readiness of the relevant experts to start contributing the preparation of the BAT guidance.

Transitory implementation phase

In this phase the main emphasis will be on:

- Preparation of BAT guidance according to agreed schedule,

- Developing information exchange on BAT which include active information support of integrated permitting authorities, and

- Supporting the permitting authorities and/or industry in the BAT assessment, assessment the integrated permit application and/or preparing integrated permit applications for the industry;

This phase can last 4 - 8 years depending on the number of required BAT guidance and number of existing installations requiring the integrated permit.

Normal implementation phase

After development of the first edition of BAT guidance the BAT shall refocus its activities and focus on maintaining the established system. The main activities during this phase include:

- Updating and publishing of BAT guidance, and

- Maintain information exchange on BAT which includes active information support of integrated permitting authorities.

Depending on the agreed scope of functions the following can be also carried out by the BAT body:

- Assessment BAT for concrete installations during the integrated permitting

- Developing of the whole integrated permit applications for the industry

- Assessment of the integrated permit application for the permitting authority.

Nevertheless, it is likely, that during the transitory phase, the permitting officers will gain experience on assessing the integrated permit applications, so that this support will not be needed so much. The exception is the chemical industry or other complex installations and their modernizations.

## Conclusions and recommendations

The objective of BAT support body is to facilitate information exchange on BAT and ensure information and technical support in relation to integrated permitting regulation.

The BAT support body shall fulfil the following main functions:

- Development and revision of national BAT guidance; in case the national resources allow to do so

- Information exchange on BAT including collecting information about implementation of BAT guidance and investigation of emerging BAT depending on the national resources.

In relation to the size of the national economy in the partner countries, it is recommended that the bigger economies with thousands of installations under integrated permitting regime should establish such a BAT support body which will carry out both above mentioned functions.

Countries with hundreds of installations under integrated permitting regime will not have resources for robust BAT support body, therefore it is recommended to establish BAT information exchange network with external experts who can share their experience with using EU BREFs. And in these smaller countries it is not envisaged to develop national BAT guidance, unless some representatives of bigger industrial sectors will take an initiative and organize the development.

Depending on the technical expertise of the integrated permitting authorities and the financial setup of the BAT support body; there are additional activities which can be implemented by the BAT support body:

- Assessment and determining BAT for concrete installations during the integrated permitting

- Developing of the whole integrated permit applications for the industry

- Assessment of the integrated permit application for the permitting authority.

The key functions or competencies of the BAT support body should be specified in the relevant legal instrument, e.g. the law on environmental permitting system in order to allow for funding from state budget.

The BAT support body is recommended to be established by selecting and appointing suitable existing organization which expertise and experience allows to build on the above mentioned BAT body functions.

The organization structure of the BAT body is proposed to contain three units:

- BAT guidance development unit

- Unit for information exchange on BAT

- Technical expert support unit.

All units of the BAT body shall work on the team cooperation basis. Thus the organization structure needs to be sufficiently flexible to allow cooperation across all units. The BAT guidance unit shall work on project basis. It is crucial that in the preparatory phase the activities of BAT body are harmonized with the implementation plan and schedule for bringing the existing industry into the integrated permitting regime.

The funding options depend first of all on the legal status of the BAT body. In case the BAT body will be established within the organization subordinated to some Ministry it gives possibility to combine the state budget, private and grant funding.

### Where to place the BAT body?

For each project country it has to be decided:

- Will the BAT body be established as a new institution or in some existing one?

- In case of existing institution, which one can be proposed as suitable one?

- Is it necessary to hire new people or to reorganize some existing institution?

The BAT body activities should be well coordinated with national TWGs and relevant international institutions, first of all the European IPPC Bureau in Seville and its Information Exchange Forum.

### Scope of BAT support body activities

To define the Scope of BAT support body activities it is necessary to answer:

- Which of the activities proposed in chapter 6.1.1 are feasible to be carried out by the proposed BAT support body in each country?

- Opportunity of financial needs for the BAT support body establishment or reorganization of existing institution

- Possible cooperation between national BAT support body within the region or with EIPPCB and other EU BAT support bodies?

# recommendations for the GBR PERMITTING AUTHORITY

The recommendations for the GBR permitting authority are elaborated for the project countries’ Ministries responsible for environmental protection. They are elaborated under Subtask 2.1.3.6 of the component 2 of the Air-Q-Gov project. They are based on the recommendations for GBR permitting system (project Subtask 2.1.2.5).

The recommendations are derived from experience with implementation of GBR regulatory systems in EU.

It is assumed that functions and responsibilities of the GBR permitting authority will cover only permitting under the GBR permitting regime. The enforcement of GBR permits will be carried out by specialized enforcement authority (e.g. environmental inspectorate), and GBR development will be arranged by specialized external experts or institutions as described in the report under Subtask 2.1.2.5.

## The role of GBR permitting authority in environmental regulatory system

The GBR permitting regime should complement both the integrated permitting regime and the existing single media based permitting system. The aim of GBR permitting system is to cover industrial and agricultural sectors with significant number of plants and operators in order to decrease the administrative burden both for the plants and for the authorities.

So the GBR permitting authority (further - GBR authority) can be the same as the integrated permitting authority or modified existing permitting authorities.

The existing regime with separate media based permits will retain the same functions for the medium polluters who will not be regulated by GBR. Since groups of large and law polluters will be regulated by the other regimes, and some medium polluter will fall in GBR permitting system, the load of the existing permitting work shall significantly decrease.

Main function of GBR authority is to ensure smooth and effective permitting procedure. The following subchapter describes relations of the GBR authority with stakeholders and tasks of the authority.

### Relation of GBR authority with stakeholders of the GBR permitting system

In order to set suitable and relevant functions and tasks of the BAT support body it is important to consider stakeholders’ interests and relations in the integrated permitting regime. The following table contains overview of the relevant stakeholders and their roles or interests in relation to the permitting regime.

Table 1 – Principal stakeholders and their roles in the GBR permitting regime

| Stakeholder | Role or interest |
| --- | --- |
| Ministry of Environmental Protection | - Preparation and official interpretation of the of legislation - Establishment and control of institutional structure of the GBR permitting regime - Methodological support and technical guidance - Dissemination of information related to the regulatory system - Appeal body (depending on the national administrative system) |
| GBR permitting authorities as part of the authorities who deal with single media | - Permitting procedure administration - Data collation and reporting |
| In case of GBR covering various environmental media – Relevant Administrative Authorities (RAA) - e.g. environmental and health authorities, local administration bodies) | - Consideration of the application for GBR (integrated) permit - Issuing statements and proposing permit conditions |
| Inspection authority | - Compliance monitoring and enforcement (inspection) - Possibly consultations within the permitting procedure |
| Operators of industrial and agricultural companies under GBR regime + investors | - To obtain the permits in minimum time and with minimum administrative cost - Fear of prosecution and fines - Keen to protect public image and maintain competitiveness |
| Professional and technical institutions, who will be appointed to develop GBR | - Representation of industry/agriculture sectors’ views - Provision of technical support and GBR |
| NGOs and public | - Representation of public interest - Highlighting environmental issues - Exerting pressure on government and industry |

The following scheme presents relations between GBR authority and stakeholders in the GBR permitting regime.

Scheme 7.1 — Relations between GBR authority and stakeholders

The red arrows show the main relations during the permitting procedure. These relations include submitting the application for permit to GBR authority, communication about the application with operator, relevant administrative authorities, and issuing of the permit. The black arrows represent other relations needed for functioning of the GBR permitting regime such as preparation of GBR and related consultations, communication with Ministry and inspectorate. The interrupted arrow indicates the communication between GBR authority and inspectorate during the permitting procedure, which may not be mandatory and can depend on the technical aspects of setting permit conditions. The double-sided arrows show that relation with all stakeholders needs to be mutual.

### Work scope of GBR authority

When the GBR permitting authority is formally appointed, it should prepare itself for the permitting function. The following responsibilities and tasks are proposed for practical preparation of the permitting authority for implementation of the GBR permitting procedure:

- Set up appropriate staff structure of the GBR authority

- Train personnel

- Establish GBR permitting regime and procedure within the organizational structure and participate in consultation about the relevant legislation

- Establish administrative mechanism for consultations with relevant administrative authorities during the permitting procedure

- Establish system for permit review and variation

Implementation phase

The permitting authority will be responsible for:

- Administration of the GBR permitting procedure

- Conducting regular, planned permit review and variation of permit conditions

- Maintain and operate a system for publication and storage of documents from permitting procedure

- Cooperation with enforcing authority (if separate)

- Collect a fee for issuing an GBR permit (if any).

GBR permitting procedure includes the following steps:

- Communication and consultation with applicants for GBR permit including site visits

- Coordination of requirements of related administration authorities (whose permits are integrated in GBR permit)

- Meetings with related administration authorities if necessary

- Maintain database of installations under GBR regime and database of permitting procedure documents

- Cooperation with the Ministry of Environmental Protection (e.g. on legal interpretation of the legislation, GBR, appeals…)

- Cooperation with inspectors

- Collection of permit fees if any.

Some steps of this permitting procedure are identical or similar to the existing permitting procedures, but steps no. 2 and 6 are new additional steps which are required for the GBR procedure.

Step no. 2: Coordination of relevant administrative authorities (RAA)

In case GBR are developed for some groups of installation which are under the integrated permitting regime or if GBR cover more than one environmental media, it is necessary to replace some exiting permits by the new GBR permit. In such a case it will be necessary to consult the issuing of the GBR permit with the relevant administrative authorities. These consultations require the coordination of relevant administrative authorities who are used to carry out their own procedure and issue permits or approval, but under the GBR regime, their status is changed. Depending on the scope of integration, RAA can include water resources, ambient air, waste management, noise/health, nature protection, agriculture, and energy authorities. In order to ensure effective coordination, the instructions for the RAA and administrative steps have to be clearly defined and agreed. (They can be very similar to those developed for the integrated permitting regime.)

The main part of these instructions is defining which part of application for permit needs the RAA’s review and consideration and what shall be the content of the RAA’ statement (e.g. proposal or permit conditions with justification). It is important to note, that RAA shall be involved in consultations about the draft GBR, so that their views and requirements can be already included in the final GBR.

Step no. 6: Cooperation with inspectors

In case the permit writers have little technical knowledge and experience in order to consider to the correctness of proposed permit conditions in the applications and compliance with GBR, it may be useful to required technical support in the form of application review by technical experts from relevant environmental inspectors. The result of the review can be comments on proposed permit conditions which will be in the form of recommendations to the permit writer.

## Organisational and human requirements

### Organisational requirements

The management and organization of the GBR authority will depend on whether GBR will cover more than one environmental medium and if the GBR authority will be set up along with integrated permitting authority. This will infer from the current distribution of permitting functions and shall be stipulated by the law on environmental permitting. Generally there are the following possibilities where to place the GBR permitting function:

- Ministry of Environmental Protection at central level

- Ministry of Environmental Protection at regional level

- Environmental inspectorate

- Regional authorities

- Regional and county authorities.

Placing the GBR permitting in the central office of the Ministry of Environmental Protection is recommendable for small countries where the current permitting is ensured by the Ministry’s central office and where the number of installations falling under the GBR permitting regime will be up to 500.

Placing the GBR permitting in regional offices of the Ministry of Environmental Protection is recommended for bigger countries where the regional offices ensure currently environmental permitting and where the number of installations falling under the GBR permitting regime will be more than 200 per region.

Placing the GBR permitting in the Environmental inspectorate is recommendable for countries where either the current permitting is ensured by the inspectorate or where environmental inspectors are the only technically capable resources to cope with GBR permitting.

Placing the GBR permitting in regional authorities is recommended for bigger countries where the regional authorities already have some experience with permitting and where the number of installations falling under the GBR permitting regime will be more than 200 per region.

Placing the GBR permitting in regional and county authorities is recommended for large countries where the regions and counties ensure currently some environmental permitting/approvals and where the number of installations falling under the GBR permitting regime will be over 400 per region.

Based on European experience the combination of GBR permitting by regional and county authorities is used in England and in the Netherlands. It is usually specified which category of industry/agriculture is administered in which level. Typical sector for GBR are farms which can be permitted on county level since there is many of them and they are relatively simple installation for administration of the GBR permitting procedure.

There is no need for special organizational set up. The organization can be the same for any decentralized level (i.e. regional offices of the Ministry of Environmental Protection, regional authorities, counties or inspectorate). Based on experience in EU countries there is a need of approximately one permitting officer per each 50 - 80 installations. Thus the GBR authority on regional or county level shall be part of either the existing permitting departments or part of the integrated permitting department. The GBR permitting team shall include permitting officers and a coordinator/manager. There should be established cooperation with media based departments which are responsible for air protection, water and waste permits in case of need for consultations.

### Human resources

The administration of GBR permitting procedure requires staff with good knowledge of relevant legislation and GBR, and administrative knowledge. The experience with operating GBR authority in EU countries shows that one permit writer can administer approximately 50 – 80 installations. To administer an installation means to issue the first GBR permit and afterwards to administer changes in issued permits and review of permits. In case the number of plants which will fall under the GBR regime will be significant (i.e. more than 25% of all plants permitted by the permitting authority), it may be useful to set up specialized unit or department. In such a case it is recommended that the GBR authority has several permitting officers and one manager or coordinator.

Permitting officers will primarily ensure the permitting procedure. It would be an advantage if they are specialized on sectors which are covered by GBR.

The manager’s role will be important in the preparatory stage since he/she shall be responsible for establishing the cooperation with relevant administrative authorities consulted during the permitting procedure (other relevant authorities or relevant department within the administrative body) and handling difficult cases of applications for GBR permits. In the implementation stage he/she will be responsible for monitoring of the permitting procedures and checking the quality of issued permits.

Qualification of a GBR permitting officer

The permitting officer needs to have the following qualification:

- Technical education (University degree)

- Minimum 3 years of experience from relevant industry/agriculture sector and/or experience with environmental permitting or enforcement

- Computer literacy

- Knowledge of environmental legislation

- Good communication skills.

Recommended areas for trainings for the permitting officers:

- Administrative procedures needed for processing the permitting procedure

- GBR and their interpretation

- Environmental legislation (relevant aspects related to GBR permits)

- Environmental performance of relevant sectors and related GBR

- Communication skills.

It is also recommended for the permitting officers to participate in any project focused on simulation of GBR permitting procedure as well as on site visits to plants within their region.

## Phases of developing and operating GBR authority

The implementation of GBR permitting regime requires carry out preparatory tasks, as it is necessary to transform and/or develop institutional, technical and administrative capacities. The following tasks shall be performed in the first phase of preparation for GBR permitting by the GBR authority:

- Establishing and developing the institutional structure for GBR permitting and ensure human and financial means

- Surveying and identifying installations under GBR permitting regime

- Establishing a reporting and database system.

The preparatory phase’s tasks shall be carried out under the coordination of the central implementation body (i.e. Ministry of Environmental Protection). The identification of installations falling under GBR permitting regime is very important as it will be the basis for planning the next phase. This phase can last 1 – 2 years depending on readiness of administrative bodies. The GBR needs to be developed during this phase by appointed experts’ teams. The development of GBR needs to be coordinated by the Ministry of Environmental Protection.

The next phase shall be carried out in accordance with the realistic implementation plan with consideration of the human, technical and financial capacities available in GBR authorities and installations. The main task of GBR authority in the second phase is the administration of GBR permitting procedure, including reviewing permit applications, consultations and issuing permits. This phase can last 4 - 8 years depending on the number of installations requiring the GBR permit, number of permitting officers and administrative demands of the permitting procedure. This phase should not interfere with the implementation of the integrated permitting regime, unless the permitting authorities have sufficient number of permitting officers.

The next phase comes after issuing of GBR permits for all installations under the GBR regime. In this phase the tasks of the GBR authority include:

- Regular permit reviews and updates based on the legal requirements (period for permit revision or updates of related legislation)

- Consideration of changes announced by operators and related procedures for change of permits

- Reporting on the implementation to the central implementing body and cooperation with related authorities (e.g. inspectors).

This phase represents the “normal” operation of GBR authority. Experience of EU Member States with operating GBR permitting regime shows that the following frequency of announced changes by operators is the usual one.

Simple operations (e.g. farms and landfills) announce one change every 2 – 3 years. More complex operations (e.g. energy production) have at least one change per year. Approximately 30% of all announced changes are not significant, so they do not require any change of the permit or only an administrative change. The remaining 70% require change of some permit conditions and thus the permitting procedure has to be carried out.

## Recommendations for the project countries

Taking that the GBR permitting regime has to simplify the procedure of integrated environmental permitting, it is reasonable not to multiply the bureaucratic structures. The regime of “centralized” permits granting has to work only for enterprises with the biggest polluting potential. In all project countries they are in list of IPPC enterprises.

For enterprises with the moderate polluting potential the GBR permits have to be granted at the nearest administrative level: region, county, municipality. In Russian Federation there is some specific due the constitutional claims on the sharing of the state power between the Federation and its Subjects. For other Project countries the concept of the nearest to enterprise administrative level will work without any restrictions.

### Where to place the GBR authority

So there is no need to establish special GBR authority at the country and regional level. The existing (or projected) IPPC authorities have to fulfil the GBR permitting work as well.

At the level of counties or municipalities the work of GBR permitting can be done by the bodies responsible for environmental issues. In some project countries the local stuff has an experience in permits granting and EIA review, but, in general, there is a need in special training.

The extra financing will be small and partly can be covered from the body budget and partly from the grants in the framework of EuropeAid projects.

## Conclusions and recommendations

The GBR permitting authority responsible for implementation of the GBR permitting regime can be established within the existing administrative authority responsible for issuing air, water, or waste permits. It is possible to add the GBR permitting function to the existing permitting department. The existing permitting officers will have less work with media based permits, so the staff with experience from GBR sectors can be appointed to carry out GBR permitting function. Alternatively the GBR authority can be established within the integrated permitting authority in the case, where GBR cover all environmental media and require similar consultation procedure like the integrated permitting.

The GBR authority has to be established one year before the actual start of issuing GBR permits in order to ensure the preparatory tasks. The main preparatory tasks are cooperation on establishing the inventory of installations and establishing administrative mechanism for consultations with authorities which are issuing media based permits and in the GBR regime their competence will be transformed to consultation on the draft GBR permit.

In the implementation phase the GBR authority will be responsible mainly for GBR permitting procedure and subsequent permit reviews and changes. This phase should not interfere with the implementation of the integrated permitting regime, unless the permitting authorities have sufficient number of permitting officers.

In any case the workload of the GBR permitting authority during issuing the first GBR permits can be handled only with realistic phase in schedule, flexible administrative procedure and good cooperation with relevant administrative authorities.

Annex 1

Правила выдачи комплексных природоохранных разрешений согласно Указу Президента Республики Беларусь

В целях оптимизации порядка осуществления административных процедур в сфере природопользования:

1. Установить, что:

1.1. Юридические лица и индивидуальные предприниматели, осуществляющие деятельность (планирующие осуществлять деятельность), связанную с эксплуатацией объектов, оказывающих комплексное воздействие на окружающую среду, вправе с 1 января 2012 г. получать комплексные природоохранные разрешения, а с 1 января 2016 г. осуществляют указанную деятельность только при наличии комплексных природоохранных разрешений;

1.2. Комплексное природоохранное разрешение является единым разрешительным документом, удостоверяющим право на выбросы загрязняющих веществ в атмосферный воздух, специальное водопользование, хранение и захоронение отходов производства с учетом внедрения наилучших доступных технических методов и устанавливающим нормативы допустимого воздействия на окружающую среду, условия осуществления хозяйственной и иной деятельности в части использования природных ресурсов и (или) оказания воздействия на окружающую среду, и заменяет собой разрешения на выбросы загрязняющих веществ в атмосферный воздух, специальное водопользование, хранение и захоронение отходов производства;

1.3. Комплексные природоохранные разрешения выдаются бесплатно на срок от 5 до 10 лет территориальными органами Министерства природных ресурсов и охраны окружающей среды в порядке, определяемом Советом Министров Республики Беларусь;

1.4. С даты получения комплексного природоохранного разрешения прекращают свое действие ранее выданные юридическим лицам и индивидуальным предпринимателям разрешения на выбросы загрязняющих веществ в атмосферный воздух, специальное водопользование, хранение и захоронение отходов производства;

1.5. Министерство природных ресурсов и охраны окружающей среды и его территориальные органы:

осуществляют контроль за соблюдением нормативов допустимого воздействия на окружающую среду и условий осуществления природопользования, установленных в комплексных природоохранных разрешениях;

вправе в установленном порядке приостанавливать полностью или частично до устранения выявленного нарушения работу отдельных производств, цехов и (или) объектов, если их эксплуатация осуществляется с нарушением нормативов допустимого воздействия на окружающую среду и условий осуществления природопользования, установленных в комплексных природоохранных разрешениях.

Порядок выдачи комплексных природоохранных разрешений согласно постановлению Совета Министров

1. Настоящим Положением устанавливается порядок выдачи комплексных природоохранных разрешений, внесения в них изменений и (или) дополнений, продления срока, прекращения их действия и выдачи дубликата.

2. Настоящее Положение распространяется на природопользователей – юридические лица и индивидуальных предпринимателей, осуществляющих деятельность (планирующих осуществлять деятельность), связанную с эксплуатацией объектов, оказывающих комплексное воздействие на окружающую среду, согласно приложению к Указу Президента Республики Беларусь от 17 ноября 2011 г. № 528 «О комплексных природоохранных разрешениях» (Национальный реестр правовых актов Республики Беларусь, 2011 г., № 130, 1/13083) (далее – природопользователи).

3. Природопользователи, осуществляющие ввод объектов, указанных в приложении к Указу Президента Республики Беларусь от 17 ноября 2011 г. № 528 (далее – объекты), в эксплуатацию, получают комплексное природоохранное разрешение со дня ввода объекта в эксплуатацию.

4. Выдача комплексных природоохранных разрешений, внесение в них изменений и (или) дополнений, продление срока и прекращение их действия, выдача дубликатов комплексных природоохранных разрешений осуществляются территориальными органами Министерства природных ресурсов и охраны окружающей среды (далее – орган выдачи разрешений) по месту государственной регистрации природопользователя. Комплексное природоохранное разрешение выдается на срок, указанный природопользователем в заявлении о выдаче комплексного природоохранного разрешения (далее – заявление), от 5 до 10 лет.

5. Административное решение, принятое органом выдачи разрешений в соответствии с настоящим Положением, может быть обжаловано в порядке, предусмотренном в статьях 30–34 Закона Республики Беларусь от 28 октября 2008 года «Об основах административных процедур» (Национальный реестр правовых актов Республики Беларусь, 2008 г., № 264, 2/1530).

Порядок принятия и рассмотрения заявлений

6. Для получения комплексного природоохранного разрешения природопользователь либо лицо, им уполномоченное, подает в орган выдачи разрешений заявление на бумажном и (или) электронном носителях и иные документы, указанные в пункте 53 перечня административных процедур, осуществляемых Министерством природных ресурсов и охраны окружающей среды и его территориальными органами в отношении юридических лиц и индивидуальных предпринимателей, утвержденного постановлением Совета Министров Республики Беларусь от 22 октября 2007 г. № 1379 (Национальный реестр правовых актов Республики Беларусь, 2007 г., № 261, 5/26021; 2009 г., № 118, 5/29744) (далее – перечень).

Форма и порядок заполнения заявления устанавливаются Министерством природных ресурсов и охраны окружающей среды.

7. Орган выдачи разрешений при необходимости получения дополнительных документов и (или) сведений запрашивает их у другого государственного органа, иной организации, к компетенции которых относится их представление, в порядке, установленном в статье 22 Закона Республики Беларусь «Об основах административных процедур».

8. Решение об отказе в принятии заявления принимается в порядке и на основаниях, предусмотренных в статье 17 Закона Республики Беларусь «Об основах административных процедур».

9. Орган выдачи разрешений обязан:

в течение 5 рабочих дней со дня подачи природопользователем заявления и иных документов, указанных в пункте 53 перечня, информировать его о принятии (непринятии) к рассмотрению представленных документов;

разместить в течение 10 рабочих дней со дня подачи природопользователем заявления и иных документов, указанных в пункте 53 перечня, общественное уведомление природопользователя на интернет-сайтах (страницах) территориальных органов Министерства природных ресурсов и охраны окружающей среды по месту осуществления природопользователем хозяйственной и иной деятельности в случае принятия к рассмотрению представленных документов;

рассмотреть предложения общественности, касающиеся заявления на получение комплексного природоохранного разрешения.

10. Природопользователь обязан:

в течение 5 рабочих дней со дня уведомления его органом выдачи разрешений о принятии заявления к рассмотрению представить для ознакомления общественности общественное уведомление путем его размещения в печатных и электронных средствах массовой информации по месту осуществления природопользователем хозяйственной и иной деятельности;

в течение 40 календарных дней со дня уведомления его органом выдачи разрешений о принятии заявления к рассмотрению направить материалы о рассмотрении поступивших обращений общественности в орган выдачи разрешений.

Порядок выдачи комплексных природоохранных разрешений

11. Орган выдачи комплексных природоохранных разрешений в срок, установленный в пункте 53 перечня, рассматривает заявление и иные документы, указанные в пункте 53 перечня, и принимает решение о выдаче комплексного природоохранного разрешения или об отказе в его выдаче.

12. При принятии решения о выдаче комплексного природоохранного разрешения учитываются:

информирование общественности в порядке, установленном в пункте 10 настоящего Положения;

соответствие данных, представленных природопользователем, требованиям нормативных правовых актов, в том числе технических нормативных правовых актов, в области охраны окружающей среды, включая требования в части установления нормативов допустимого воздействия на окружающую среду, целевым показателям, определенным планами и программами по развитию видов экономической деятельности, территории, включая территориальные комплексные схемы по охране окружающей среды и проекты водоохранных зон на период действия комплексного природоохранного разрешения, а также программами и мероприятиями по охране окружающей среды;

соответствие планируемой деятельности наилучшим доступным техническим методам и условиям осуществления природопользования с учетом таких методов;

наличие у природопользователя специальных разрешений (лицензий), если они предусмотрены законодательными актами.

13. Решения об отказе заявителю в выдаче комплексного природоохранного разрешения принимаются в порядке и на основаниях, предусмотренных в статьях 25 и 26 Закона Республики Беларусь «Об основах административных процедур».

14. Уведомление о решении, принятом органом выдачи разрешений, направляется природопользователю в порядке, предусмотренном в статье 27 Закона Республики Беларусь «Об основах административных процедур».

15. Срок действия комплексного природоохранного разрешения определяется при:

вводе в эксплуатацию объектов – со дня ввода объекта в эксплуатацию;

эксплуатации объектов – с первого числа месяца, следующего за месяцем, в котором принято решение о выдаче комплексного природоохранного разрешения.

16. Комплексное природоохранное разрешение выдается:

руководителю юридического лица – при предъявлении документа, подтверждающего его служебное положение, а также документа, удостоверяющего его личность;

индивидуальному предпринимателю – при предъявлении документа, удостоверяющего его личность;

уполномоченному представителю лица, указанного в абзацах втором и третьем настоящего пункта, – при предъявлении доверенности, оформленной в порядке, установленном законодательством, а также документа, удостоверяющего его личность.

17. В случае утраты комплексного природоохранного разрешения для выдачи дубликата природопользователь обязан обратиться в орган выдачи разрешений с заявлением в произвольной форме.

Дубликат комплексного природоохранного разрешения выдается в течение 5 рабочих дней со дня обращения природопользователя. При этом действие комплексного природоохранного разрешения не приостанавливается.

18. Форма комплексного природоохранного разрешения устанавливается Министерством природных ресурсов и охраны окружающей среды.

Комплексное природоохранное разрешение оформляется в двух экземплярах: один выдается природопользователю либо уполномоченному лицу, второй хранится в органе выдачи разрешений.

19. В случае нахождения объектов природопользователя на территории различных административно-территориальных единиц орган выдачи разрешений направляет копию выданного природопользователю комплексного природоохранного разрешения в территориальный орган Министерства природных ресурсов и охраны окружающей среды по месту осуществления деятельности природопользователя.

20. Комплексные природоохранные разрешения регистрируются органом выдачи разрешений в журнале учета комплексных природоохранных разрешений.

Регистрационный номер комплексного природоохранного разрешения сохраняется за природопользователем в процессе всего периода осуществления им деятельности, связанной с воздействием на окружающую среду.

21. Информация о выданных комплексных природоохранных разрешениях предоставляется органом выдачи разрешений на основании запроса государственных органов и иных организаций в сроки и в порядке, установленные законодательством.

22. Орган выдачи разрешений в течение 10 дней со дня отправления природопользователю уведомления о решении, принятом органом выдачи разрешений, размещает на интернет-сайте территориального органа Министерства природных ресурсов и охраны окружающей среды по месту осуществления природопользователем хозяйственной и иной деятельности информацию о получении природопользователем комплексного природоохранного разрешения.

23. Заявление и иные документы, предусмотренные в пункте 53 перечня, представленные природопользователем для получения комплексного природоохранного разрешения, продления срока его действия, внесения в него изменений и (или) дополнений, хранятся в органе выдачи разрешений.

Продление срока действия комплексного природоохранного разрешения

24. Действие комплексного природоохранного разрешения продлевается органом выдачи разрешений на срок от 5 до 10 лет.

25. Для продления срока действия комплексного природоохранного разрешения природопользователь либо лицо, им уполномоченное, обязаны не позднее чем за два месяца до истечения срока действия комплексного природоохранного разрешения подать в орган выдачи разрешений заявление по форме, устанавливаемой Министерством природных ресурсов и охраны окружающей среды, и иные документы, предусмотренные в пункте 53 перечня.

26. Решение об отказе в принятии заявления принимается в порядке и на основаниях, предусмотренных в статье 17 Закона Республики Беларусь «Об основах административных процедур».

27. Орган выдачи разрешений принимает заявление и документы, представленные природопользователем для продления срока действия комплексного природоохранного разрешения, рассматривает их и принимает решение о продлении срока действия комплексного природоохранного разрешения или об отказе в продлении срока его действия в порядке и на основаниях, предусмотренных в статьях 25 и 26 Закона Республики Беларусь «Об основах административных процедур», в срок, предусмотренный в пункте 53 перечня.

Внесение в комплексное природоохранное разрешение изменений и (или) дополнений, прекращение его действия

28. Природопользователь либо лицо, им уполномоченное, обязаны в трехмесячный срок обратиться в орган выдачи разрешений для внесения в комплексное природоохранное разрешение изменений и (или) дополнений в случаях изменения:

наименования, местонахождения природопользователя и (или) его обособленных подразделений (филиалов) и (или) объектов;

нормативов допустимого воздействия на окружающую среду и условий осуществления природопользования, указанных в комплексном природоохранном разрешении.

29. При внесении в комплексное природоохранное разрешение изменений и (или) дополнений природопользователь представляет в орган выдачи разрешений заявление по форме, устанавливаемой Министерством природных ресурсов и охраны окружающей среды, и иные документы, предусмотренные в пункте 53 перечня. Оригинал разрешения представляется в орган выдачи разрешений в течение трех рабочих дней после получения уведомления о положительном решении о внесении изменений и (или) дополнений в комплексное природоохранное разрешение, направленного в порядке, предусмотренном в статье 27 Закона Республики Беларусь «Об основах административных процедур».

30. Решение об отказе в принятии заявления принимается в порядке и на основаниях, предусмотренных в статье 17 Закона Республики Беларусь «Об основах административных процедур».

31. Орган выдачи разрешений принимает документы, представленные для внесения изменений и (или) дополнений в комплексное природоохранное разрешение, рассматривает их и принимает в течение 30 дней решение о внесении изменений и (или) дополнений в комплексное природоохранное разрешение или об отказе во внесении изменений и (или) дополнений в данное разрешение в порядке и на основаниях, предусмотренных в статьях 25 и 26 Закона Республики Беларусь «Об основах административных процедур».

В случае принятия органом выдачи разрешений решения о внесении изменений и (или) дополнений в комплексное природоохранное разрешение срок его действия не изменяется.

32. Действие комплексного природоохранного разрешения прекращается по решению суда, а также по решению органа выдачи разрешений при:

выдаче нового комплексного природоохранного разрешения;

прекращении деятельности или ликвидации природопользователя;

неполучении природопользователем комплексного природоохранного разрешения в течение шести месяцев со дня принятия решения о выдаче комплексного природоохранного разрешения или внесении в него изменений и (или) дополнений либо продления срока его действия;

выявлении факта представления недостоверных сведений, на основании которых выдано комплексное природоохранное разрешение, внесены в него изменения и (или) дополнения, продлен срок его действия.

33. Орган выдачи разрешений уведомляет природопользователя о прекращении действия комплексного природоохранного разрешения в течение 5 рабочих дней со дня принятия им такого решения в порядке, предусмотренном в статье 27 Закона Республики Беларусь «Об основах административных процедур».

Available on: http://ec.europa.eu/environment/enlarg/handbook/handbook.htm

The key characteristics and the schemes 5.1 and 5.2 are borrowed from the mentioned above Manual for IPPC inspectors (Zagreb, 2009)

E.g. the Environment Agency in the UK, the Institute for environmental management in Hungary, VITO institute in Belgium, the National Environment Institute in Finland.

This number depends on the number of sectors covered by the integrated permitting regime.

The example of instructions for developing BAT guidance is listed in the Decision 2012/119/EU on rules for the collection of data and on the drawing up of BAT reference documents, available at http://eur-lex.europa.eu/LexUriServ/LexUriServ.do?uri=OJ:L:2012:063:0001:0039:en:PDF