## Slide 1
Making projects more environmentally sustainable – module 6
Environment and climate change in development cooperation

## Slide 2: Structure of module 6
Situation analysis
Idea identification
Project formulation
Implementation
Evaluation
The Project Process
Entry points for increasing the environmental sustainability of a project
Notes: Expansion
Examples:
Groupwork / discussion

## Slide 3: Situation analysis
Collecting data on the situation
Identify stakeholders and their interests
Identify risks, problems, negative factors and threats related to environment and climate
Identify strengths, positive factors and opportunities
Discuss cause-effect diagrams to analyse the linkages between the factors and understand the logics of the area
Create Problem Tree
Notes:   Identifying project ideas consistent with partner country’s and EC’s objectives and strategies
  Assessing relevance and feasibility
  Pre-selecting options that look worth financing and will be subject to more detailed formulation

## Slide 4: Problem analysis – Problem Tree
At the top: future threats and impacts
In the middle: environment deterioration affecting production and well-being
At the bottom: natural constraints, climate change influences, institutional causes
Kenyan sugar sector is not competitive
Incorporating ENV and CC
Bad infrastructure
High transportation costs; loss of cane
Low cane quality
Low yields, low quality
Low mechanisation
Poor husbandry practices
Limited research in cane development
Payment system based on weight
State owned sugar mills inefficient
Costly import of sugar
Threatening collapse of sector
Fragile livelihood of farmers
No valuable add on benefits
No co-generation of power
Organisations are weak
Lack of training and motivation
Land degradation; soil errosion; energy loss; climate impact; increased poverty; deterioation of ecosystems; water wastage; ….
Changed rain patterns; longer dry season; reduced growing areas; higher population pressure; lack of governmental support, ….
Worsened situation ….
Notes: A very useful tool that is not always used – provides a very clear picture of the challenges meeting the developing country / the donor in a specific context.
The greened logframe
Built on the basis of adequate consideration of environmental issues in stakeholder analysis and problem analysis (and then in objective and strategy analysis)
Integrates the environmental dimension:
  In the identification of objectives and expected results
  but also in the choice of “environmentally sustainable” indicators
  And in the formulation of the risks and assumptions on which project success depends

## Slide 5: Strategy analysis
At the top: Future overall goals
In the middle: Objectives for environmental efforts
At the bottom: Outputs of practical efforts
Kenyan sugar sector is competitive
Low transportation costs, no crops lost
High yields, high quality
Private + effective sugar mills
Self-sufficiency with sugar
Stronger sugar sector
Good livelihood of farmers
Combined sugar and power plants
Strong organisations

## Slide 6: Vision analysis
Increased agricultural production
Increased crop levels
Reduced impact of
drought on
production
Improved capacity of
new breeds to produce milk
Man hour savings through tractor use
Increased availability of land for cultivation
Increased levels of fish catches
Use of pest management techniques
Introduce irrigation systems
Cross breeding and artificial insemination
Mechani-sation – introduction of tractors
Terracing hillsides to create more land available to farm
Improving fish stocks

## Slide 7: Idea identification
The identification process:
  Identifying relevant project ideas
  Assessing relevance and feasibility
  Pre-selecting best options for detailed formulation
  Include environmental concerns where feasible
Result: Draft Identification Fiche
Notes:   Identifying project ideas consistent with partner country’s and EC’s objectives and strategies
  Assessing relevance and feasibility
  Pre-selecting options that look worth financing and will be subject to more detailed formulation

## Slide 8: Project identification The logical framework –
Specific objective
Overall objective
Means & costs
O1
O2
Intervention logic
Activities
Outputs
Assumptions
Notes: Includes consideration of environmental, CC {and GE} issues in analyses
Integrates the environmental dimension:
  In objectives and results
  In the choice of indicators
  In risks and assumptions
See Annex 6 of the Guidelines
Indicators allow measurement of the achievement of objectives and results; they are associated with targets (= quantified objectives defined in time)
Environmental indicators are selected to measure:
  the achievement of environmental objectives
  the implementation of some environmental requirements linked with other objectives (“mainstreaming-related” indicators)
Non-environmental indicators should not be associated with negative environmental pressures or impacts

## Slide 9: Building the logical framework
Output 2
Output 1
Logical framework
Moyens
Overall obj.
Specific obj.
Activity 1.1
Activity 1.2
Activity 1.3
Activity 2.1
Activity 2.2
Activity 2.3
Indicators
Sources
of verif.
Assumpt.
Specific objective
1.1
Overall objective
Means & costs
1.2
1.3
2.1
2.2
2.3
O1
O2
Intervention logic
Means & costs
9
Notes: Includes consideration of environmental, CC {and GE} issues in analyses
Integrates the environmental dimension:
  In objectives and results
  In the choice of indicators
  In risks and assumptions
See Annex 6 of the Guidelines
Indicators allow measurement of the achievement of objectives and results; they are associated with targets (= quantified objectives defined in time)
Environmental indicators are selected to measure:
  the achievement of environmental objectives
  the implementation of some environmental requirements linked with other objectives (“mainstreaming-related” indicators)
Non-environmental indicators should not be associated with negative environmental pressures or impacts

## Slide 10: Identification Fiche (or AF): Entry points
Entry point in IF / AF | Issues for ENV and CC integration
Policies/Strategies of partner government | Environmental and climate integration
Problem analysis / Strategic analysis | Problem tree and Objective tree
Stakeholder analysis | Groups affected by environmental and climatic impact; Environmental and climate stakeholders
Objectives and expected results | Project logics, the LogFrame
Assumptions and risks | Project sustainability; environmental and climate related risks
Cross-cutting issues/Sustainability | Summing up; screening results
Budget | Resources for ENV and CC measures, awareness raising, capacity development
Next steps, work plan and time schedule | Summary, plan
Notes: Partner government policies and strategies
Refer to any environmental, climate-related and/or sustainability-oriented policies and strategies relevant for the project.
Problem analysis/strategic analysis
Take into account major environmental and climate-related linkages (impacts, risks, constraints and opportunities). Refer to environmental considerations in assessing project alternatives.
Lessons learned
Refer as relevant to any lessons learned from past projects with regard to environmental sustainability, climate resilience, etc. (e.g. from the specific country or sectoral context)
Stakeholders analysis
Include groups potentially affected by environmental impacts and climate-related risks, including risks associated with increased vulnerability to climate change or variability arising from the project.
Risks and assumptions
Consider environmental uncertainties, e.g. risks of natural disasters, scarcity of some resources, risks associated with climate change and variability, and assumptions (implicit or explicit) about future climatic conditions and climate-related risks.
Objectives and expected results
Integrate climate and environment-related aspects as relevant in the description of objectives and expected results and in the logical framework (see Annex 6).
Cross-cutting issues
Specify the outcome of the environmental and climate risk screenings and indicate whether an EIA and/or a CRA study is required to properly address relevant environmental and climate aspects.
Sustainability
Consider environmental sustainability. Refer to the attention given at the identification stage to ensuring that the achievement of project objectives, activities and results do not generate increased pressure on fragile ecosystems and scarce natural resources, or drive maladaptation.
Budget
Preliminarily assess costs related to integration of environmental and climate aspects in project design and implementation. Adapt formulation costs according to the results of the screenings (based on the nature, scope and depth of further assessments required).
Next steps
Confirm in the conclusions of the screening whether an EIA and/or a CRA is required, and which environment-, natural resource- and/or climate-related aspects will be the subject of further investigation.
A summary the outcomes of the preliminary environmental screening (see Part 3 of Annex 7) should be annexed to the Project Identification Fiche.

## Slide 11
Activity 6 – ENV and CC in Action Fiche
By analysing the Action Fiche for a Sugar Sector project in Kenya the participants become aware of the many entry points for ENV and CC in Action Fiches.
Groups of 5 to 6 get together and discuss:
Read the Action Fiche for the Sugar Sector project in Kenya. Note: The action fiche has been edited by the course managers to fit the purpose of this activity.
Discuss entry points for ENV and CC in the action fiche
Give attention to the option of introducing co-generation of power to the sugar industry in Kenya
Note down on cards relevant issues to be included in the action fiche – one card for each section of the fiche.
Present to plenary
10’ for additional reading; 20’ for group discussion and cards; 15’ plenary review: allow 45 mins

## Slide 12: Call for Proposals
Excellent entry point for environmental integration.
Explicitly include ENV and CC concerns in the program/call.
Evaluate proposals with national partners.
Notes: Partner government policies and strategies
Refer to any environmental, climate-related and/or sustainability-oriented policies and strategies relevant for the project.
Problem analysis/strategic analysis
Take into account major environmental and climate-related linkages (impacts, risks, constraints and opportunities). Refer to environmental considerations in assessing project alternatives.
Lessons learned
Refer as relevant to any lessons learned from past projects with regard to environmental sustainability, climate resilience, etc. (e.g. from the specific country or sectoral context)
Stakeholders analysis
Include groups potentially affected by environmental impacts and climate-related risks, including risks associated with increased vulnerability to climate change or variability arising from the project.
Risks and assumptions
Consider environmental uncertainties, e.g. risks of natural disasters, scarcity of some resources, risks associated with climate change and variability, and assumptions (implicit or explicit) about future climatic conditions and climate-related risks.
Objectives and expected results
Integrate climate and environment-related aspects as relevant in the description of objectives and expected results and in the logical framework (see Annex 6).
Cross-cutting issues
Specify the outcome of the environmental and climate risk screenings and indicate whether an EIA and/or a CRA study is required to properly address relevant environmental and climate aspects.
Sustainability
Consider environmental sustainability. Refer to the attention given at the identification stage to ensuring that the achievement of project objectives, activities and results do not generate increased pressure on fragile ecosystems and scarce natural resources, or drive maladaptation.
Budget
Preliminarily assess costs related to integration of environmental and climate aspects in project design and implementation. Adapt formulation costs according to the results of the screenings (based on the nature, scope and depth of further assessments required).
Next steps
Confirm in the conclusions of the screening whether an EIA and/or a CRA is required, and which environment-, natural resource- and/or climate-related aspects will be the subject of further investigation.
A summary the outcomes of the preliminary environmental screening (see Part 3 of Annex 7) should be annexed to the Project Identification Fiche.

## Slide 13: Instruments - Blending
Strategic use of grant combined with additional flows such as loans and risk capital, from different sources, e.g. European Financial Institutions.
Support can be provided under different forms (investment grant, TA, guarantees, interest rate subsidy)
Objective: to achieve financial and non-financial leverage in support of EU policy objectives.
Seven regional blending facilities: covering mainly [Transport], Energy, Environment, Water and support to SME's sectors.
Climate change windows: new resources. Tracking of climate change related projects (Rio markers). More than €500 million EU grants committed to green projects (60% of all commitments).
Blending is not an objective, but an instrument.
Notes: Expansion
Examples:
Groupwork / discussion

## Slide 14
Uganda: support development of SME's in Agribusiness by improving access long term finance. Total Project Volume: €30 m NIP resources: €15m Involved EFI's to be defined
Egypt: Wind Farm in the Gulf of El Zayt. Total Project Volume: €340 M NIP resources: €20M NIF Resources: €10M Involved EFI's: EIB/KFW
Central America EE & RE SME Programme: TA component (energy audits, feasibility studies), supporting of promotion and implementation. Total: €36 m, Grant: €3 m; Involved EFIs: KfW, BCIE
Burkina Faso: Solar Power Plant
Instruments – Examples of blending

## Slide 15: Screening for ENV and CC impact
Is there a legal requirement for an EIA?
Would an EIA or CRA fit a policy commitment?
Annex 7 – project lists and questions
Are there significant climate issues?
Project EIA and CRA classes:
  A – significant impacts expected – EIA/CRA required
  B – some uncertainty, further analysis necessary
  C – no significant impacts – EIA/CRA not required
15
Notes: Is there a legal requirement under national legislation for an EIA to be conducted ?
Would an EIA be recommended in conformation with a policy commitment?
Annex 7 – project lists and questions
Project EIA classes:
A – significant impacts expected – EIA required
B – some uncertainty, further analysis necessary
C – no significant impacts expected – EIA not required

## Slide 16: Formulation phase
Project
  The potential (positive and negative) impacts of the project on the environment and climate
  The (positive and negative) environmental conditions that may affect the effectiveness, efficiency, sustainability or impact of the project
  Impacts generated
  Opportunities, risks & constraints
  ENVIRONMENT
EIA, CRA or Formulation study
Notes: Some sector programmes require an SEA, others do not
In both cases: Action Fiche (+ Technical and administrative provisions to be attached to the Financing Agreement)
Annex 4 of the Guidelines identifies the environmental issues to be considered in SPSP formulation studies
Identification of environmental opportunities, risks and constraints
Evaluation of the sector programme’s main environmental impacts, incl. alternatives and socio-economic dimension
Analysis of performance indicators
Evaluation of institutional capacities
Recommendations for sector programme improvement and SPSP formulation

## Slide 17: Project formulation
Studies potentially undertaken during the formulation phase
Technical feasibility study
Environmental impact assessment
Climate risk assessment
Financial and economic analysis
OR, preferably a single “formulation study” covering these various aspects of the project.
Findings should be fed back into the logframe and relevant sections of the action fiche
17
Notes: Includes consideration of environmental, CC {and GE} issues in analyses
Integrates the environmental dimension:
  In objectives and results
  In the choice of indicators
  In risks and assumptions
See Annex 6 of the Guidelines
Indicators allow measurement of the achievement of objectives and results; they are associated with targets (= quantified objectives defined in time)
Environmental indicators are selected to measure:
  the achievement of environmental objectives
  the implementation of some environmental requirements linked with other objectives (“mainstreaming-related” indicators)
Non-environmental indicators should not be associated with negative environmental pressures or impacts

## Slide 18: Indicators
Indicators allow measurement of the achievement of objectives and results; they are associated with targets (= quantified objectives defined in time)
Environmental indicators are selected to measure:
  the achievement of environmental objectives
  the implementation of some environmental requirements linked with other objectives (“mainstreaming-related” indicators)
  Quick buzz:
  Suggest three project targets and related indicators
  More bout indicators in module 8
18
Notes: Includes consideration of environmental, CC {and GE} issues in analyses
Integrates the environmental dimension:
  In objectives and results
  In the choice of indicators
  In risks and assumptions
See Annex 6 of the Guidelines
Indicators allow measurement of the achievement of objectives and results; they are associated with targets (= quantified objectives defined in time)
Environmental indicators are selected to measure:
  the achievement of environmental objectives
  the implementation of some environmental requirements linked with other objectives (“mainstreaming-related” indicators)
Non-environmental indicators should not be associated with negative environmental pressures or impacts

## Slide 19: AF and TAPs (repetition from IF)
Possible entry points | Environmental aspects
Justification, problem analysis | Environmental issues addressed
Objectives and expected results | Environmental constraints linked to objectives/results
Stakeholder analysis | Stakeholders who may see their environment modified by the project
Assumptions and risks | Environment risks and climate-related risks
Cross-cutting issues | Measures to ensure environmental sustainability
Monitoring and evaluation | Environment-related indicators
Annexes to the TAPs | EIA report, EMP, budget for environmental management, …
19
Notes: At the end of the formulation phase, the drafting of the Action Fiche (AF) and Technical and Administrative Provisions (TAPs) of the financing agreement should be based on a careful review of the results of the environmental mainstreaming process to this point, as well as an appreciation of the acceptability of the project with respect to the negative impacts and climate-related risks that cannot be mitigated (residual impacts and risks), exposure to other environmental risks and constraints, and adaptation requirements.The logical framework should be finalised taking into account the results of the screening process, the results of the EIA and/or CRA (if any), and otherwise the results of environmental integration in the formulation study. Table 6.2 provides a checklist of entry points to consider.
Exercise: Examples on env and climate requirements in AF or TAP?

## Slide 20: Implementation: Entry points
Minimise pollution-generating consumption
Incl. EMP or equivalent measures
Incl. env. and cc indicators
Incl. environment-related ones
Execution of action plan
Monitoring activities:
    Monitoring of activities, consumption, costs,…
    Monitoring of results (based on indicators)
    Monitoring of assumptions and risks to be able to respond quickly to new information and changes in the project’s environment
Undertaking environmental performance review is a good management practice

## Slide 21: Implementation – Roles
Stakeholder | Roles
EC Staff | Check that ENV and CC requirements from previous steps are complied with Check that conclusions from EIA and CRA are reflected in project documents Promote ‘environmental performance review’ or ‘climate risk review’
National partner | Evaluation of measures to address ENV and CC related risks Project management and monitoring
Project management team | Implementing project activities, including EMP or Climate Adaptation Plan measures Monitoring – also ENV and CC related indicators Complying with national legislation

## Slide 22: Evaluation – ENV and CC indicators
22
Environmental, Climate Change and Green Economy indicators are selected to measure:
  the achievement of ENV and CC objectives
  the implementation of ENV and CC requirements linked with other objectives (“mainstreaming-related” indicators)
Non-environmental indicators should not be associated with negative environmental pressures or impacts
Notes:   Indicators allow measurement of the achievement of objectives and results; they are associated with targets (= quantified objectives defined in time)
Indicators are usually classified according to their level: input indicators (which measure the resources provided),
output indicators (direct results), outcome indicators (benefits for the target group) and impact indicators (longterm
consequences).
Independently from the environmental nature of the indicators, the hierarchy between these levels should always
be maintained, especially when the inputs or the outputs are a source of environmental impact. For instance, when
roads are built (outputs) to allow farmers to sell more and at a higher price (outcome), we should never measure
the outcome in terms of ‘number of km of road’ because this is reflecting a cost, including an environmental cost.
Similarly, if we want to protect biodiversity (impact), we should be aware that the area covered by the network of
protected areas (MD G 7, target 7.B, indicator 7.6) measures only an institutional input and implies costs that are
not necessarily compensated by a positive impact on biodiversity. This is a general rule but it is particularly important
for environmental integration because environmental costs are frequently associated with low-level objectives.
Environmental indicators can also be classified according to another system: the DPSIR 170 (Driving forces - Pressure
– State – Impact – Response):
ÎÎ ‘Driving forces’ relates to drivers, such as population growth, markets, education.
ÎÎ ‘Pressure’ refers to the human activities generating impacts, e.g. fishing, logging, emission of pollutants.
ÎÎ ‘State’ refers to the situation and trends of environmental resources or parameters, e.g. forest cover or
deforestation rate, water quality.
ÎÎ ‘Impacts’ refers to the consequences for human beings171, ecosystems and man-made capital.
ÎÎ Response refers to the measures taken in order to address environmental issues, e.g. establishing
protected areas, preparing new laws.
It is important not to mix these classification systems (notably in assessments like the Country Environmental
Profile). In logical framework approaches (for NI Ps, GBS, SPSPs or projects) the input–output–outcome–impact
system is the most adequate.

## Slide 23: Environmental and climate change indicators
  In the logframe
  In the monitoring framework
  In the Environmental Management Plan
Regular monitoring of environmental indicators is useful as a preparation for project evaluation:
  Basis for the definition of impact indicators
  Basis for evaluating the effect of external factors on the achievement of project objectives
23
Notes: Refer also to module 9

## Slide 24: Evaluation: Environmental and climate change integration
Implementation of the recommendations formulated in the EIA, the CRA and/or the formulation study?
Level of implementation (zero, partial, full)
Effectiveness and efficiency (cost-effectiveness) of environmental integration measures
Impact and sustainability of these measures
Impact of environmental integration (or lack thereof) on the project’s general performance?
24

## Slide 25: Evaluation: Environmental and climate change integration
The classical evaluation criteria (for both projects and sector support) can be interpreted from an environmental perspective
Relevance
Effectiveness
Efficiency
Impact
Sustainability
25

## Slide 26: BUZZ groups, two persons Define important environmental evaluation criteria – 10 mn
Relevance
Effectiveness
Efficiency
Impact
Sustainability
26

## Slide 27: The ex post EIA
Usually, an (ex ante) EIA predicts potential impacts
The ex post EIA determines actual impacts. It aims to:
      Improve capacities to predict environmental impacts, for use in future EIAs
      Study in more detail the environmental aspects of project evaluation (impact criterion) so as to draw lessons for future projects
27

## Slide 28: Module 6 – recap main messages
Making a project more sustainable starts with an analysis of problems and opportunities
The identification phase encircles the project and makes potential environmental and climate perspectives more visible
Screening tools are useful in the identification phase and different entry points are available
In the formulation phase, EIA and CRA can be highly effective
Implementation – entry points, indicators and roles
Evaluation is about relevance, effectiveness, efficiency, impact and sustainability

## Slide 29: Resources – Module 6
Project Cycle Management – EU http://ec.europa.eu/europeaid/multimedia/publications/documents/tools/europeaid_adm_pcm_guidelines_2004_en.pdf
Guidelines on environmental mainstreaming – EU http://ec.europa.eu/europeaid/infopoint/publications/europeaid/documents/172a_en.pdf
Environmental Integration Handbook – EU http://ec.europa.eu/europeaid/multimedia/publications/documents/thematic/europeaid-environmental-handbook_en.pdf
Sector support and project guideline – EU http://ec.europa.eu/europeaid/how/delivering-aid/sector-approach/documents/guidelines_support_to_sector_prog_11_sept07_final_en.pdf
Evaluation Guideline – EU http://ec.europa.eu/europeaid/infopoint/publications/europeaid/8a_en.htm
Risk assessment and mapping guideline – EU http://ec.europa.eu/echo/civil_protection/civil/pdfdocs/prevention/COMM_PDF_SEC_2010_1626_F_staff_working_document_en.pdf

## Slide 30: Optional slides
30

## Slide 31: Relevance
Has the project taken into account the environmental issues identified during problem analysis and/or in the Country Environmental Profile?
Has the project been given environmental objectives, or have environmental constraints been attached to its objectives, so as to properly manage its potential environmental impacts?
31

## Slide 32: Effectiveness
If the project was effective (i.e. achieved its objectives), was this at the expense of the environment?
If the project was not effective, was this because some environmental constraints were under-estimated?
Have the adopted environmental measures (e.g. Environmental Management Plan) produced the expected effects?
32

## Slide 33: Efficiency
Has the project made an appropriate (limited) use of scarce resources or inputs that damage the environment?
Were the measures adopted in the context of the Environmental Management Plan (or similar measures) cost-effective?
33

## Slide 34: Impact
What were the project’s environmental effects on the outside world? Are they acceptable? How do they compare with the effects predicted in the EIA?
Overall, has the project contributed to the objective of promoting sustainable development?
34

## Slide 35: Sustainability
Are the natural resources on which the project’s sustainability depends threatened?
Does the project itself encourage stakeholders to overexploit their resources?
If the Environmental Management Plan recommends the adoption of recurrent and long-term mitigation measures, are they financially sustainable?
35

## Slide 36: Instruments - Blending
Strategic use of grant combined with additional flows such as loans and risk capital, from different sources, e.g. European Financial Institutions.
Support can be provided under different forms (investment grant, TA, guarantees, interest rate subsidy)
Objective: to achieve financial and non-financial leverage in support of EU policy objectives.
Seven regional blending facilities: covering mainly [Transport], Energy, Environment, Water and support to SME's sectors.
Climate change windows: new resources. Tracking of climate change related projects (Rio markers). More than €500 million EU grants committed to green projects (60% of all commitments).
Blending is not an objective, but an instrument.
Notes: Expansion
Examples:
Groupwork / discussion

## Slide 37
Uganda: support development of SME's in Agribusiness by improving access long term finance. Total Project Volume: €30 m NIP resources: €15m Involved EFI's to be defined
Egypt: Wind Farm in the Gulf of El Zayt. Total Project Volume: €340 M NIP resources: €20M NIF Resources: €10M Involved EFI's: EIB/KFW
Central America EE & RE SME Programme: TA component (energy audits, feasibility studies), supporting of promotion and implementation. Total: €36 m, Grant: €3 m; Involved EFIs: KfW, BCIE
Burkina Faso: Solar Power Plant
Instruments – Examples of blending