## Slide 1: Regional Water and Energy Seminar – Nadi – Fiji May 2014
Energy Facility Projects in Vanuatu

## Slide 2: Energy Facility I projects
Vanuatu submitted four proposals to the global CfP and all four were granted.
Total amount of grants: EURO 2,494,098
Beneficiaries: local government (Provincial) for 3 grants and one NGO (VANREPA) for the 4th one.
Implementation: 24 months for three projects with Provinces (MALANPA, PENAMA and TORBA) and 30 months with NGO.
Contracts signed in Dec. 2007 and first installment disbursed within two weeks after signature.

## Slide 3: Type of projects
3 projects addressed production and distribution of electricity in rural areas. Low tension and copra oil as the source of energy for generators. Entire process from copra production to distribution of electricity to be managed by communities. Successful pilot project in island of Espiritu Santo (Port Olry)

## Slide 4: From Copra, to oil and pre-paid card in Port Olry

## Slide 5: The answer is blowing in the wind…
Wind mills and battery banks for the two southernmost islands in Vanuatu. Not too many coconuts but plenty of wind. (island of Futuna below)

## Slide 6: Outcome of these grants
3 Copra oil projects: no electricity is produced today. Issue with financial/record of expenditure, whereabouts of interests and contractors not happy, ready to sue the provincial government. One grant contract fully remastered.
Vanuatu daily news digest | 6 May 2014Supplementary Budget approved by Parliament for this year amounts to VT 300 million. The Prime Minister has revealed that the additional funding is predicated upon the anticipated financial benefits to be derived from the Permanent Residence Programme based in Hong Kong and the Capital Investment Immigration Plan and Consular Programme (CIIP), Daily Post reveals this morning. CIIP has still to be debated in Parliament, item 23 on the MPs' agenda. Additional budgetary concerns involve a payment of VT 135 million under the Interchange (bandwidth) project and VT 139 million for the government's contribution to the European Union's Electrification Facilities projects in Torba, Malampa and Penama, along with provisions for the 2017 Mini Games (VT 29 million).

## Slide 7: Futuna and Anneytum: no electricty
Heading for full recovery. Article in the British press in December 2013.
None of the project have made it past the first disbursement. Political interference.

## Slide 8: Energy Facility II
Two submissions. One successful from the Government for a 1 MW solar farm. EIB already refinanced on the same site 11 Wind mills .
Government being the beneficiary we had to sign a FA. Government is co-donor with 720,000 EURO , EU 2.5MEURO and UNELCO (concession for production/distribution of electricity in Port Vila) 1 MEURO.
Implementation: 48 months from signature in June 2012.

## Slide 9: Expected Results:

## Slide 10: 23 months later
NAO is yet to finalise and sign the intended grant of 2.5 MEURO to UNELCO so that the project can start, fully managed by a company of the Suez Group, fully capable of taking the project to a success.
Not enough time left in the FA to implement the project (30 months minimum).
Unless full commitment from government and a rider to the FA. Will not be successful.

## Slide 11: Discussions:
Call for Proposal process. Are the project fully appropriated by Beneficiaries? Case of Water facility submissions as well.
EU procedures?
Capacity of beneficiaries to implement and more specifically accountability?
Political economy
Impact of failure of these projects on local poor population.
How could we improve?