## Slide 1: Pacific - Regional Water and Energy Seminar, Exchange of best Practice
EXPERIENCES WITH BUDGET SUPPORT IN SOLOMON ISLANDS
Marc Van Uytvanck
12-15 May 2014

## Slide 2: Solomon Islands Climate Change Adaptation Programme (SICAP)
Duration: 4 years (2011-14)
Budget: € 2.8 M
Modality: General Budget Support
Tranche 1: Fixed € 1M & Variable € 0.225M
Tranche 2: Fixed € 1M & Variable € 0.5 M

## Slide 3: Releases¹
General conditions (3): F + V
National policy and strategy process: process of the implementation of the Medium-Term Development Strategy (MTDS) and National Development Strategy Framework (NDS)
Macro-economic stability: maintaining a policy of macroeconomic stability, review of IMF-backed macroeconomic programme
Public finance management: improve and reform public finance management identified in the Governments Economic and Financial Reform Priorities matrix (EFRP)

## Slide 4: Releases²
Specific conditions (3): V
CC is mainstreamed in the Development Budget: development budget allocates at least SBD 10M to the implementation of National Adaptation Programme of Actions (NAPA)
Institutional capacities of Ministry of Environment strengthened: training on Climate Change and/or Disaster Risk Reduction received by technical
CC Strategy is approved: including ranking of affected high-risk communities; costing of CC adaptation measures; and Guidelines for Human Resettlements projects to minimize risks of conflicts

## Slide 5: Assessment¹
General conditions
MTDS & NDS (M)
IMF review (M)
PFM review through EFRP matrix agreed between SIG & donor partners in the Core Economic Working Group (CEWG) (NM)
2012 Public Expenditure & Financial Accountability (PEFA) assessment

## Slide 6: Assessment²
Specific conditions
Budget allocated & degree of implementation (PM)
Trainings attended & supporting documents (PM)
CC policy & implementation of sub-conditions (PM)
Conclusion: No 2nd tranche release

## Slide 7: Improving governance and access to water, sanitation and hygiene promotion (WASH) for rural people.
Duration: 5 years (2014-19)
Budget: € 17.4M
Modality: Sector Reform Contract
5 Tranches: Fixed € 10M & Variable € 3M
Support: TA, studies, contingencies, evaluation, visibility: € 4.4M
FA: 2014

## Slide 8: Bottlenecks
CEWG excellent for policy dialogue, but each donor utilizes its own criteria → no common ground on releases of tranches for BS
Assessment can be negative, but political reasons can overtake and tranches are released → credibility towards BS
Small delegations do not always have an economist as staff member to handle the 3 GCs