EXTERNAL COMMUNICATION STRATEGY (ECS)

ACTION PLAN 2009/2010

Actions running from the end of 2009 to 2010 should capitalize on the campaign theme sparked at Stockholm Water week, and based on the ECS paper approved earlier in spring by the EUWI secretariat, in partnership with EUWI working groups.

EUWI is a catalyst. It makes things happen, as one poster at Stockholm water week stated: “goodwill makes it happen”. Thus, the communication concept consists of stressing tangible and concrete benefits from EUWI efforts, especially at grass-root levels, whenever feasible. Ideally, audio-visual / motion picture should highlight these benefits in a form of “storytelling” video clips that should not last more than two (2’) minutes (3’ being a maximum). So, the creative concept should follow a countdown principle: to start the story from the factual results (more often at a population level), and take it back up to the ignition, which is EUWI.

Of course, other means of communication are to be implemented (posters, brochures...) when appropriate, provided they are executed according to the present rules of communication established by the publics’ attitudes toward these means of communication.

In practice, each region working group should be involved in the communication effort, and come up with a sufficient amount of stories –related to EUWI objective fulfilments– among which to select the most impactful one(s). The material to script the stories should encompass the tale itself, plus story-related graphs, pictures and videos. The group should also avail a group’s spokesperson who will narrate the story, as a voiceover and/or featuring in person on the video clip. Having local people to witness about water improvement is mandatory.

Since short format video clips are also (should be) good user-friendly means of information, they should then be displayed:

- in communication campaigns,

- during conferences & presentations, and Working Groups’ meetings.

- on EUWI, SPLASH, and other related websites & electronic vehicles,

The more we describe the chain of actions and results initiated by EUWI, the more government officials, scientists, NGOs, and water managers will feel uplifted and valued for having had a share in some actions for which they literally see plain results. The more we track those concrete results, build a database of them, and advertise about them, the more EUWI will get publicity and support.

A few success stories among the many to exploit:

- Expanding from the Stockholm water week 5 booklet stories

- Funds allocated to research through EUWI increasing dramatically: + €100 million in FP6 Global Chang; + €32 million under FP6 Cooperation Program

- EUWI obtaining in 2004 €500 million for the ACP-EU Water Facility for development of water and sanitation in Sub-Saharan Africa

- Together with AMCOW, launching a five African river basin programme supporting transboundary water management

- AWG helping development and recognition of the African ANEW NGO network as the civil society representation in EUWI-AWG

- FWG bringing together water practitioners and financial specialists

2009/2010 ECS ACTION PLAN

| Communication vehicles | Outlets | Quantity | Copywriting + Art direction | Execution | Time frame |
| --- | --- | --- | --- | --- | --- |
| Kinds / types of communication vehicles | Outlet description | Amount of needed items | Who is in charge for text, visuals and making of? | Who is in charge for layout, editing & execution? | Timing & bottom-line |
| Video clip stories* from EECCA working group’s successful outcomes. Testimonial length between 0:30 up to 3:00 minutes. EECCA WG to provide content. | Ideally, stories should materialise successful implement-ation of any of EUWI 5 objectives in that region. | Ideally, one clip per EUWI objective > 5 clips | EUWI com officer to gather story content from working group representative; EUWI com officer to organise content and write storyboard (outsourcing art work if need be). | EUWI com officer to brief video editor (internal or outsourced?) and supervise the making of. | Starting asap; completing work during spring |
| Video clip stories from Mediterranean working group’s successful outcomes. Testimonial length between 0:30 up to 3:00 minutes. Mediterranean WG to provide content. | Ideally, stories should materialise successful implement-ation of any of EUWI 5 objectives in that region. | Ideally, one clip per EUWI objective > 5 clips | EUWI com officer to gather story content from working group representative; EUWI com officer to organise content and write storyboard (outsourcing art work if need be). | EUWI com officer to brief video editor (internal or outsourced?) and supervise the making of. | Starting asap; completing work during spring |
| Video clip stories from Africa working group’s successful outcomes. Testimonial length between 0:30 up to 3:00 minutes. AWG to provide content. | Ideally, stories should materialise successful implement-ation of any of EUWI 5 objectives in that region. | Ideally, one clip per EUWI objective > 5 clips | EUWI com officer to gather story content from working group representative; EUWI com officer to organise content and write storyboard (outsourcing art work if need be). | EUWI com officer to brief video editor (internal or outsourced?) and supervise the making of. | Starting asap; completing work during spring |
| Video clip stories from Latin America working group’s successful outcomes. Testimonial length between 0:30 up to 3:00 minutes. LA WG to provide content. | Ideally, stories should materialise successful implement-ation of any of EUWI 5 objectives in that region. | Ideally, one clip per EUWI objective > 5 clips | EUWI com officer to gather story content from working group representative; EUWI com officer to organise content and write storyboard (outsourcing art work if need be). | EUWI com officer to brief video editor (internal or outsourced?) and supervise the making of. | Starting asap; completing work during spring |
| Video clip stories from NGOs’ working group’s successful outcomes. Testimonial length between 0:30 up to 3:00 minutes. NGOs to provide content | Ideally, stories should materialise successful implement-ation of any of EUWI 5 objectives in their field. | Ideally, one clip per NGO / per story > ‘n’ clips | EUWI com officer to gather story content from NGO’s representative; EUWI com officer to organise content and write storyboard (outsourcing art work if need be). | EUWI com officer to brief video editor (internal or outsourced?) and supervise the making of. | Starting asap; completing work during spring |
| Video clip stories from Research & Finance successful outcomes. Testimonial length between 0:30 up to 3:00 minutes. Research & Funding to provide content. | Ideally, stories should materialise successful implement-ation of any of EUWI 5 objectives in their field. | Ideally, one clip per success / significant action > ‘n’ clips | EUWI com officer to gather story content from Research’s representative; EUWI com officer to organise content and write storyboard (outsourcing art work if need be). | EUWI com officer to brief video editor (internal or outsourced?) and supervise the making of. | Starting asap; completing work during spring |
| Posters | Poster should depict significant visual + headline extracted from story(ies) | One per story. Amount of posters depends on use: a few for congress/ convention; 20-200+ for media PR. | EUWI com officer to extract significant message and finds creative leap to draw attention, raise interest, and spark viewer’s expected attitude (if need be, art work & prepress outsourced). | OIB or JRC for printing of small quantities; perhaps outsourcing if media PR (printing techniques differ when big quantities). | Depending on events to come: Stockholm water week; timely campaign, if any |
| Leaflets | Leaflet should significantly reflect in visual, headline & text (body copy) what video clip story is | One per story. Duplication depends on leaflet use and publics to reach: thousands of samples in any case. | EUWI com officer to extract significant message and finds creative leap to draw attention, raise interest, and spark viewer’s expected attitude (outsourcing art work if need be). | Outsourcing art work (design, layout) & prepress if need be; OIB for printing | Depending on events to come: Stockholm water week; campaign timing, if any |
| PPT presentation Visual aid/support for conference, convention. Must be short; a few words, eye-catching visuals, uncluttered | Only highlights; closely respecting rules on ppt good use. If possible, mix with short video clip or clip extracts | One per event | Speaker to brief EUWI communication officer and give him/her highlights to stress. EUWI com officer to make ppt presentation with respect to proven best practice methods | EUWI com officer | To be delivered one week the latest before actual event to allow slight changes |
| Annual report 2010 EUWI activities & achievements per region, accounts, political messages... | Exhaustive details from EUWI activities | 1 electronic format posted on the web | DG Dev EUWI secretariat to gather content; EUWI com officer to rewrite. DGT to proofread if available & willing | OIB: editing (layout) & printing if necessary. JRC editing on web | 07/2010 |
| Annual report 2010 executive summary | User-friendly highlights from 2010 report | 1 electronic format + paper brochure if needed | DG Dev EUWI secretariat to select content from whole 2010 report; EUWI communication officer to rewrite. DGT to proofread if available & willing | OIB: editing (layout) & printing. JRC editing on web | 07/2010 |
| EUWI Website: to consider whether JRC keeps handling it or entrusted to another entity. Also discussing login & password legitimacy (not being overly secretive) | Creating paths & links toward Aquaknow, SPLASH, & NeWater, and other related websites, emailing campaign towards stakeholders | Enriching website: forums, FAQ sheet, newsletters multimedia devices, | EUWI officer to: - coordinate contributors’ work - brief & give advice to website team (designer, editor, webmaster...) - write, rewrite, and update page content | EUWI com officer + website team | Ongoing process |
| EUWI website referencing. Beyond the 3rd page of a search engine, a website will never be seen! Under the entry “water”, EUWI appears only on Google page 23. | Internet strategy: use Direct Mkg (DM) methods to optimise EUWI location on the net | Implement-ing a series of tools and tips for better referencing | EUWI communication officer to advise and brief website team | EUWI website team | Ongoing process |
| Blurb for EUWI ambassadors next to partner countries government’s representatives | A pitch similar to a FAQ; short demo of EUWI achieve-ments | Electronic format to download and/or 1 paper per EUWI ambassa-dor | EUWI communication officer to write the blurb | EUWI website team + OIB: editing on website & printing if needed | 01/2010 |

*Clip: a multi-media mix of audio & visual:

- motion pictures

- photos (zoom effect, fade in/out)

- sounds, narrator

- graphs (KISS:Keep-It-Short-&-Simple)

- drawings, etc.

Though the idea is to ultimately avail communication vehicles on EUWI.net, they can be partly or totally gathered together on a CD-ROM or DVD for distribution.