ACP – EU Water Facility

Contribution Agreement 9 ACP RPR 109#2

Support to the Finance Working Group of

the EU Water Initiative

Final Report

31 May 2010

The contents of this publication are the sole responsibility of Global Water Partnership/EUWI FWG and can in no way be taken to reflect the views of the European Union.

| Global Water Partnership Organisation (GWPO) Drottninggatan 33 111 51 Stockholm Sweden Phone: + 46 (0) 8 522 126 30 Fax: + 46 (0) 8 522 126 31 | EU Water Initiative Finance Working Group (EUWI FWG) c/o GWPO Secretariat Drottninggatan 33 111 51 Stockholm Sweden Phone: +46 (0) 8 522 126 45 Fax: +46 (0) 8 522 126 31 |
| --- | --- |

List of Content

List of Abbreviations

1.  SUMMARY AND CONTEXT	5

2.  ACTIVITIES AND STATUS OF OUTPUTS	        6

3.  DIFFICULTIES ENCOUNTERED AND MEASURES TAKEN	 8

4.  CHANGES INTRODUCED IN IMPLEMENTATION	10

5.  ACHIEVEMENTS/RESULTS	10
6.  COMMENTS ON FINANCIAL EXPENDITURE REPORT	14

7.  RESULTS ANALYSIS – ADDITIONAL COMMENTS	15

ANNEX I: Final report from the project Strengthening Capacity in Strategic

Financial Planning for the Water Supply and Sanitation Sector in Lesotho

ANNEX II: Financial Expenditure Report and Budget Follow-up 2008 - 2010

List of abbreviations

| AFD AMCOW | Agence Française de Développement African ministers’ council on water |
| --- | --- |
| AWG | EUWI Africa Working Group |
| DFID | Department for International Development |
| EECCA EUWI | Eastern Europe, Caucasus and Central Asia European Union Water Initiative |
| FWG | Finance Working Group |
| GWPO MDG MoU | Global Water Partnership Organisation Millenium Development Goal Memorandum of Understanding |
| OECD SG | Organisation for Economic Co-operation and Development Steering Group (of EUWI) |
| SSA SWAp | Sub-Saharan Africa Sector-wide approach |
| WB | World Bank |
| WSP | Water and Sanitation Programme |
| WSS WWF | Water supply and sanitation World Water Forum |

# 1. SUMMARY AND CONTEXT

| Project location | GWPO/EUWI FWG Secretariat (Sub-Saharan Africa) |
| --- | --- |
| Project start date: | 01/01/08 |
| Project end date: | 31/03/10 |
| Total Project duration (in months) | 27 months |
| Total budget | € 413,126 (as per Amendment No. 2 to the contract) |
| EC contribution: | € 223,088 |
| (%) of eligible costs | 54% |

The European Union Water Initiative (EUWI) is a contribution of the EU towards achieving the water-related Millennium Development Goals (MDGs). The Finance Working Group (FWG) was formed in 2003 to shape the financial strategy of EUWI. Originally, the FWG was hosted by DFID (UK), since July 2006 it is hosted by the Global Water Partnership Organisation (GWPO) in Stockholm under an agreement between DFID and GWPO.

The FWG has implemented a project co-financed by the ACP-EU Water Facility and DFID that has now come to a close, this is the final report. The project budget was at the outset €740,000 financed by a contribution of €400,000 from the ACP-EU Water Facility (WF) and the balance of €340,000 co-funded by DFID during 2008-2009. The scope of the project was reduced in 2009 and the revised budget according to Amendment No. 2 to the contract was €413,126.

The project focused on the implementation of Water Supply and Sanitation (WSS) sector financing strategies in two African countries (later reduced to one) and over half of the total budget was earmarked for this end. The main project goal was to contribute to achieving the fifth EUWI objective which reads “identification of additional financial resources and mechanisms to ensure sustainable financing” of the WSS sector.

The country study in Lesotho was implemented in partnership with the Organisation for Economic Co-operation and Development (OECD) using mainly the FEASIBLE methodology. The study was initiated in October 2008 and completed in February 2010. It achieved its intended objectives, although implementation took longer than anticipated due to problems related to access to data. The project included a component for capacity development and dissemination of the experiences gained from the country study.

This final project report follows the outline of progress reports # 1 and # 2 dated 16 January 2009 and 22 January 2010 respectively. The final report from the Lesotho country study is at Annex I, while Annex II provides a summary of project costs. Other reports from the study are recorded on a CD-ROM that will be sent with the hard copies of this report.

# 2. ACTIVITIES & STATUS OF OUTPUTS

Activities and status of outputs of planned activities are shown below as listed in the EUWI FWG work plan for 2008. They will be further described in section 5 (Achievements/Results) and also in section 7 (results analysis – additional comments).

| Strategy respective paragraphs | Activities | Expected outputs | Activities and status of outputs |
| --- | --- | --- | --- |
| - Provision of financing expertise at country level in response to requests | - Technical assistance to develop country level WSS finance strategy | - AWG / FWG meetings - Design, preparation & implementation of financing strategies in selected SSA countries - Collaboration with EU MS / EC at country level - Consultancy contracts | 1. Completed: 5 AWG meetings and 2 FWG meetings during the project period. 2. Completed: Financing strategy project in Lesotho. The final report from this project is at Annex I. 3. Completed: Collaboration with EU/EC and other donors in Lesotho on this project in preparation for a SWAp for support to the WSS sector. 4. Completed: Consultancy contract signed with PEM consult for the development of a WSS financing strategy in Lesotho. |
| - Maximise opportunities for accessing EU resources available for support | - Develop guidance on approach, tools and methodologies to develop WSS finance strategies - Produce studies, analysis and reviews of financial resources in water sector to inform water sector practitioners. - Provision of ad hoc technical assistance | - FWG membership - FWG meetings. - Joint meetings (with key partners) - Collaboration between FWG key partners e.g. WSP/ OECD /GWP on best practice - Collaboration with Donors / IFIs - Consultancy contracts | 1. Completed: Broad stakeholder representation and steady number of FWG members. 2. Completed: EUWI FWG annual meetings were held during the World Water Week in Stockholm in August 2008 and 2009. 3. Completed: Meetings were held with GWP, DFID, OECD, the OECD Task Force on water finance, Sida, SIWI, and the EUWI Coordination Group. 4. Completed: Close collaboration with OECD on tools and methodologies (best practice) for development of WSS financing strategies in SSA. 5. Completed: Collaboration with donors in the partner country involved (Lesotho only) and in the framework of EUWI meetings. However, the envisaged collaboration with the WSP of the WB on the SWIFT methodology failed to materialise. 6. Not completed: Consultancies. |
| - Increased knowledge of finance mechanisms and policy tools for water-related development | - Meetings - Seminars - Workshops | - FWG meetings - Collaboration between FWG key partners e.g. WSP/ OECD /GWP others on capacity building - Consultancy contracts | - Completed: For the FWG annual meetings representatives from Lesotho (in 2008 and 2009) and from Mauritania (in 2008) were invited for knowledge-sharing and planning of country studies (the study in Mauritania was not implemented because of unforeseen political events in that country). For the 2008 meeting a Dutch NGO working on finance of sanitation and for the 2009 meeting representatives from a micro-credit company were also invited. - Completed: The FWG Chair played an active role in the OECD Member Led Task Force on Water Finance and participated in meetings in Paris in April and October 2008. The Task Force submitted its report to the WWF in Istanbul in March 2009. - Completed: A workshop in South Africa in March 2010, organised by the UNDP programme CapNet with participation of experts involved in the Lesotho country study, to design a training course on strategic financial planning for the WSS sector in African countries. - Completed: A consultancy to prepare a report on best practice for strategic financial planning for the WSS sector, “Strategic Financial Planning for Water and Sanitation in Africa: Rationale, Methodology, Experience, Lessons Learned”. - Completed: Five regional workshops on water finance held in collaboration with GWPO regional networks in West Africa, East Africa, EECCA, Central America and South America (financed mostly from the DFID direct contribution to FWG). |
| - Coordination and management of EUWI FWG. | - Management and coordination of FWG membership | - Secretariat established in GWP - FWG meetings - Chairmanship - Programme Administrator | 1. Completed: The EUWI FWG Secretariat was established through an MoU between DFID and GWPO and hosted by the GWPO in Stockholm, Sweden since 2006. The MoU was renewed in June 2009. 2. Completed: The annual meetings of the EUWI FWG were held during Stockholm World Water Week in August 2008 and 2009. At the latter meeting the FWG tentative work plan for 2009-2012 was approved. 3. Completed: FWG was managed by a Chair appointed with the consent of the stakeholders at the FWG annual meeting. The 2009 annual meeting agreed to appoint a new Chair for FWG from 1 December 2009. 4. Completed: The Chair was supported by a Programme Administrator, who was contracted by GWPO to work 80 per cent part time until 1 September 2009 when she left on extended maternity leave. Her replacement worked 60 per cent part time until she resigned in January 2010 whence the position was left vacant. |

# 3. DIFFICULTIES ENCOUNTERED & MEASSURES TAKEN

During implementation of the project the following difficulties were encountered:

  - Lack of a governance structure for FWG. In the original design of EUWI there were a total of seven working groups, four regional (Africa, Latin America, Mediterranean and EECCA) and three cross-cutting (for research, finance, and monitoring), reporting to a Steering Group (SG). The SG was composed of representatives from EU Member States, the Commission and civil society stakeholders and approved the annual work plans of the working groups.

After a few years there was an emerging perception that the SG was not effective in guiding EUWI, members said that “the SG does not steer anything”. One reason was that several working groups had been taken in hand by EU Member States which did not leave much room for the views of the SG: thus Spain took charge of the Latin American working group, Greece the Mediterranean working group, the Commission had the working group on research, and the Africa working group (AWG) was led by a troika of Member States. Another reason was that SG meetings were not seen to be effective. The EUWI review supported by DFID in 2006-2007 therefore recommended that the SG be replaced by a Coordination Group which would receive but not approve annual work plans from the working groups. This recommendation was implemented in the spring of 2007.

The transfer of FWG from DFID to GWPO from July 2006 meant that under this new EUWI organization there was no governance structure for FWG, the only working group not led by a Member State (or the Commission). The annual FWG meeting became the venue for decisions related to governance and management (such as approval of work plans and appointment of the FWG Chair), but it was not well suited for governance purposes. The lack of a governance structure created a situation where FWG did not have direct access to selected Member States and suffered a certain isolation.

  - Insufficient collaboration with the EUWI Africa Working Group. The absence of close involvement by Member States (other than the UK through DFID) in the FWG work impacted mostly on the region of most importance for FWG, Africa. In the spring of 2007, when the recommendations of the EUWI review were being considered by the Member States, the FWG Chair proposed that AWG and FWG be merged. However, this did not meet with the approval of the SG, where representatives from other regional working groups claimed to have financial issues in which they wanted the involvement of FWG. There was support in the SG for the FWG proposal, but since decisions were taken by consensus and some SG members were opposed, the proposal fell.

AWG and FWG held joint meetings, but the collaboration cannot be said to have been close. FWG had an item on the agenda for the AWG meetings, but attempts by FWG to collaborate closer together did not bear fruit. In hindsight, it was regrettable that a closer collaboration between FWG and AWG did not come about. The focus of the FWG project was on ACP countries and on Africa (although with DFID funding work was done also in countries outside ACP). The attempts by AWG to conduct policy dialogues in partner countries was seen to have largely failed and was, in principle, abandoned by AWG at its meeting in London in December 2008. If the country dialogues from the beginning had been conducted from the perspective of WSS sector finance, it is likely that they would have attracted more interest from African partners.

  - Failure to involve a second African country. The FWG project document specified that support would be extended to WSS financing strategies in two African countries. For the reasons outlined in section 3 of Progress Report # 2, not repeated here, it proved impossible to involve a French-speaking partner country, and the project therefore implemented only one country study (in Lesotho). As a result, the scope of the project was substantially reduced.

It is unlikely that inclusion of a second and French-speaking country would have changed the overall conclusions from the Lesotho project about the importance of strategic financial planning and the lessons learned from use of the FEASIBLE methodology. Still, the universal validity and legitimacy of project findings and conclusions would have been enhanced by inclusion of a country from the West Africa region.

  - Delay in completion of the Lesotho country study. A difficulty of a more technical nature related to the delays of completion of the Lesotho country study. The contract with the consultant was of a 12 month duration and expected to end around 1 October 2009. The consultant requested a no-cost extension by six months, in the event the contract was extended until 5 February 2010. Three reasons were cited for the delays, one relating to establishing accurate population estimates and definition of service areas for both urban and rural water supplies, another relating to delays in carrying out a survey of connections in urban water systems by the water utility, and the third was the delay in organizing training in the FEASIBLE methodology by the COWI consulting firm.

The government of Lesotho was of the view that extending the contract of the consultant was important in order to allow him to complete the country study in good order which would render greater reliability and validity to his findings and conclusions. The contract extension finally granted until 5 February 2010 allowed the consultant sufficient time to do this.

  - Project management constraints.  The difficulties of finding partners for the two envisaged country studies were clearly underestimated at the outset. This is because already in 2007, before the project started, strong expressions of interest in strategic financial planning studies had been received from Burkina Faso and from Ghana. In the event, it was not possible, for different reasons, to go forward in those two countries. The management input required to find a substitute for the second country,  to procure and appoint consultants for the Lesotho study, and to administer the project was such that there was little capacity left to work as inclusively as would have been desirable to promote an active working group.

# 4. CHANGES INTRODUCED IN THE IMPLEMENTATION

Timeline & expenditure curve changed

The deletion of the second country study, confirmed in Amendment No. 2 to the agreement  between the Commission and GWPO, meant a reduction of the estimated project cost from €740,000 to €413,126. The total project cost as per 31 March 2010 was €381,610, 52  per cent of the original budget and 92 per cent of the budget foreseen in Amendment # 2.

These figures, as well as those in Annex II, refer only to the project co-financed between the ACP-EU Water Facility and DFID. They do not include the contributions given by DFID in 2006 and in 2009, the latter of which is mentioned in section 7, point 1, below.

# 5. ACHIEVEMENTS/RESULTS

The results achieved by the project are discussed below in the light of the difficulties outlined in section 3 above.

1. PROVISION OF FINANCING EXPERTISE AT COUNTRY LEVEL

Activities: 
a) Technical assistance to develop country level WSS finance strategy

Expected output: 1) AWG/FWG meetings
There were frequent working level contacts between AWG and FWG, and mutual participation in meetings, but there were no significant joint actions or initiatives. In particular, the inability of EUWI AWG/FWG to initiate close collaboration with AMCOW was a disappointment. One reason was the inability of the AMCOW secretariat to plan and organize a joint meeting, one was planned for May 2009 but called off in the last minute;  it eventually took place in July 2009 with only AWG participation. But the underlying reason was likely that African partners had come to see EUWI as rather marginal in view of its failure to add value at country level.

Expected output: 2) Design, preparation & implementation of financing strategies in selected SSA countries.
The most significant contribution of the Lesotho country study was to demonstrate the importance of strategic financial planning in order to “ensure sustainable financing” of water sector interventions in Africa. Whether it could contribute to the “identification of additional financial resources” for the sector is more uncertain and can, in any event, only be assessed in the more long term. Still, it is likely that strategic financial planning, consistent with the findings and conclusions outlined in the final report (see Annex I), will be increasingly demanded by donors as a requirement for increased support to the WSS sector.

An important conclusion from the Lesotho country study relates to the applicability in SSA of the FEASIBLE methodology. It is important to recall that this methodology was originally developed for application in the countries of the former Soviet Union and Eastern Europe, and that one purpose of using it in the project was to test its applicability in Africa. The feasibility of application of  FEASIBLE in an African context was the subject of a technical workshop hosted by OECD in Paris in April 2007. Experts who had worked with FEASIBLE in different countries participated in the workshop, WSP was also represented.  The conclusion was that FWG should proceed with applying FEASIBLE.

However, the Lesotho study concluded that the FEASIBLE methodology was too technical and demanding in terms of data to be operationally useful under the conditions, usually characterized by shortages of accurate data, obtaining in Africa. The consultant recommended that it was preferable to adapt the FEASIBLE methodology to suit the local situation rather than using the generic approach. But he also found that the basic principles underlying FEASIBLE are sound and helpful in developing a financial strategy for the WSS sector. These principles provided the framework for the workshop in March 2010 that launched a process to design a training course on strategic financial planning for WSS.

Expected output: 3) Collaboration with EU MS / EC at country level

Status of output: In the Lesotho country study contacts were maintained by the consultant with representatives of EU MS and the EC Delegation as well as local stakeholder groups regarding progress of the financing strategy project. The EC Delegation was represented on the project steering committee.

Expected outputs: 4 Consultancy contracts
Status of output: Following a procurement process according to EC rules, a consultancy contract was signed with PEM consult s/a, Denmark, for the development of the WSS financing strategy in Lesotho. The contract has been invoiced and honoured in full. A procurement process was also launched for one of the French-speaking countries (Burkina Faso) but was cancelled since the country authorities at a late stage withdrew their support for the project (the reason has never been clearly explained but apparently related to a botched presentation of the country study at a key meeting in Ouagadougou of which the project had not been informed beforehand).

2. MAXIMISE OPPORTUNITIES FOR ACCESSING EU RESOURCES

Activities:
a) Develop guidance on approach, tools and methodologies to develop WSS finance strategies

b) Produce studies, analysis and reviews of financial resources in water sector to inform water sector practitioners.

c) Provision of ad hoc technical assistance

Expected output: 1) FWG membership

The FWG membership sensu strictu was the number of organizations represented at the FWG annual meetings, a total of around 25. These included EU Member States’ aid agencies, civil society organizations, and a few private sector representatives. Material produced for FWG could be accessed via the EUWI/FWG website. It is likely that actual interest in water finance is widespread and goes far beyond the participation in the FWG meetings, but no statistics were kept of visits to the website.

Mention of funding by the EU was made in all presentations made at FWG annual meetings and in final reports issued under the project. All progress reports and final reports from the Lesotho country study give visibility to the EU support.

Expected output 2) FWG meetings

The FWG annual meetings were held during the World Water Week in Stockholm in August 2008 and 2009, in each meeting with some 40 participants. Both meetings were held back-to-back with AWG meetings.

Expected output 3) Joint meetings (with key partners)

FWG has participated in a variety of meetings with EU MS, the Government of Lesotho, the World Bank, OECD members, and other partners to present its work programme and explained the purpose of the WSS financing strategies and the application of the FEASIBLE methodology.

Expected output 4) Collaboration between FWG key partners e.g. WSP/ OECD /GWP on best practice

There has throughout been close collaboration with OECD on tools and methodologies (best practice) for development of WSS financing strategies with particular emphasis on application of the FEASIBLE methodology. OECD was actively involved in the (ultimately abortive) efforts to launch a study in a French-speaking country.

Expected output 5) Collaboration with Donors / IFIs

In 2007 there were close working contact with the World Bank-supported Water & Sanitation Programme (WSP) regarding WSS financing strategies and on the SWIFT methodology developed by the WSP. However, in 2008 those contacts tapered off. In agreement with the consultants working in Lesotho it was decided to drop from that country study any attempt to apply SWIFT.  The reasons were that  SWIFT is a partial model that covers only water services and not sanitation, that it is tailored to conditions in Kenya, and that WSP itself had stopped developing the tool.

Expected output 6) Consultancy contracts

No consultancy was carried out under this heading.

3. INCREASED KNOWLEDGE OF FINANCE MECHANISMS & POLICY TOOLS

Activities:
a) Meetings

b) Seminars

c) Workshops

Expected output 1) FWG meetings

The FWG meetings have already been covered.

Expected output 2) Collaboration between FWG key partners (WSP/OECD/GWP) on capacity building

At the outset it was planned to organize two workshops on strategic financial planning in the WSS sector, one in English and one in French, to review and disseminate experiences from the country studies. Since only one country study was carried out, this plan was modified, as reflected in Amendment # 2.  It was decided to design a training activity with help from the UNDP project CapNet with which FWG has previously collaborated, and a small workshop was held by CapNet in South Africa in March 2010 with participation of experts involved in the Lesotho study and others.

This workshop was judged by CapNet and by participants to have been successful. It decided on the structure and content of a training manual to support future training activities on strategic financial planning for WSS. Preparation of this manual will require further work which will be supported by CapNet. The target group for the envisaged training would be officials in finance ministries, water ministries, government agencies, SWAp coordination committee members, representatives of water utilities, NGOs and academia concerned with strategic financial planning of WSS. Actual training would commence in the second half of 2010, provided that financial support could be found. One possibility would be to use DFID support to the FWG for this purpose. 

The demand from the GWP regional networks for water finance workshops is considerable and exceeds the financial and human resources available. These workshops aim to bring together water practitioners with finance experts with a view to raising the level of awareness of the former of financial issues, techniques and opportunities. Two were held in 2007 (in Ouagadougou and Nairobi) and one in early 2008 (in Tbilisi), all were judged to have been successful. The Nairobi workshop included participation of five ministers from East Africa and led to the so-called Nairobi Accord. This was presented by one of the ministers to the AMCOW EXCO meeting in Brazzaville and subsequently fed into the AU process leading to the Sharm el Sheikh Declaration which includes a specific section on financing WSS.

In 2009 two workshops in Latin America were designed, planned and implemented, one in Guatemala in July 2009 and the other in Colombia in October 2009, both were highly appreciated by participants. All of these workshops have been financed from the DFID support to the FWG (with co-finance from GWPO).

Demand for similar events is high and the African Water Facility has expressed interest in building on this initiative. FWG will proceed with three similar workshops in 2010 in collaboration with GWPO.

Expected output 3) Consultancy contracts

When the Lesotho country study was nearing completion a consultancy was initiated under the project to synthesize experiences from strategic financial planning under EUWI with a focus on its application in Africa. The paper builds on experiences from similar projects in not only Lesotho but also Egypt (under the EUWI Mediterranean working group) and the Kyrgyz Republic (the EECCA working group). It provides a useful overview of the rationale for strategic financial planning, the use of FEASIBLE, and the experiences from these three country studies. It will be published in 2010 by GWPO.

4. COORDINATION AND MANAGEMENT OF EUWI FWG

Activities: Management and coordination of FWG membership

Expected output 1) Secretariat established in GWPO

The FWG Secretariat has been hosted by the GWPO in Stockholm, Sweden, since 2006 based on a MoU between GWPO and DFID. The MoU was renewed and will secure hosting arrangements for the FWG through May 2012. This will ensure that the FWG project is followed up, and that conclusions and recommendations from the Lesotho country study are acted upon.

There were several benefits to FWG from being hosted in this manner. GWPO provided financial management, auditing and personnel administration (contracting the Chair and the part time Programme Officer), it assisted in the procurement of consultants, and the GWP regional partnerships worked with FWG to organize the financing workshops.

Expected output 2) FWG meetings

These meetings were held as scheduled. On both occasions there were useful and constructive discussions about issues related to finance of the WSS sector. The 2009 meeting included a session on micro-credit for WSS which was later followed up with USAID with a view to exploring possible collaboration, as of April 2010 the dialogue with USAID was still continuing. At the meetings the FWG work plans were also discussed and approved. However, because of the capacity constraints of the project secretariat, referred to in section 3 above, and also because of lack of flexibility within the project budget, it was not possible to use these meetings proactively to discuss and launch new initiatives.

Expected output 3) Chairmanship

The FWG Chair has been appointed with the consent of participants at the FWG annual meetings. At the annual meeting in August 2009 the Chair expressed his wish to resign from the FWG. He nominated a replacement who was approved by the meeting and by DFID. The new Chair is contracted by GWPO, is not concerned with the ACP-EU Water Facility project, and his costs are covered entirely from the DFID contribution. To ensure continuity, the former Chair, also contracted by GWPO, remained as Project Manager until the close of the project at the end of March 2010.

Expected output 4) Programme Administrator

The Chair has been supported by a Programme Administrator, contracted by GWPO, who was working 80 per cent part time until she went on maternity leave in September. Her replacement worked 60 per cent part time until January 2010 when she resigned from GWPO. Her position has since then remained vacant.

# 6. COMMENTS ON FINANCIAL EXPENDITURE REPORT

A financial expenditure report for the project is attached at Annex II. As shown, the total project cost is €378,609 broken down over the project period as follows:

| Year | Cost (€) |
| --- | --- |
| 2008 (Year 1) | 156,431 |
| 2009 (Year 2) | 161,803 |
| 2010, first quarter (Year 3) | 63,376 |
| Total | 381,610 |

The table below breaks down the total cost in three principal costs categories:

| Cost category | Cost (€) | Per cent |
| --- | --- | --- |
| Project secretariat (Chair and Programme Officer) | 123,614 | 32 |
| Lesotho country study | 193,320 | 51 |
| Operating the FWG | 64,676 | 17 |
| Total | 381,610 | 100 |

Costs under the category “operating the FWG” include all travel and related costs, the FWG annual meetings, one consultancy, the workshop in March 2010, office costs, and administrative overhead costs. As the table shows, those costs are a small part of the total.

All costs are within budget with two small exceptions, €10 for the Programme Administrator (budget line 1.1.2) and €92 for Secretariat travel Europe to Africa (budget line 2.1). Those cost items were within budget in Euros but since actual payments were made in SEK the differentials are explained by currency fluctuations.

The FWG accounts have been perused and approved by the GWPO auditors for each year of the project.

# 7. RESULTS ANALYSIS – ADDITIONAL COMMENTS

The presentation of achieved results in section 5 above should be supplemented with some additional comments on subjects not known when the project document was prepared in 2007 or at least not made explicit in that document.

1. Continuation of DFID support to FWG. In June 2009 GWPO and DFID signed a new MoU for continued support to FWG. This support extends for three years, i.e. until May 2012, and provides GBP450,000, or GBP150,000 per year, to FWG. The activities to be carried out with this support were listed in Progress Report # 2.

This means that there will be good possibilities to follow up the FWG project now concluded. It will be possible to continue promoting strategic financial planning in general within EUWI and, in particular, within the auspices of collaboration with AWG, hopefully closer in the future. Specifically, it should be possible to support the training activities to be carried out by CapNet in this area. The DFID support will provide valuable continuity to the now concluded project.

2. Possibility to promote strategic financial planning in other partner countries. During the course of the project several African partner countries expressed interest in support for strategic financial planning of WSS. For example, at the 2nd Africa Water Week African ministers expressed interest in this approach which they considered would be useful in helping satisfy Paris Declaration requirements.

The continued DFID support will not suffice to support country studies similar to that carried out in Lesotho, but FWG could act as a broker with EU Member States which may be disposed to support such studies in African countries. This could be an area for collaboration between AWG and FWG.

3.  Training in water finance and strategic financial planning. One of the activities to be covered by the DFID support to FWG during 2009 – 2012 is training. There have been good experiences from the workshops carried out during 2007 – 2009 in collaboration with the GWP regional networks, there is much interest in providing water practitioners, typically engineers, with some first knowledge of finance related to the WSS sector.

CapNet considers strategic financial planning a priority in its work programme and will develop the conclusions from the workshop in March 2010 into a training course in a format similar to the workshops carried out by FWG and GWPO, typically of a duration of one week. CapNet will use its own funds or seek funding from other sources to carry out such workshops, but they could also be supported by FWG using the resources provided by DFID.

4. Conclusions about the FEASIBLE methodology. The FEASIBLE methodology was developed for use in Eastern Europe and the countries of the former Soviet Union. The rationale for the involvement of OECD in the FWG project was to test this methodology under African conditions. As said above, the conclusion from the Lesotho country study on this matter is clear. On the one hand, this methodology is too demanding in terms of data to be applied at full scale in most African countries, where data shortages are more prevalent than in the countries for which it was originally designed. The final report from the study (Annex I) therefore emphasizes a purpose-built methodology over the more generic FEASIBLE approach.

But on the other hand, FEASIBLE creates an analytical framework which is useful and fully relevant under African conditions and which should be the basis for promoting strategic financial planning with African partners. The underlying methodology provides a sound basis for strategic financial planning, provided that it is adapted to suit local conditions.

5.  Results for the Government of Lesotho. The benefits from the country studies on strategic financial planning for host governments were not explicitly discussed in the project document, although they are substantial. The Government of Lesotho has throughout been very supportive of the country study and appreciated the added value it could generate for the WSS sector.

The outcomes of the Lesotho study have made important contributions to the preparation of a two-year interim sector strategy to define priorities for the coming years and serve as a basis for budget support from the sector from the EC. The Government is deliberating the four scenarios highlighted by the study (Annex I, section 2.2) with a view to selecting one, or perhaps a compromise scenario, that could serve as a basis for a submission to the Ministry of Finance & Development Planning.  The Government would then have a better overview of financial requirements to achieve MDG targets and Vision 2020 and be able to allocate funds accordingly.

The projects identified by the study (Annex I, Annex B) have been incorporated in the Government’s interim sector strategy as priorities for implementation. The strategy has been generally accepted as an important tool to guide future planning of the sector.

The SWAp for the water sector is not yet finalised. But the study has made an important contribution by strengthening coordination within the sector and, in particular, by harmonising water-related data from the Department of Statistics. As a result, the Ministry of Natural Resources is now in a much better position to conduct dialogues about its financial needs with donors and with the Ministry of Finance & Development Planning.

Finally, there have been important capacity building outcomes, as Basutho technical personnel have learned not only to conduct a comprehensive strategic financial planning exercise but also to understand strengths and weaknesses of the FEASIBLE methodology

Naturally, all regional working groups had financial issues. However, no approaches were ever made by them to FWG.

This activity was co-financed with OECD which paid the COWI consultant’s fees while the project paid for his travel and subsistence for a one-week course in Lesotho.

In connection with an EUWI AWG meeting in Ouagadougou in April 2007

The two quotations derive from the fifth EUWI objective which in the LogFrame for the FWG project was stated as the overall objective.

This workshop is mentioned on page 9 of the project document of the ACP-EU Water Facility project.