5
4

2005-05-04
EUWI EU WATER INITIATIVE

STEERING GROUP PAPER No.2005/008: 2005 Work Programme and Budget

1. The EUWI 2005 Work Programme, by Working Group 

	Working Group
	Activities
	Targets/Purpose 

per Activity
	Duration/Comple-

tion Date

	Africa WSS
	Update the work plan 2005
	* Updated work plan

* Updated WG      membership

* Troika active
	Ready by February 2005

	
	Prepare concept notes for generic use in the country dialogue process
	* National policy dialogues (ToR)

* Road mapping

* MSF

* Financial planning

* Capacity building
	Gradually over the year

	
	Organize  WG meetings, attend WG meetings and secure cross-WG linkages
	* 5 WG meetings

* One or two in Africa

* Combined with FWG and IWRM WG
	Spread over the year

	
	Policy dialogue process
	* Start in 10 countries, selected by AMCOW

* Supported by the roving ambassador

* Get possibly more MS involved
	Over the year:

* Continue with Zambia and Ghana

* Start with Mozambique, Ethiopia and Cap Verde

* Prepare the other five processes

	Finance
	Finalise Phase 2 report
	Internal review by FWG members of draft report and finalise
	8 months/February 2005

	
	Post final report
	Final report posted on EUWI web site with fully searchable and interactive platform and possibility of web based chatroom to discuss relevant issues
	3 months/March 2005

	
	Design of financial element of country dialogues
	Working with the Africa WSS WG in country dialogues to provide a basis for financial analysis of the sector in each country
	Long term, different elements will be completed throughout 2005 and 2006

	
	Working with EECCA and MED WGs
	Joint meetings and sharing of knowledge to support other regional WGs
	2005

	Africa IWRM
	Follow up implementa-

tion of the action plans in the five selected TB basins
	* Ensure requests from RECs to EC delegations

* Follow up consultation process in each sub-region

* Continue dialogue with RBOs about action plans
	Requests from RECs received by May 2005, consultation and dialogue to continue through 2005

	
	Coordinate activities with the Africa WSS WG
	Agreement on joint activities 
	June 2005

	
	Review status of IWRM national plans in African countries
	Review complete by next WG meeting
	August 2005

	
	Support preparation of IWRM national plans in coordination with other EUWI components
	Preparation to start in a number of countries yet to be determined
	End of 2005

	EECCA
	Develop a work program-

me for the further development of the component, based on existing studies and analyses
	Decision by the EECCA WG - HLM
	WG meeting 29 March 2005

	
	First identification of priority actions to implement the work programme to be backed by financing strategy
	Decision by the EECCA WG -HLM
	WG meeting in October 2005

	
	Initiate action phase towards the development of national action plans and policy dialogues to achieve the MDGs in  the EECCA region
	Work started in EECCA countries involved
	End of 2005

	Research
	WG meetings, consolida-

tion of interfaces with stakeholders, reporting
	One planning session of WG, one review session and one public informa-

tion session; dialogue with all major stakehol-

ders; information and progress reports submitted
	WG sessions in January, June and August 2005; dialogues through Sept. 2005; reporting after each WG session.

	
	Interface with other EUWI WGs
	Joint identification of communication modali-

ties, priority research needs, key actors, and mutual action with all WGs
	Throughout 2005

	
	Promotion of access to information, awareness, better knowledge mana-

gement, and RTD funding
	Access to research results facilitated; demand driven approaches to knowledge exchanges promoted; access to training and research funding promoted; information dissemina-

tion strengthened
	Throughout 2005

	CIS and other cross-cutting functions
	Administration and main-tenance of CIS-Net
	* Use of CIS expanded

* EUWI information materials produced
	Throughout 2005

	
	Coordination of EUWI/

Secretariat activities
	* Preparation of SG meetings

* Other meetings facilitated

* Support to WGs provided, as needed
	Throughout 2005

	
	Stockholm events to be coordinated by the Secretariat
	Organization of a MSF meeting and specific related sessions, incl. possible WG meetings
	August 2005

	Mediterranean
	Consolidate and standar-

dise organisational set up; standardise WG member-

ship and modalities; screen possibilities for political platform/process to carry the MED EUWI forward
	* Preparation of WG meetings
* Strengthen linkages of the MED EUWI with ongoing regional processes (e.g. the Euro-

Med)
	Throughout 2005 with emphasis on the first semester

	
	Concretise MED EUWI Activity Plan with specific priority activities/interventions on regional and national levels
	* Carry out priority background assessments
* Organize sub-regional meeting on IWRM status

* Organize regional meeting on long term financing

* Kick off “country dialogues” process

* Run capacity building programme on shared waters in SE Europe

* Consolidate matching funds and activities from other donors and partners

* Explore funding possibilities for further action
	Throughout 2005

	
	Promote awareness; raise involvement of EU and partner countries; sensi-
tise and attract new donors
	* Carry out specific communication activities/
communication  strategy

* Organize donor meeting(s)

* Streamline ways, possibilities and fields of donors’ and other partners’ involvement
	Throughout 2005

	Latin America
	Meeting in Madrid with LA water directors to explore interest in forming a WG
	Meeting held 
	March 2005

	
	Constitute WG based on ToR prepared by the Secretariat in Madrid
	ToR for WG approved at meeting in Cartagena, Colombia
	June 2005

	
	Survey of donor practices regarding water in LA
	Draft survey report reviewed by the WG in June 
	August 2005

	
	Review situation in LA with regard to IWRM national plans and water legislation
	Review complete and approved by the WG
	October 2005

	
	Organize preparations for the 4WWF in Mexico in 2006


	Preparations complete as per guidelines from the WWC
	Until end of 2005

	Monitoring and reporting
	Design and discuss a model for policy analysis and monitoring
	Outline of methodology complete
	January - March 2005

	
	Select case studies and discuss these with EUWI WGs
	Participate in EUWI WG meetings
	January – March 2005

	
	Test the methodology on case studies from the EUWI WGs
	Conclusions on viability of methodology
	May – July 2005

	
	Review the methodology and analyse existing information gaps
	Information gaps identified
	August – September 2005

	
	Select three countries or basins and collect data on the current status and performance in them
	Data collected
	October – December 2005

	
	Prepare version 0 of the “progress report”
	Progress report with early indicators of case studies prepared
	December 2005

	
	Organize WG meetings
	Three WG meetings held 
	January, April and August


2. Summary of the 2005 Budget by Working Group 
	Working Group
	Total

Cost (€)
	Of which

Funded (€)
	Residual

(€)
	Comments/Explanations

	Africa WSS
	700,000
	143,000
	557,000
	Of the residual €518,000 refers to costs for the ten country dialogues assumed to be covered by the lead MS in each country, remainder covered by the Netherlands.

	Finance
	240,000
	180,000
	60,000
	Most of the residual (€50,000) refers to consultants, other costs covered by the UK.

	Africa IWRM
	244,000
	244,000
	
	Cost estimate provided for the October 2004 SG meeting, costs covered by France

	EECCA
	294,700
	294,700
	
	Of which €199,999 for consultants; cost estimate provided for Oct. SG meeting, costs covered by the EC 

	Research
	250,000
	195,000
	55,000
	Includes €160,000 for IWRM review study funded by the EC, DG/RTD. Residual to be covered by the MS represented in the WG 

	Mediterranean
	250,000
	250,000
	
	Information provided for October 2004 SG meeting, costs covered by Greece.

	Latin America
	220,000
	220,000
	
	Budget allocation by Spain, excluding any contribution that may come from Portugal

	Monitoring and reporting
	450,000
	142,000
	308,000
	Costs covered by Italy. Residual not funded as of April 2005.

	Cross-cutting activities:
a. CIS
	297,600 (CIS only) 

+ 108,000
	297,600
	108,000
	CIS budget covered by Austria, of which €240,000 for consultants. There is an option for CIS enhancement, including translation of full CIS into three languages, at a cost of €108,000; this is not yet funded. 

	b. The EUWI Secretariat
	
	
	
	The EUWI Secretariat involves 6-8 staff working part time and is funded by the EC, including three ENDs

	c. Stockholm events
	Subsidy of EUWI related events 250,000
	
	
	Funding secured, mostly from Sweden


Summary of 2005 costs (indicative only):
* Gross estimated costs of all Working Groups and other EUWI components - € 3.3 million

* Funded by EU MS - €2.2 million

* Unfunded residual as of April 2005 - €1.1 million
At the meeting of the Steering Group on 18 January 2005 a presentation was made of the 2005 Work Programme and Budget. The presentation was incomplete, and the Secretariat was requested to provide a finalised version for endorsement at the next SG meeting.





A complete summary of the 2005 Work Programme by Working Group is shown below,


followed by a table showing estimated costs in 2005 for each Working Group. The information provided in January has been updated through contacts with the Working Group chairs.








