2005-05-04

EUWI EU WATER INITIATIVE

STEERING GROUP PAPER No.2005/008: 2005 Work Programme and Budget

At the meeting of the Steering Group on 18 January 2005 a presentation was made of the 2005 Work Programme and Budget. The presentation was incomplete, and the Secretariat was requested to provide a finalised version for endorsement at the next SG meeting.

A complete summary of the 2005 Work Programme by Working Group is shown below,

followed by a table showing estimated costs in 2005 for each Working Group. The information provided in January has been updated through contacts with the Working Group chairs.

1. The EUWI 2005 Work Programme, by Working Group

| Working Group | Activities | Targets/Purpose per Activity | Duration/Comple- tion Date |
| --- | --- | --- | --- |
| Africa WSS | Update the work plan 2005 | * Updated work plan * Updated WG membership * Troika active | Ready by February 2005 |
|  | Prepare concept notes for generic use in the country dialogue process | * National policy dialogues (ToR) * Road mapping * MSF * Financial planning * Capacity building | Gradually over the year |
|  | Organize WG meetings, attend WG meetings and secure cross-WG linkages | * 5 WG meetings * One or two in Africa * Combined with FWG and IWRM WG | Spread over the year |
|  | Policy dialogue process | * Start in 10 countries, selected by AMCOW * Supported by the roving ambassador * Get possibly more MS involved | Over the year: * Continue with Zambia and Ghana * Start with Mozambique, Ethiopia and Cap Verde * Prepare the other five processes |
| Finance | Finalise Phase 2 report | Internal review by FWG members of draft report and finalise | 8 months/February 2005 |
|  | Post final report | Final report posted on EUWI web site with fully searchable and interactive platform and possibility of web based chatroom to discuss relevant issues | 3 months/March 2005 |
|  | Design of financial element of country dialogues | Working with the Africa WSS WG in country dialogues to provide a basis for financial analysis of the sector in each country | Long term, different elements will be completed throughout 2005 and 2006 |
|  | Working with EECCA and MED WGs | Joint meetings and sharing of knowledge to support other regional WGs | 2005 |
| Africa IWRM | Follow up implementa- tion of the action plans in the five selected TB basins | * Ensure requests from RECs to EC delegations * Follow up consultation process in each sub-region * Continue dialogue with RBOs about action plans | Requests from RECs received by May 2005, consultation and dialogue to continue through 2005 |
|  | Coordinate activities with the Africa WSS WG | Agreement on joint activities | June 2005 |
|  | Review status of IWRM national plans in African countries | Review complete by next WG meeting | August 2005 |
|  | Support preparation of IWRM national plans in coordination with other EUWI components | Preparation to start in a number of countries yet to be determined | End of 2005 |
| EECCA | Develop a work program- me for the further development of the component, based on existing studies and analyses | Decision by the EECCA WG - HLM | WG meeting 29 March 2005 |
|  | First identification of priority actions to implement the work programme to be backed by financing strategy | Decision by the EECCA WG -HLM | WG meeting in October 2005 |
|  | Initiate action phase towards the development of national action plans and policy dialogues to achieve the MDGs in the EECCA region | Work started in EECCA countries involved | End of 2005 |
| Research | WG meetings, consolida- tion of interfaces with stakeholders, reporting | One planning session of WG, one review session and one public informa- tion session; dialogue with all major stakehol- ders; information and progress reports submitted | WG sessions in January, June and August 2005; dialogues through Sept. 2005; reporting after each WG session. |
|  | Interface with other EUWI WGs | Joint identification of communication modali- ties, priority research needs, key actors, and mutual action with all WGs | Throughout 2005 |
|  | Promotion of access to information, awareness, better knowledge mana- gement, and RTD funding | Access to research results facilitated; demand driven approaches to knowledge exchanges promoted; access to training and research funding promoted; information dissemina- tion strengthened | Throughout 2005 |
| CIS and other cross-cutting functions | Administration and main-tenance of CIS-Net | * Use of CIS expanded * EUWI information materials produced | Throughout 2005 |
|  | Coordination of EUWI/ Secretariat activities | * Preparation of SG meetings * Other meetings facilitated * Support to WGs provided, as needed | Throughout 2005 |
|  | Stockholm events to be coordinated by the Secretariat | Organization of a MSF meeting and specific related sessions, incl. possible WG meetings | August 2005 |
| Mediterranean | Consolidate and standar- dise organisational set up; standardise WG member- ship and modalities; screen possibilities for political platform/process to carry the MED EUWI forward | * Preparation of WG meetings * Strengthen linkages of the MED EUWI with ongoing regional processes (e.g. the Euro- Med) | Throughout 2005 with emphasis on the first semester |
|  | Concretise MED EUWI Activity Plan with specific priority activities/interventions on regional and national levels | * Carry out priority background assessments * Organize sub-regional meeting on IWRM status * Organize regional meeting on long term financing * Kick off “country dialogues” process * Run capacity building programme on shared waters in SE Europe * Consolidate matching funds and activities from other donors and partners * Explore funding possibilities for further action | Throughout 2005 |
|  | Promote awareness; raise involvement of EU and partner countries; sensi- tise and attract new donors | * Carry out specific communication activities/ communication strategy * Organize donor meeting(s) * Streamline ways, possibilities and fields of donors’ and other partners’ involvement | Throughout 2005 |
| Latin America | Meeting in Madrid with LA water directors to explore interest in forming a WG | Meeting held | March 2005 |
|  | Constitute WG based on ToR prepared by the Secretariat in Madrid | ToR for WG approved at meeting in Cartagena, Colombia | June 2005 |
|  | Survey of donor practices regarding water in LA | Draft survey report reviewed by the WG in June | August 2005 |
|  | Review situation in LA with regard to IWRM national plans and water legislation | Review complete and approved by the WG | October 2005 |
|  | Organize preparations for the 4WWF in Mexico in 2006 | Preparations complete as per guidelines from the WWC | Until end of 2005 |
| Monitoring and reporting | Design and discuss a model for policy analysis and monitoring | Outline of methodology complete | January - March 2005 |
|  | Select case studies and discuss these with EUWI WGs | Participate in EUWI WG meetings | January – March 2005 |
|  | Test the methodology on case studies from the EUWI WGs | Conclusions on viability of methodology | May – July 2005 |
|  | Review the methodology and analyse existing information gaps | Information gaps identified | August – September 2005 |
|  | Select three countries or basins and collect data on the current status and performance in them | Data collected | October – December 2005 |
|  | Prepare version 0 of the “progress report” | Progress report with early indicators of case studies prepared | December 2005 |
|  | Organize WG meetings | Three WG meetings held | January, April and August |

2. Summary of the 2005 Budget by Working Group

| Working Group | Total Cost (€) | Of which Funded (€) | Residual (€) | Comments/Explanations |
| --- | --- | --- | --- | --- |
| Africa WSS | 700,000 | 143,000 | 557,000 | Of the residual €518,000 refers to costs for the ten country dialogues assumed to be covered by the lead MS in each country, remainder covered by the Netherlands. |
| Finance | 240,000 | 180,000 | 60,000 | Most of the residual (€50,000) refers to consultants, other costs covered by the UK. |
| Africa IWRM | 244,000 | 244,000 |  | Cost estimate provided for the October 2004 SG meeting, costs covered by France |
| EECCA | 294,700 | 294,700 |  | Of which €199,999 for consultants; cost estimate provided for Oct. SG meeting, costs covered by the EC |
| Research | 250,000 | 195,000 | 55,000 | Includes €160,000 for IWRM review study funded by the EC, DG/RTD. Residual to be covered by the MS represented in the WG |
| Mediterranean | 250,000 | 250,000 |  | Information provided for October 2004 SG meeting, costs covered by Greece. |
| Latin America | 220,000 | 220,000 |  | Budget allocation by Spain, excluding any contribution that may come from Portugal |
| Monitoring and reporting | 450,000 | 142,000 | 308,000 | Costs covered by Italy. Residual not funded as of April 2005. |
| Cross-cutting activities: a. CIS | 297,600 (CIS only) + 108,000 | 297,600 | 108,000 | CIS budget covered by Austria, of which €240,000 for consultants. There is an option for CIS enhancement, including translation of full CIS into three languages, at a cost of €108,000; this is not yet funded. |
| b. The EUWI Secretariat |  |  |  | The EUWI Secretariat involves 6-8 staff working part time and is funded by the EC, including three ENDs |
| c. Stockholm events | Subsidy of EUWI related events 250,000 |  |  | Funding secured, mostly from Sweden |

Summary of 2005 costs (indicative only):

* Gross estimated costs of all Working Groups and other EUWI components - € 3.3 million

* Funded by EU MS - €2.2 million

* Unfunded residual as of April 2005 - €1.1 million