EU WATER INITIATIVE

WORK PROGRAMME 2006 to 2008

FINANCE WORKING GROUP

| Activities | Expected output per activity | Duration/completion date | Working Group objective no. | Cost (€’000) Cost (€’000) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Operation of the FWG (EUWI obj 3) |  |  |  | 2006 | 2007 | 2008 |
| - Meetings of the FWG including meeting cost of developing country attendees. | 3 FWG meeings p.a. with one being in a developing country | Continuous throughout period. | FWG obj 1 To facilitate discussion between key stakholders on work of the FWG | 50 | 70 | 80 |
| - Attendance at SG meetings. | Better under understanding of progress of overall EUWF activities to enable improved planning for future FWG activities. | As above | FWG obj 1 To ensure that FWG continues to provide appropriate inputs to EUWF | 1 | 1 | 1 |
| - Attendance at other EUWI Working Group meetings. | Dissemination of what FWG has to offer and improved understanding of needs of other groups | As above. | FWG obj 1 To ensure work of FWG ties in with needs of other groups and is demand led | 2 | 2 | 2 |
| - Consultancy to provide Secretariat Services to FWG | Day-to day management of the FWG activities and contact point for FWG. | As above | FWG obj 1 Provide an officient service with quick response times | 70 | 80 | 90 |
| To provide financing expertise at country level in response to requests (EUWI objs 1 & 5) |  |  |  |  |  |  |
| - Development of SWIFT investment planning model in Mozambiqe | An operational interactive tool that will help decision makers consider options for investment in the WSS sector | Inputs by FWG should be completed in 2006 | FWG objs 2 & 3 To be able to make available an interactive financing model to assist governments allocate funding in WSS sector with specific reference to the needs of Mozambique in the first instance | 75 | 0 | 0 |
| - Seminars on potential application of model in other WSS Africa Group target countries | More efficient and comprehensive examination of investment options leading to better use of available funds for investment and maintenance. | One Seminar per year in different regions. | FWG objs 2 & 3 To advertise the availability of the model and to enable decisions makers to assess application to their needs. | 30 | 40 | 50 |
| - Assistance with the application of model in interested target countries | As above | Demand led, but estimate inputs to one/two country per year. | FWG obj s 2 & 3 To help with the calibration and use of the model where requested to do so by Country Dialogue Groups | 50 | 60 | 70 |
| - Assistance to Government of Ethiopia in the development of their financial planning for the sector | An operational sector investment plan for the WSS sector in Ethiopia. | Inputs by FWG should be completed in 2006 | FWG obj s 2 & 3 The FWG has a specific request from both the Government and the Country Dialogue Group for specific assistance | 25 | 40 | 0 |
| - Assistance with the development of a national financing planning strategy for WSS in Moldova | An operational National Planning Strategy | As above | FWG obj s 2 & 3 The FWG has a specific request from the Government to help in the development of a finance plan for the sector with specific reference to the application of teh FEASIBLE planning model | 75 | 0 | 0 |
| - Seminars elsewhere in EECCA region on approach developed in Moldova and Aremenia | .Improved planning for investment in the WSS sector in the EECA region | One seminar per year over the period. | FWG obj s 2 & 3 To make other countries in the EECCA region aware of the approach adopted in Moldova and its possible application for them | 25 | 30 | 35 |
| - Assistance to other EECCA countries as required to develop similiar finance planning strategies | As above | Demand led, but estimate inputs to one country per year. | FWG obj s 2 & 3 To provide specialist financial expertise to assist in the adaptation and use of approaches developed in Moldova and Aremenia | 25 | 30 | 35 |
| - Provision of general ad-hoc inputs in finance sector to country dialogue groups as requested | As above | As above | FWG obj s 2 & 3 To provide a general, demand led advisory service on water financing issues | 10 | 15 | 20 |
| Make available web based tool to help interested parties identify potential funding sources in the WSS Sector (EUWI objs 3 & 5) |  |  |  |  |  |  |
| - Continued development of interactive web-site on financing options | To take forward work done to date to a stage when the basic website can go live | Work should be completed during first half of 2006. | FWG objs 2 & 3: An operational, interactive website on funding sources for WSS sector. | 10 | 0 | 0 |
| - Funding of contract with appropriate organisation for the ongoing development and maintance of the website | An improved web-site which is actively managed to meet needs. | Continuous throughout period once web-site goes live in 2006. | FWG obj s 2 & 3: To develop and expand the website to better meet the needs of developing country practitioners and to undertake day-to-day.management. | 200 | 150 | 100 |
| - Seminars to publicise the website and demonstrate its application | Increased knowledge by developing country practitioners of potential funding support for WSS sector. | One seminar per year in different geographic regions. | FWG obj s 2 & 3: To highlight availability of website to developing country practitioners and to improve understanding of its potential application. | 20 | 20 | 20 |
| - Prepare hard copy of key website information plus annual updates | As above | Main work in 2006, followed by annual updates. | FWG obj s 2 & 3: To make information available to potential users who do not have access to the internet. | 10 | 5 | 5 |
| Help maximise opportunities for accessing EU resources available for support to countries in the WSS sector (EUWI obj 5) |  |  |  |  |  |  |
| - Continued laision with EUWF Team | Improved mutual understanding of objectives and needs | Continuos throughout period. | FWG obj 4: To assist in increasing non-ODA inputs in support of projects | 1 | 1 | 1 |
| - Develop closer working relationship with Water Unit in DG Dev | As above | As above | FWG obj 4: To help maximise benefits of available funding to help achieve WSS MDGs | 1 | 1 | 1 |
| - Develop closer working relatioship with EIB | As above | As above | As above | 1 | 1 | 1 |
| - Develop closer working relationship wiht TACIS team | As above | As above | As above | 1 | 1 | 1 |
| - Develop closer working relationship with PPC/EAP Task Force | As above | As above | As above | 1 | 1 | 1 |
| - Develop closer working relationship with EBRD | As above | As above | As above | 0 | 0 | 0 |
|  |  |  | Total Annual Cost | 683 | 548 | 513 |

Budget (€):						Working Group objectives:

(summarize as numbered bullets in the box below)

1.To consult widely with stakeholders to ensure that FWG is making real contribution..

2. To provide support in the financing sector to Country Dialogue Groups and governments on demand led basis.

3.To develop tools to enable decission makers to compare investment options quickly and efficiently and to disseminate the availability of these tools.

4. To liase closely with the various EU organisations and facilities providing finance to the WSS sector to help maximise benefits and the achievement of the MDGs

|  | 2006 | 2007 | 2008 |
| --- | --- | --- | --- |
| Total cost (Euro’000) | 683 | 548 | 513 |
| Of which funded | 200 | 200 | 150 |
| Residual | 483 | 348 | 363 |