SPLASH Update to the EUWI coordination group - November 2008

SPLASH is the name of the EUWI Eranet, and is a consortium of 16 ministries, funding agencies and national research and technological development agencies from 11 European countries. The initiative aims to improve water research for poverty reduction and thus contribute to the achievement of the Millennium Development Goals(MDGs). It will:

- Coordinate existing programmes to minimize duplication and identify gaps;

- Support the transfer of research into policy and practice;

- Map good research management to maximize use of resources;

- Design collaborative research programmes which address identified needs.

Overall Progress and plans for the future:

SPLASH conducted a 3 day workshop in Bonn in October 2008, during which all work packages presented their respective findings. This resulted in: a summary of lessons learned to date; a series of recommended actions and a draft action plan to address some of these. SPLASH is currently developing a series of 12 concept notes to take forwards these findings and actions as potential components of the workplan for the future. These will be reviewed with stakeholders in December 2008, presented to donors for funding decisions in January 2009. Work plans for the period 2009 and 2010 will then be developed collaboratively with SPLASH partners in February 2009.

1. Coordination As a first step towards improved coordination, SPLASH mapped the existing nationally funded programmes in water research in Developing Countries. A database of results from this mapping can be accessed through the SPLASH website. There it is possible to search for programme information by theme, donor, region or country. See: http://www.splash-era.net/outputs/index.php

This shows that SPLASH partners are supporting research activity extensively in the Mekong and East African

regions. Moving forwards, SPLASH aims to facilitate the development of links between existing programmes which may benefit from coordinated effort.

2. Understanding the Links between research, policy and practice An important objective of SPLASH is to help improve the transfer of research into policy and practice. SPLASH has examined how research knowledge transfer takes place using participatory techniques in selected countries. We found that research is more effective and likely to be used, if the appropriate stakeholders are involved throughout the research cycle. This must include defining the research agenda, with interactions between stakeholders through appropriate partnerships and platforms. From this we have developed guidelines for improved dialogue procedures. Our work has shown that uptake of research by policy makers and practitioners depends on the incentive structures and strategic approaches to using research taken by both researchers and research users. Being able to communicate research findings in the right way and at the right time plays a key role in this. SPLASH proposes to develop training material which will enhance research communication and strategic dissemination skills, as well as supporting intermediary platforms and partnerships for knowledge exchange.

3. Research Management SPLASH is examining the research management practice of European partners, including programme identification, implementation and evaluation, and will synthesise guidance on good practice supported by case studies. Our work shows that few programmes funded by our partners address the development of research management capacity, and most capacity development activities target the individual. Once developed, it is hoped that research management guidelines should support improved European and Developing Country institutional capacity to manage research programmes, and thus enhance effectiveness of our programmes.

4. Designing collaborative research SPLASH is working with development partners to understand thematic research priorities within the sector.

During 2009 we will design programmes for joint funding to address these priorities. Where possible, our programmes will aim to:

• assist existing networks and initiatives; and

• bring innovations from research to ongoing water and sanitation programmes.