## Slide 1
EUWI-Africa Working Group
AWG Meeting, 21 November, 2010
Progress Update
Dick van Ginhoven, DGIS, The Netherlands

## Slide 2: Update on progress
Workplan 2010
Activities
Financial resources
Way forward

## Slide 3: AWG - Workplan 2010
Strategic Objectives | Activities
Implementation of declarations | Sanitation mapping CRS guidance paper (OECD-DAC)
Aid effectiveness and efficiency | EU Code of Conduct study Follow-up on SWAp side event
Ownership and multi-stakeholder partnership | - 3 AWG meetings, of which 2 in Africa - Support to participation of CSO in the AWG
Advocacy and knowledge sharing | Continued and improved communications - Development of advocacy material

## Slide 4: Activities of AWG in 2010 (Nov 2010)
Implementation of declarations
CRS guidance paper:
  Goal: improving sector monitoring, OECD system
  Output: Guidance note for Ministeries
  Status: Note is ready, ublication in December
Sanitation mapping study:
  Goal: mapping existing and future EU commitments on sanitation for Africa
  Output: report with data and information on situation
  Status: draft report by early December, first results in AWW3-session (24 Nov)

## Slide 5: Activities of AWG in 2010
Aid Effectiveness oriented
EU Code of Conduct study:
  Goal: status of implementation and adherence to Paris and Accra Declarations
  Output: report
  Status: draft report by early December
SWAp sharing and learning event:
  Goal: sharing and learning event, sub-regional
  Output: workshop documentation, case studies
  Status: postponed to early 2011, back-to-back with other regional event

## Slide 6: Activities of AWG in 2010
Multi-stakeholder Partnership
3 AWG meetings: July, Sept & Nov
CSO involvement: we have enabled 5 CSO rep’s to attend the AWG meetings
Advocacy & Knowledge sharing
web-site maintenance
communications: 2 newsletters & 2 email updates (EN&FR)
2communications materials: briefing notes & fact sheets: to be made from the studies’ results

## Slide 7: Extra activities of AWG in 2010
Donor meeting to prepare the 1st HLM of SWA
initiative of AWG, focus on Africa, with EU+ participation
held in London, March 2010, hosted by DFID
Dialogue Sessions on Aid Effectiveness
Sept/SWWW: participation of SWA, AMCOW, GLAAS, Liberia, etc
Nov/AWW3: focus on Sanitation 5 Year Drive, together with SWA, AMCOW & UNSGAB

## Slide 8: Financial resources for AWG
AWG had the following financial resources:
Support from WFac (contract untill 2010)
Bilateral support, from the acting co-chair & other EU MS
As from end-2010
EC-thematic budget line (about 1m €, untill 2012) through a UNDP trust fund

## Slide 9: Way forward, next steps
Review of AWG Governance, financed by Netherlands, starting this week
New funding in 2010-2012
  Inception plan of UNDP: t.b.d. today
  Workplan 2011: t.b.d. today
New Troika members: uncertainties

## Slide 10
Thank you!