- IMPLEMENTING PARTNER : CEOSS

| PERSONS OF CONTACT |  |  |
| --- | --- | --- |
| NAME | ROLE | CONTACTS |
| Michael El Daba | Funding and Media Manager IESF animator | Mail: michael.eldaba@ceoss.org.eg Tel: 201227313020 Skype: michaeleldaba |
| Bassem Sayed | Programs Manager - Economic Development | Mail: bassem.sayed@ceoss.org.eg |

| STATUS OF THE PROJECT The following questions are meant to collect information about the ongoing implementation of your project. |  |
| --- | --- |
| Have you completed your baseline? | No |
| Why not? | The project was delayed in the Ministry approval so as we cannot start any activities before that. we are currently doing it |
| Do you need any support from the IESF team related to your baseline? | Not yet thanks |
| Have you completed your monitoring plan? | No |
| Why not? | We are currently completing it with the delegation here due to the above mentioned delay |
| Do you need any support from the IESF team related to your monitoring plan? | Not yet thanks When will it be done and ready to share? Please post on Two-Way Platform as soon as possible. |
| Have you developed the communication plan for your project? | Yes |
| Do you need any support from the IESF team related to your communication plan? | Not yet thanks Please post on Two-Way Platform as soon as possible. |
| Have you launched the field work with the beneficiaries? | No |
| Why not? | We are currently completing it with the delegation here due to the above mentioned delay |
| Do you need any support from the IESF team related to your work with the beneficiaries? | Not yet thanks When will the first Technical Progress Report be ready ? Please send us a copy as well through the Two-way Platform. Please provide name of EC Projet Manager |