- IMPLEMENTING PARTNER: OXFAM UK

| PERSONS OF CONTACT |  |  |
| --- | --- | --- |
| NAME | ROLE | CONTACTS |
| Annie Wakanyi | Funding Coordinator | Mail: AWakanyi@oxfam.org.uk Tel: 254733754498 Skype: Annie.Wakanyi1 |
| Michael Juma | Governance Officer, Urban Programme | Mail: MiJuma@oxfam.org.uk Tel: 254716021 Skype: Michael.juma |
| Caroline Wambui | Project Manager IESF animator | Mail: CWambui@oxfam.org.uk Tel: +254 20 282 1195; mobile +254724969260 Skype: caroline.naomi |

| STATUS OF THE PROJECT The following questions are meant to collect information about the ongoing implementation of your project. |  |
| --- | --- |
| Have you completed your baseline? | No |
| Why not? | The three baseline surveys (gender and power analyses; and on women small scale traders) are currently at completion stages When will it be done and ready to share? Please post on Two-Way Platform as soon as possible. |
| Do you need any support from the IESF team related to your baseline? | No; support was given by IESF on the earlier drafts |
| Have you completed your monitoring plan?: | No |
| Why not? | A draft has been developed and shared with IESF, the plan will be completed after the baselines are finalized We do not see any upload of this on the Two Way platform. When did you send it? |
| Do you need any support from the IESF team related to your monitoring plan? | Yes, feedback on the shared draft awaited We do not see any upload of this on the Two Way platform. When did you send it? |
| Have you developed the communication plan for your project? | Yes. At review and sign-off stage at Oxfam after which it will be shared with IESF and EU team for review, and approval |
| Do you need any support from the IESF team related to your communication plan? | Yes, once the drafts are shared When will it be done and ready to share? Please post on Two-Way Platform as soon as possible. |
| Have you launched the field work with the beneficiaries? | Yes |
| Do you need any support from the IESF team related to your work with the beneficiaries? | Not at the moment When will the first Technical Progress Report be ready ? Please send us a copy as well through the Two-way Platform. Please provide name of EC Projet Manager |