WEZESHA PROJECT

Project Title: Promoting livelihoods and Inclusion of vulnerable women domestic workers and women small scale traders

M&E PLAN

| Expected results | indicator | Indicator definition | Baseline situation | Project Target | Data needs and questions | Data sources/ means of verification | Tools/ Methods | Frequency | Responsibility | How to share the information ( report/ presentation ) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Overall objectives: To contribute to achieving secure and productive lives of vulnerable population dependent on informal economy in Nairobi urban settlements. | Increase in incomes of women dependent on informal economy | Women report an increase in their monthly average income through their engagement in the informal economy |  |  | Average monthly income for the women engaging in domestic and small scale trade | National Household Economy surveys Baseline and evaluation reports | Review of National Economy survey reports, FGDs, KII, Households- Baseline and evaluations | Annual | Project Manager with support from Oxfam MEAL Coordinator | Annual Project Progress reports |
|  | Increased contribution of the women in the informal economy to the local and national economy. | Women make significant contribution in the national income |  |  | Proportion of national income from the informal sector ( gendered analysis) | National Household Economy surveys Baseline and evaluation reports | Review of National Economy survey reports, FGDs, KII, Households- Baseline and evaluations | Annual | Project Manager with support from Oxfam MEAL Coordinator | Annual Project Progress reports |
|  | Increase in realization of rights by domestic workers and small scale traders. | Women understand their rights pertaining to domestic and small trade and empowered to challenge duty bearers for quality service provision |  |  | Proportion of women aware of their rights and are influencing decision and policy making at the county and national level | National Household Economy surveys Baseline and evaluation reports | Review of National Economy survey reports, FGDs, KII, Households- Baseline and evaluations | Annual | Project Manager with support from Oxfam MEAL Coordinator | Annual Project Progress reports |
| SO - To enhance socio-economic empowerment of poor and vulnerable women dependent on the informal economy in Nairobi urban settlements | 60% of small traders and domestic workers open new businesses and/or expand their present businesses 40% small traders report increased profits: 50% increase in number of domestic workers earning the minimum wage: 50% Increase in relevant actions taken by targeted women in claiming their rights 20% of affirmative responses of the requests from County Government to requests for provision of basic social services from the targeted women 30% of women targeted report that they have started savings and/or have opened a bank account |  |  |  | Proportion of target women with businesses Proportion of small scale traders reporting a change in business revenue against purchases. Proportion of domestic workers earning more than the minimum wage Percentage of targeted women claiming their rights Proportion of target group requests that receive affirmative response from the County Govt Proportion of target women with savings and operating active bank accounts | Evaluation reports (Baseline survey, midterm and end-line) | Structured interviews with the target women KII with DW employers FGDs Review of minutes and records for the target groups | Start, Mid and End of Project | Project Manager/Coordinator; Oxfam supported by Oxfam and partner MEAL teams | Reports, PowerPoint; to be shared by the consultant, the reports will be shared with the donors and other relevant stakeholders. , |
| R1 - Increased livelihood opportunities and social support options of women target groups | 70% of targeted women of micro and small scale traders and domestic workers are applying their acquired skills in accessing employment/business opportunities. | Micro and Small Scale Traders: Successful business-profitable and expanding - Making profit - Meeting basic needs - Savings |  |  | - Level of business management skills such as record keeping and savings - Knowledge on credit and financial service products and providers - Visibility and Viability of their businesses; type of businesses. - Customer reach and diversity of stock - Proportion of the target women with existing businesses or have started new businesses - Level of individual stock and savings | Evaluation reports (Baseline survey, midterm and end-line) Project progress reports Target women business records | Structured interviews with the target women FGDs Review of business records Observations Success Stories Case studies | Quarterly | SITE project management | Reports, sharing during quarterly meetings, social media, |
|  |  | Domestic Workers Domestic workers having required competences for their jobs and attracting commensurate remuneration (Marketing skills, housekeeping, healthcare Hygiene, saving skills for personal development) |  |  | - Level of knowledge and skills to undertake household chores (adding value to increase payment) - DW remuneration - Proportion of DW accessing employment opportunities - Increased acceptance/satisfaction of DW by their employers based on improved skills - Proportion of DW starting new business to diversify their livelihood sources | Evaluation reports (Baseline survey, midterm and end-line) Project progress reports | Structured interviews with the target women KII with DW employers FGDs Review of business records Observations Success Stories Case studies | Quarterly | SITE project management | Reports, sharing during quarterly meetings, social media, |
|  | 50% targeted women have access to credit and other business support services. | Targeted small and medium scale traders and DW are aware of the credit and financial service providers and the products offered and are using them to start or expand their business |  |  | - Awareness levels of the existing service providers and products available - Levels of understanding how to access these services - Proportion/Number of the targeted Small and Medium Traders and DW accessing these services - Challenges inhibiting access and use of these services and proposed ways to address the challenges in accessing these products - Access and affordability | Evaluation reports (Baseline survey, midterm and end-line) Project progress reports Reports from Credit and financial service providers reports | Interviews FGD’s Review of reports by service providers on the target SMT and DW women applied and received any support | Quarterly | SITE | Reports, sharing during quarterly meetings, social media, |
| R2 – Greater equity and resilience of women target groups | 20% increase in the number of targeted women registered with National Health Insurance Fund (NHIF) | Targeted women registered and/or covered under the NHIF scheme and are utilizing the services provided by the scheme. |  |  | - Proportion of the SMT and DW aware of these services - Proportion/number of the targeted SMT and DW registered/covered under the scheme - Relevance of the products offered to the needs of the target group - Challenges in accessing the scheme | Evaluation reports (Baseline survey, midterm and end-line Reviewed NHIF Act Project progress report | Structured interviews with the target women KII with NHIF personnel FGDs Review of existing policies on NHIF | Quarterly | WEL | Reports, sharing during quarterly meetings, social media, |
|  | 20% increase in the number of targeted women enrolled into public pension schemes National Social Security Fund and Retirement Benefits Authority | Targeted women registered and consistently remitting payments under the NSSF/RBA scheme and are utilizing the services provided by the scheme. |  |  | - Proportion of the SMT and DW aware of these services - Proportion/number of the targeted SMT and DW registered under the scheme - Relevance of the products offered to the needs of the target group - Challenges in accessing the scheme | Evaluation reports (Baseline survey, midterm and end-line Reviewed NSSF Act Project progress report | Structured interviews with the target women KII with NHIF personnel FGDs Review of existing policies on NSSF/RBA | Quarterly | WEL | Reports, sharing during quarterly meetings, social media, |
|  | 30% increase in the number of targeted women who feel their households have stable safety-nets for the longer-term | Women reporting to be benefiting from public social protection schemes (elderly, orphans etc.) initiated by the Govt and and that these safety nets programs are adequately addressing their household demands |  |  | - Proportion of target women benefiting from the safety nets programs | Evaluation reports (Baseline survey, midterm and end-line) Project progress reports | Structured interviews with the target women KII with Ministry of Devolution personnel FGDs Review of Safety Nets beneficiary database | Annually | WEL | Reports, sharing during quarterly meetings, social media, |
|  | Positive change in workload sharing at household level between men and women. The target value for this indicator will be determined after the baseline. | There is a decrease in the time that women are being engaged in care work at the household level thus having more time to engage in personal socio-economic development.. |  |  | - Establish workload between men and women including time taken for such work - Attitudes and perceptions and beliefs towards care work | Evaluation reports (Baseline survey, midterm and end-line Project progress report Research & gender analysis Care work analysis research report | Structured interviews with the target women KII with Ministry of labour personnel FGDs with both men and women on care work | Annually | WEL | Reports, sharing during quarterly meetings, social media, |
| R3 - Women target groups empowered about their rights and having a collective voice | 60% increase in targeted women’s groups who have a clear understanding of how to claim their legal (labour) and human rights and knowledge of organizations that can support them to claim their rights | Target women understand their labour and human rights and processes on how to engage around addressing their rights and violations |  |  | - Level of understanding of human rights and labour rights related to domestic work - Skills to negotiate for their rights - Awareness of institutions that they can get support on issues of labour and human rights | Evaluation reports (Baseline survey, midterm and end-line Project progress reports | Interviews, Focus Group discussions Minutes of target group meetings observations | Quarterly basis | NOPE Team Leader | Reports, sharing during quarterly meetings, social media, |
|  | 1000(500) groups and 2 federations of targeted women are able to claim their rights, challenge rights violations and seek redress | Formal and informal structures with leadership structures advocating for and claiming the rights of the target women |  |  | - Existence and membership of the groups and target groups’ federations - Leadership structure of the groups and federations - Effectiveness of the reporting structures and governance of the groups - Follow up mechanisms on cases reported in terms and resolution and/or redress | Evaluation reports (Baseline survey, midterm and end-line Project progress reports Group meetings minutes | Interviews, observations FGDs Review of group minutes, | Quarterly basis | NOPE Team Leader | Reports, sharing during quarterly meetings, social media, |
|  | 50% of target groups actively participating in decision making processes with duty bearers, and influencing policies and decisions that are responsive to their requests in their favour | Target women understand the policies affecting their work environment and their social needs. Target women are actively engaging (they use their skills to challenge the systems to amend/negotiate the policies in their favour) in influencing duty bearers and policies to improve their social and working environment. |  |  | - Understanding of the duty bearers at the county government for social service delivery - Understanding Policies and legislation for small traders and labour, its formulation and implementation - Level of participation in budget allocation and review - Proportion of target women participating in leadership positions of the federations | Evaluation reports (Baseline survey, midterm and end-line Project progress reports By laws and policies in place | Interviews, FGDs Review of policies and laws | Annually | NOPE Team Leader | Reports, sharing during quarterly meetings, social media, |
| R4 -Government and other stakeholders well informed and delivering their responsibilities toward target groups with increased efficiency | Kenyan government takes concrete steps towards ratification of the ILO Convention Number189 | Stakeholders such as KUDHEHIA/COTU, Ministry of Labour and the Federation of Kenyan Employers actively participate in the ratification process |  |  | - Status of the ratification | Evaluation reports (Baseline survey, midterm and end-line Media reports, Ministerial statement, | Review of the relevant government reports and policies | Semi annual | Oxfam | Report |
|  | Number of laws, policies and decisions influenced, enacted and/or implemented that improve enabling work environment for the target women small traders and domestic workers in Nairobi City | Policies and laws formulated and decisions taken creating enabling environment for the domestic workers and small scale traders |  |  | - Number of new and existing laws and policies adopted influencing working environment for the target women - Level of satisfaction with the existing policies/laws | Laws and policies | Review of the existing and new policies and laws | Semi annual | WEL, OXFAM and NOPE |  |
|  | Increased actions by the government to enforce compliance on Labour Laws. | Action taken by law enforcers to promote and/or to create an enabling environment to ensure rights of targeted women are respected |  |  | Numbers of reported and resolved cases Levels of satisfaction with the law enforcement. | Evaluation reports (Baseline survey, midterm and end-line Progress reports and media reports Reports on Occurrence books | Observations FGDs Interviews with Victims and law enforcers | Annually | WEL, OXFAM and NOPE | Reports |