Accelerated Access to Vocational Skills Training and Decent Employment in Zimbabwe Programme

Half Year Report

1 January 2015 to 31 July 2015

Young Africa – Zimbabwe

Executive Summary

Young Africa is a vocational skills training organisation that has been delivering vocational skills training services to young people in Zimbabwe since 2002. In 2013, Young Africa piloted a mobile vocational skills training programme which led to the conceiving of the accelerated access to vocational skills training and decent employment programme in Zimbabwe, in partnership with the European Union. This programme is a three year programme being implemented in 7 districts of Zimbabwe.

The first six months of implementing this programme have been slow owing to bureaucratic processes which come with getting the necessary clearances to operate in the various districts. However to date, six districts have given Young Africa the go ahead to start implementing, with the seventh district (Nyanga), in the final stages of drafting the Memorandum of Understanding which will formalise Young Africa’s operations in the district. The slow start to the implementation of the programme has seen the financial burn rate being low in the first six month of programme implementation (an average of 27%). Most of the expenditure has been on logistical and preparatory activities to get the project grounded in the districts so it could take off. All districts are scheduled to start enrolling and training starting mid to end of August and thereafter, the financial burn rate is expected to peak.

In this outreach mobile training programme, the European Union will provide 80% of the budget and Young Africa has to co-fund the remaining 20% either directly or through other funding partners. To-date, Young Africa has managed to raise 0.19 (19%) of the 20% co-funding for the first year. Young Africa is intensifying its fund raising and has to date submitted several proposals to potential donor partners where it expects to raise a further 36% in the next three months.

To inform its programming and to benchmark the programme starting point before implementation, YA Africa in these first six months of programme implementation conducted a baseline survey with the assistance of an external consultancy organisation. The objective of the baseline survey was to identify the relevant skills that Young Africa had to adopt in its vocational skills training programme and also to get key benchmark information on the programme indicators. The skills the programme will offer to the youths through this programme have to be relevant to the resources inherent in the respective districts and the livelihood options available related to the resources available. A report on the baseline is due to be presented to Young Africa by the contracted consultancy organisation on the 14 of August 2015.

Background and Introduction

Young Africa (YA) has been delivering Technical Vocational Education Training (TVET) to young people in Zimbabwe since 2002 using its integrated training model. This model integrates skills training with life skills, entrepreneurship and computer literacy training. Traditionally, YA has been conducting its TVET programme through its Chitungwiza and Epworth centres. However, in 2013, YA piloted a mobile outreach TEVT programme in Goromonzi district in Mashonaland East Province and Buhera District in Manicaland Province. An evaluation of this mobile outreach programme indicated that the programme was effective in equipping young people with the requisite skills that gave them a chance to live a more decent life through access to a stable livelihood. The evaluation also indicated that there is a lot of demand for vocational skills training in outlying areas of Zimbabwe, with very few vocational training centres available to meet this demand.  There is therefore a gap between the demand for TVET and the supply of TVET services which YA, through this programme, is contributing to close.

In line with the findings of the evaluation and the successful implementation of the pilot mobile TVET outreach programme, YA partnered with the European Union, to launch a mobile outreach programme in 3 provinces of Zimbabwe namely Harare, Manicaland and Matabeleland North. The purpose of this report is to give an account of the progress YA has made in implementing this mobile out-reach TVET programme 6 months (February to July 2015)  after it was launched. The report will be divided into three main sections namely, an overall narrative, a financial update and a monitoring and evaluation overview.

Programme overview

The accelerated access to vocational skills training and decent employment in Zimbabwe programme is a three year programme running from February 2015 to January 2018. The programme aims to deliver TVET using the YA integrated vocational skills training model and has the purpose of empowering marginalized and vulnerable young people (16 to 35years), and people dependent on the informal economy for better livelihoods. The programme is mainstreaming gender, HIV and AIDS and disability.  At the end of its three year life, YA targets to have reached with TVET, 10080 under-priviledged young people in 7 districts of Zimbabwe. Of these, 60% should be women and 2100 should be people with disabilities (PWDs). A total of 2016 master crafts persons will actively participate in the programme and will provide internship and mentorship to trainees.

The programme generally had a slow start, owing to the various bureaucratic protocols that had to be observed at national, provincial and district levels. In the initial programme design, YA was targeting 4 provinces namely Harare province, Manicaland province, Mashonaland West province and Matabeleland North province. Following complications with negotiating for permission to operate in Mashonaland West province, a decision was made to refocus on only on Harare, Manicaland and Matabeleland provinces only. This change will not affect any deliverables of the programme and as such the broader scope of the programme will not be compromised in anyway. To date, YA has managed to engage with all relevant local authorities and has been given the green light to start operating in the respective districts through the signing of Memorandums of Understanding. However, there is still one district (Nyanga) where a Memorandum of Understanding with the local authority is still outstanding.

District updates

| District | MOU | Recruitment of trainees | Recruitment of trainers | Recruitment of MCs |
| --- | --- | --- | --- | --- |
| Harare | Signed | In progress | In progress | In progress |
| Chipinge | Signed | In progress | In progress | In progress |
| Makoni | Signed | In progress | In progress | In progress |
| Nyanga | Pending | In progress | In progress | In progress |
| Binga | Signed | In progress | In progress | In progress |
| Hwange | Signed | In progress | In progress | In progress |
| Lupane | Signed | In progress | In progress | In progress |

All districts will be ready to roll out the first training by 17 August 2015.

Financial update

The overall budget for the programme is 2.2million Euros. The EU will provide 80% of the total budget and YA has to co-fund the other 20% either directly from internal fundraising or through partnerships with other donors. To-date YA has managed to fund raise for the programme as follows;

| Donor partner | Budget (m -euro) | %contribution to overall budget |
| --- | --- | --- |
| EU | 1,760,000.00 | 80 |
| IYF | 27,522.94 | 1 |
| SERVE | 55,000.00 | 3 |

YA has submitted proposal to some donors and expects to secure more funding. The potential funders have the prospects of contributing to the overall budget as follows in the first year of programming;

| Donor partner | Budget (m -euro) | %contribution to overall budget |
| --- | --- | --- |
| IYF | 110092 | 5 |
| Australian Aid | 23952 | 1 |

Expenditure for all budgets is generally low because vocational skills training has not started in all the other districts except for Harare. Expenditure has therefore generally been confined to programme staff recruitment costs, logistical costs which include among others, costs associated with attending and doing programme presentations in district cluster meetings and inception meetings at national and district level.  During programme design, Young Africa was conservative on some budget lines in an effort to keep the budget as low as possible. It was the first time the organisation was applying for a grant of this magnitude and it was felt applying for a yearly budget exceeding 500k would jeopardise the organization’s chance of accessing this support. However, it has been observed that some crucial activities were either omitted in the budget or were under-budgeted. Thus, a budget re-rationalisation exercise has to be done in the second half of the first year of implementation to address this weakness so that operationalising this budget will become smoother.

Summary of the EU expenditure as at 31 Jul 2015

|  | Budget (Euro) | Expenditure to date (Euro) | Balance (Euro) | % expenditure to date |
| --- | --- | --- | --- | --- |
| Human Resources | 264240 | 115808 | 148432 | 44 |
| Equipment and supplies | 140960 | 84310 | 56650 | 60 |
| Local office | 37780 | 7122 | 30658 | 19 |
| Other costs and services | 72940 | 10586 | 62354 | 15 |
| Other | 356686 | 20997 | 335689 | 6 |
| Total | 872606 | 238823 | 633783 | 27 |

The overall expenditure of the EU budget is 27%. This is mainly because TVET has only started in Harare only. The other 6 districts are starting to run their first round off trainings in August 2015. Also all construction work (computer laboratory and factory shells) is scheduled for the second half of year one and first half of your two.

Summary of the SERVE budget expenditure as at 31 July 2015 (Co-funding)

|  | Total budget | Total expenditure | Balance | % expenditure |
| --- | --- | --- | --- | --- |
| Travel and transport | 21,390 | 16,514 | 4,876 | 77.20 |
| Equipment and supplies | 340 | 286 | 54 | 84.19 |
| Supplies | 900 | 143 | 757 | 15.90 |
| Consultant and contracts | 900 | - | 900 | 0.00 |
| Other direct costs | 17,170 | - | 17,170 | 0.00 |
| Other costs and services | 3,300 | 367 | 2,933 | 11.12 |
| Total | 55,200 | 17,310 | 37,890 | 31.36 |

The overall budget expenditure is generally low (31%) because training has not yet started. The first cohort is due to start training in August 2015 and thereafter, the burn rate is expected to go up significantly.

The summary report for ZimWorks Fixed Obligation Grant (Co- funding)

| Object Class Categories | Total budget | Total expenditure | Balance | % expenditure |
| --- | --- | --- | --- | --- |
| Travel and Transportation | 8,475 | 3,510 | 4,965 | 41 |
| Equipment | 1,839 | 1,698 | 141 | 92 |
| Supplies | 2,343 | 1,574 | 769 | 67 |
| Consultants & Contracts | 1,100 | 750 | 350 | 68 |
| Other Direct Costs | 7,870 | 6,920 | 950 | 88 |
| Subtotal Direct Costs | 21,627 | 14,452 | 7,175 | 67 |
| Indirect | 550 | 30 | 520 | 5 |
| Total | 21,627 | 14,482 | 7,145 | 67 |

The fixed obligation grant is coming to an end at the end of August 2015. Expenditure rates are very low for travel and transportation where there is a balance of USD4965. YA will engage the donor so that the balance can be used to purchase materials for trainees for the next recruitment.

Monitoring and Evaluation

For the period, the following outputs came out of the monitoring and evaluation unit;

- A monitoring and evaluation framework and plan

- Production of relevant monitoring and evaluation tools

- A baseline survey was conducted

Baseline and needs assessment survey

Young Africa contracted Ask Dev consultancy firm to conduct a baseline and needs assessment to guide its implementation and provide relevant targeted vocational technical skills courses required in all areas of implementation. The baseline and needs assessment were conducted successfully from the13th to the 25th of July 2015 in Harare, Manicaland Province (Chipinge, Makoni and Nyanga) and Matabeleland province (Binga, Lupane and Hwange).Findings from the survey indicated that, stakeholders and young people in the districts expressed high interest in the programme and vowed to support the programme as it aims to economically empower the young people through the provision of hand skills. Courses that young people in Matabeleland require apart from the traditional courses offered by YA are brick moulding, building, Tourism, music, beading, carving, conservative agriculture, crocodile farming, fish farming, cattle fattening, pig rearing and sport development amongst others. In Manicaland the courses that young people require apart from those being offered by YA are building, painting, horticulture, fish farming, poultry, value addition for agriculture products, plumbing and brick moulding. Stakeholders urged YA to desist from interfering in districts politics hence urged YA to understand the political landscape of each district before implementation and remain apolitical in its operations. The full baseline report will be presented to YA by the 14th of August.

Summary of progress towards achieving milestones and targets

Little progress has been made towards achieving year 1 milestones. All districts have, except Nyanga, have been cleared to start implementation. A baseline survey was successfully conducted to identify training needs per district and the report of the baseline will be out on the 14th of August 2015. All trainings will therefore commence from the end of August onwards. Below is a summary of the programme progress to-date.

| Activity | Indicator | Purpose | Output/ Outcome | Baseline | Target | Frequency | Progress Achieved to date | Comment |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To increase access to TVET services for 2,100 PWD | Percentage of PWD formally and informally employed | To assess the impact of the programme on PWD | Outcome | Baseline | At least 35% of participants will be formally or informally employed by the end of the programme | Pre/post program surveys reports | 0 | Programme in early implementation stage |  |
|  | Percentage of PWD with improved livelihoods and increased personal resilience | To assess the impact of the programme on PWD participants | Outcome | Baseline | At least 35% of participants will have improved standards of living and personal resilience by the end of the programme | Pre/post program surveys reports Progress Monitoring reports | 0 | Programme in early implementation stage |  |
|  | Percentage of PWD with ability to use computers | To assess the improvement of the computer literacy levels of PWD | Outcome | Baseline | At least 60% of participants will have improved ability to use computers by the end of the programme | Pre/post program surveys Progress Monitoring Reports | 0 | Most PWD to be enrolled in year 2 after TVET centres refurbishment |  |
|  | Number of centres with disability inclusive equipment | To assess the facilitation of learning for PWD by making the centres Disability friendly | Outcome | 0 | 2 (Chitungwiza & Epworth) | Baseline reports Midterm Evaluation Report Final Evaluation Report | 0 | Refurbishment and furnishing not yet started .will commence in the second half of year one. |  |
| To increase access to TVET service for 7,980 marginalised young people aged between 15-35 years | Number of young men and women graduating from Technical Vocational and Education Training(TVET) | To assess the increased access to vocational skills training and decent employment within the informal sector among young women and men | Outcome | 0 | 7,980 Yr1-1,360 Yr 2- 3950 Yr 3-2,670 | Once off beginning of every cohort updated regularly | 293 | This figure is only for Chitungwza, Epworth and the Harare out reach. District outreaches will start in August and the first cohort is expected to graduate in October. |  |
|  | Percentage formal and informal employment rate among TVET graduands | To assess the impact of the programme to young men and women with regard to employment rates | Outcome | 0 | Formal and informal employment rates of participants will improve by at least 60% from baseline | Student baseline Student follow up tool | 0 | Programme in early implementation stage |  |
|  | Percent improvement in livelihoods status and increased personal resilience among TVET graduands | To assess the impact of the programme on participants with regard to changes in their standards of living and personal resilience. | Outcome | Baseline | At least 35% of participants will have improved standards of living and personal resilience by the end of the programme | One off-project inception Once every two months After training-6 months ex post | 0 | Programme in early implementation stage |  |
|  | Number of factory shells constructed and equipped | To assess the development of incubation services that support the start up and expansion of promising youth owned enterprises | Output | 0 | 4 shells will be constructed and equipped | Quarterly from construction commencement | 0 | The factory shells will be tailored to the kind of skills that it they will house. The programme will target to house those skills which show potential per district. Construction will commence early in year two when all these factors have been determined. |  |
|  | Percent increase in household income and asset ownership attributable to the programme | To assess the impact of the programme on participants with respect to income increase | Outcome | Baseline | At least 40% of TVET beneficiaries will have increased their incomes and assets by the end of the programme | Student baseline reports Programme reports | 0 | Programme in early implementation stage |  |
| To strengthen Capacity of 2,016 MCs and Associations and increase their participation in DDCs | Number of new jobs or employment created by MCs | To assess impact of the programme on MC’s business expansion | Outcome | 0 | 1,008 over three years | MC baseline reports MC Follow up reports | 0 | Programme in early implementation stage |  |
|  | Number of MCs/Associations participating in District Development Committees (DDC) | To assess the capacity strengthening of MC associations to meaningfully and confidently engage in DDC activities to advocate for the improvement of the SMEs operating environment | Outcome | 0 | 7(one association per district) | Programme reports Minutes form Association meetings | 0 | Programme in early implementation stage |  |
| To increase access to micro-financing for 2,016 MCs and apprentices | Percentage of MCs and apprentices accessing microfinance | To assess the enabling of apprentices and MCS to start up and expand own businesses respectively. | Outcome | 0 | At least 20% of MCs accessing micro finance by the end of the programme At least 55% of apprentices accessing micro finance by the end of the programme | 6 months ex post-after graduating and training | 0 | Programme in early implementation stage |  |
|  | Percentage of MCs with expanded business by 20% | To assess the effectiveness of the programme on MCs | Outcome | 0 | At least 20%of MCs participants will expand their business by the end of the programme | MC Baseline reports Programme reports | 0 | Programme in early implementation stage |  |
|  | Percentage of young men and women starting their own enterprises at least 6 months ex post | To assess impact of programme to participants with regard to enterprise start-up | Outcome | 0 | At least 25% of youths will start own businesses at least 6 months ex post training | Student Baseline reports Programme reports | 0 | Programme in early implementation stage |  |
| To train MCs in entrepreneurship, computers and life skills | # of MCs trained in entrepreneurship, computers and life skills | To track progress of planned activities towards attainment of project’s results and impact regarding training on entrepreneurship, computers and life skills | Output | 0 | Yr 1-300 Yr 2-1,500 Yr 3-216 (separate targets for computers, life skills and entrepreneurship training) | Quarterly | 30 MCs were trained in entrepreneurship focusing in marketing and record keeping. |  |  |
| To facilitate training in advocacy | # of advocacy trainings held # of stakeholders trained in advocacy | To track progress of planned activities towards attainment of project’s results and impact with regard to advocacy | Output | 0 | 7 trainings held 30 stakeholders | Early Year 2 | 0 | Target for the deliverable is year 2 |  |
| To facilitate review/development of curricula | Revised Curriculum | To track progress of planned activities towards attainment of project’s results and impact with regard to curriculum revision | Output | baseline | TBA (results from Baseline) | Once -Year 1 | 0 | Not yet done |  |
| To facilitate refurbishment and expansion of TVET centre and residence | Refurbished and expanded TVET centre and residences Construction of Computer lab | To track progress of planned activities towards attainment of project’s results and impact with regard to refurbishment and construction | Output | 0 | 2 Centres(Epworth and Chitungwiza) 1 Computer lab constructed at Chitungwiza | Year 1 | 0% | Not yet started. Consultations are being done with Disabled Persons Organisation (DPOs) to get an informed position on the type of renovations which can be done at the residential centres. |  |
| To roll out internship and mentorship programme | # of students participating in internship and mentorship programme | To track progress of planned activities towards attainment of project’s results and impact with regard to student’s participation in internship and mentorship | Output | 0 | Yr 1- 1,700 Yr 2-5,000 Yr 3-3,380 | Quarterly-outreach TVET Half yearly-yearly-residential TVET | 293 | All trainees have gone through internship and mentorship as it is part of the curriculum. |  |
| To facilitate life skills training | # of life skills training conducted to TVET students | To track progress of planned activities towards attainment of project’s results and impact with regard to life skills training. | Output | 0 | Yr 1-17 trainings Yr 2-50 trainings Yr 3-34 trainings | Residential TVET-bi annual Outreach TVET-Quarterly | 3 trainings conducted (17% ) | 1 each for Chitungwiza and Epworth and 1 for outreach. |  |
| To train TVET students in using computers(Including 2,100PWD) | #of TVET students trained in using computers | To track progress of planned activities towards attainment of project’s results and impact with regard to training of TVET students on using computers. | Output | 0 | Yr 1- 1,700 Yr 2-5,000 Yr 3-3,380 | Residential TVET-bi annual Outreach TVET-Quarterly | 177 trained in computers | These are Chitungwiza and Epworth graduates excluding outreach. |  |
| To enrol PWD into the TVET training programme | # of PWD recruited into the TVET training | To track progress of planned activities towards attainment of project’s results and impact with regard to number of PWD recruited into TVET training. | Output | 0 | 2,100 (Yr 1-340 Yr 2-1,050 Yr3 -710) | Residential TVET-bi annual Outreach TVET-Quarterly | 2 enrolled in the Harare outreach | These enrolled through the outreach. In the second half of the year, numbers are expected to peak as there will be efforts to make the centres more disability friendly. |  |
| To carry out TVET outreaches | # of TVET outreaches carried out | To track progress of planned activities towards attainment of project’s results and impact with regard to TVET outreaches. | Output | 0 | 7 | Quarterly | 1 outreach has been done that is 14% for the quarter | Implementation in other districts not yet commenced |  |
| To facilitate training in Access to Finance | # of access to finance training conducted | To track progress of planned activities towards attainment of project’s results and impact with regard to finance training conducted. | Output | 0 | 334 trainings (Yr 1-56 Yr 2-166 Yr 3-112) | Residential TVET-bi annual Outreach TVET-Quarterly | 5 trainings | Only Chitungwiza has received ISAL trainings, they are plans to roll out the trainings to graduates from the outreach and from Epworth. |  |
| To facilitate business competitions for MCs and TVET students | # of business competitions for MCs and TVET students held | To track progress of planned activities towards attainment of project’s results and impact with regard to business competitions. | Output | 0 | 24 competitions(3 national,21 districts) Yr1-8 Yr 2-8 Yr3-8 | Annually |  |  |  |
| To carryout gender, disability HIV and AIDS mainstreaming training | # of gender ,disability, HIV and AIDS mainstreaming trainings held to staff # of gender, disability and HIV and AIDS mainstreaming trainings held to students | To track progress of planned activities towards attainment of project’s results and impact of mainstreaming training | Output | 0 | 6 trainings (Year 1-3 trainings-1 staff,2 students Year 2- 2 trainings (1 for staff,1 for students Year 3-1 for students | Quarterly, Bi annually and annually. | 2 | one on gender and the other on disability mainstreaming were done for staff. |  |

Monitoring and evaluation plan August to December 2015

|  |  |  | ALL DISTRICTS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity |  |  | MONTH |  |  |  |  |  |  |
|  |  |  | August |  | Sep | Oct | Nov | Dec | Jan-16 |
| Baselines |  |  |  |  |  |  |  |  |  |
| Data Capturing |  |  |  |  |  |  |  |  |  |
| Progress Monitoring |  |  |  |  |  |  |  |  |  |
| Reports generation |  |  |  |  |  |  |  |  |  |
| Follow up monitoring |  |  |  |  |  |  |  |  |  |
|  | Baseline All districts |  |  |
|  | Data Capturing at district level |  |  |
|  | Data Capturing at Head office level |  |  |
|  | Progress Monitoring |  |  |
|  | Reports Generation |  |  |
|  | Follow up monitoring after training |  |  |

Work plan up to December 2015

See attached work plan up to December 2015.

Conclusion

Even through the programme had a slow start in implementation, there is still enough room to cover for lost time. All districts are geared to start training and the role out strategy for trainings should be such that all trainings start at the same time, with alternate weeks of vocational skills training (theory and practice).