- IMPLEMENTING PARTNER: OIKOS

| PERSONS OF CONTACT |  |  |
| --- | --- | --- |
| NAME | ROLE | CONTACTS |
| Francesca Lucchi | Project Manager IESF animator | Mail: francesca.lucchi@istituto-oikos.org Tel: 255752021039 Skype: Francesca Lucchi |
| Silvia Beretta | Program Manager | Mail: silvia.beretta@istituto-oikos.org Tel: 393483181186 Skype: Silvia Beretta |

| STATUS OF THE PROJECT The following questions are meant to collect information about the ongoing implementation of your project. |  |
| --- | --- |
| Have you completed your baseline? | NO |
| Why not? | We still need to close the Inception Meetings at village level in Longido District. |
| Do you need any support from the IESF team related to your baseline? | No, we are confident we will close this activity in a few weeks. We have finalized the baseline interviews, sample of 150. We are working on the cleaning and reporting of data. |
| Have you completed your monitoring plan?: | NO |
| Why not? | We have implemented other activities, we are working on the definition of the indicators and the criteria to measure them. |
| Do you need any support from the IESF team related to your monitoring plan? | NO, thank you We have finalized and share the Monitoring Plan on the IESF Platform. |
| Have you developed the communication plan for your project? | No |
| Why not? | We are in contact with the head quarter in Milan Italy, Istituto Oikos, to develop the communication plan, we are still working. Istituto Oikos have arranged a mission in March here in Tanzania with the Communication staff to finalize the Communication strategy. |
| Do you need any support from the IESF team related to your communication plan? | NO, thank you |
| Have you launched the field work with the beneficiaries? | No |
| Why not? | We are presenting the project in Inception Meetings at local levels before |
| Do you need any support from the IESF team related to your work with the beneficiaries? | NO, thank you We are selecting the names of all the beneficiaries and the names of the Trainers who will conduct the Training sessions on the field, while finalizing the contents of the Marketplace Literacy Trainings, which will start approximately in April. |