## Slide 1
26th – 28th April 2016
A Presentation to:
06th Quarterly Review Meeting
Aweil Grand Hotel, Aweil

## Slide 2
South Sudan Rural Development (SORUDEV) Programme
A Presentation to 06th QRM – April 2016

## Slide 3: Project Fact Sheet:
Project Title: Implementation of SORUDEV Smallholders' Component in Northern Bahr el Ghazal State
Project Period: 15th February 2014 – 14th February 2017
Total budget: € 2,222,222
Implementing partners: Concern World wide (CWW); Langich United Youth Development Association (LUYDA) Aweil Project for Agriculture Development (APAD)
Coverage: Aweil Centre County: 3 Payams – 18 Bomas; Aweil North County: 4 Payams – 24 Bomas;
Aweil West County: 7 Payams – 39 Bomas;
A Presentation to 06th QRM – April 2016

## Slide 4: Project Fact Sheet:
Goal: To contribute to increased food security, reduced vulnerability and enhanced livelihoods of rural households in NBeG, SSD
Specific Objective: To increase agricultural production & income of smallholder farmers in NBeG.
The specific objective will be achieved by:
Strengthening extension services, use of good practices & reduced losses
Facilitating the adoption of animal draught cultivation throughout the State
Increasing market access & linkages between value chain actors
Target: 4,500 active smallholder (SH) farmer households (HHs)
A Presentation to 06th QRM – April 2016

## Slide 5: Progress Against Indicators – SORUDEV
A Presentation to 06th QRM – April 2016
Specific Objectives | Indicators | Baseline values |  |  | Target | Achievement/ Progress | Comments/ Issues
 |  | Ave | MHH | FHH |  |  | 
To sustainably increase agricultural production and agricultural income of small holder farmers in NBeG through the setup of functional agricultural and livestock advisory and extension services that effectively reaches small holder farmers. | Average monthly income of targeted households from all sources disaggregated by gender of HH head (SSP) | 195 | 212 | 107 | 120 | Mid-term review (MTR) done | Data analysis in progress
 | Average yields (kg/ha sun dried grain) for Sorghum, Groundnuts, Simsim, for targeted SH famers for the last completed cropping season. | Sorghum G/nut Simsim | 525.5 576 478 | 492.5 841.3 576 | 600 850 500 | MTR | 
 | Average household asset index score for targeted households | 11 | 11.1 | 10.5 | 13 | MTR | Data analysis in progress
 | Average number of food groups consumed in targeted households in the previous day and night (Household Dietary Diversity Score) |  | 7 | 7 | 8 | MTR | Data analysis in progress
 | % of targeted farming HH consuming at least 2 meals in the previous 24hours | 85 | 85.2 | 87.7 | 88% | 88.5% | Data analysis in progress

## Slide 6: Last quarters achievements:
A Presentation to 06th QRM – April 2016
County | Payam | Boma | # of groups | Membership |  |  | Actual area (fed) cultivated | Yield per crops grown (tons) |  |  | Comments
 |  |  |  | Total | M | F |  | Sorghum | G/nuts | Sesame | 
Aweil West | Achana | GORI | 2 | 41 | 28 | 13 | 151 | 33.885 | 7.965 | 7.245 | 
 |  | MAJOKDENGDIT | 2 | 41 | 28 | 13 | 18 | 35.235 | 10.35 | 8.775 | 
 |  | MAROL MADAN | 2 | 47 | 15 | 32 | 178 | 32.31 | 11.565 | 7.47 | 
 | Ayat West | LULIC | 2 | 39 | 29 | 10 | 138.43 | 38.5 | 19 | 15 | 
 |  | MALEK MAYAR | 2 | 30 | 23 | 7 | 114.5 | 32 | 17 | 11 | 
 |  | MAYOM BOL | 2 | 30 | 28 | 2 | 91.75 | 30 | 16.5 | 9 | 
 |  | POTNYANG | 2 | 37 | 24 | 13 | 155.75 | 41 | 21 | 13.5 | 
 |  | MANYIEL DENG | 2 | 30 | 24 | 6 | 114.25 | 22.35 | 11.3 | 2.7 | 
 |  | NYINBUOLI | 2 | 25 | 14 | 11 | 91.5 | 19 | 9 | 2 | 
 | Gumjuer East | GUKIC | 2 | 30 | 14 | 16 | 139 | 13.32 | 4.75 | 0.5 | 
 |  | MAKUEI | 2 | 24 | 9 | 15 | 83 | 17.01 | 5.04 | 1.8 | 
 |  | AMETH | 2 | 33 | 20 | 13 | 141 | 14.22 | 9.63 | 0.54 | 
 |  | WEDWEIL | 2 | 33 | 15 | 18 | 150 | 10.44 | 7.74 | 0.99 | 
 |  | AGUAT | 2 | 40 | 22 | 18 | 177 | 17.55 | 8.24 | 0.81 | 
 |  | MAPPER NGOR | 2 | 27 | 9 | 18 | 118 | 12.33 | 9.05 | 0.95 | 
 | Mariem West | Kongdai | 2 | 50 | 32 | 18 | 150 | 9.945 | 1.35 | 0 | 
 |  | Mariem | 2 | 41 | 6 | 35 | 143.5 | 8.1549 | 1.107 | 0 | 
 |  | Makem | 4 | 87 | 9 | 78 | 261 | 17.3043 | 2.349 | 0 | 
 |  | Chimeldit | 13 | 260 | 25 | 235 | 910 | 51.714 | 7.02 | 0 | 
 |  | Chimelthii | 4 | 96 | 33 | 63 | 288 | 19.0944 | 2.592 | 0 | 
 |  | Chimel-North | 1 | 10 | 2 | 8 | 35 | 1.989 | 0.27 | 0 | 
 | Mariem East | Rualngol | 2 | 50 | 28 | 22 | 225 | 19.8 | 0.9 | 0 | 
 |  | Magar | 2 | 50 | 30 | 20 | 225 | 19.8 | 0.9 | 0 | 
 |  | Maluilakong | 1 | 25 | 20 | 5 | 112.5 | 9.9 | 0.45 | 0 | 
 |  | Akalthut | 1 | 25 | 20 | 5 | 125 | 9.9 | 0.45 | 0 | 
 |  | Rumpaleu | 1 | 25 | 20 | 5 | 125 | 9.9 | 0.45 | 0 | 
 |  | Malou Dut | 1 | 25 | 20 | 5 | 125 | 9.9 | 0.45 | 0 | 
Total |  |  | 64 | 1251 | 547 | 704 | 4586.18 | 556.5516 | 186.418 | 82.28 | 0
1. Crop Yield Assessment

## Slide 7: Last quarters achievements:
A Presentation to 06th QRM – April 2016
County | Payam | Boma | # of groups | Membership |  |  | Actual area (fed) cultivated | Yield per crops grown (tons) |  |  | Comments
 |  |  |  | Total | M | F |  |  |  |  | 
 |  |  |  |  |  |  |  | Sorghum | G/nuts | Sesame | 
Aweil North | Malual Centre | PAMAT | 1 | 50 | 1 | 18 | 39.5 | 88.5 | 94.5 | 10.5 | 
 |  | MARENG AKOK | 2 | 50 | 1 | 4 | 119 | 219.75 | 45.5 | 7 | 
 |  | MATUIC | 1 | 50 | 43 | 7 | 54 | 164 | 27 | 13.25 | 
 |  | MAPER DENGACUIL | 2 | 50 | 40 | 10 | 77 | 185 | 31 | 9.5 | 
 |  | AUYII/KANGKUOT | 2 | 50 | 47 | 3 | 29 | 55 | 48 | 1 | 
 |  | MAROL DENGGENG | 2 | 50 | 45 | 5 | 39 | 58 | 27 | 6 | 
 | Malual North | MAJAK BOL | 2 | 50 | 42 | 8 | 201 | 243 | 272 | 3 | 
 |  | RIANG YOR | 2 | 50 | 35 | 15 | 96 | 64 | 40 | 4 | 
 |  | MAYOM BUKIC | 2 | 50 | 40 | 10 | 46 | 41.5 | 14 | 0 | 
 |  | ROLGUT | 1 | 45 | 24 | 21 | 75 | 84.5 | 94 | 7 | 
 |  | PETH YIEK | 1 | 32 | 0 | 32 | 52.5 | 70 | 0 | 0 | 
 |  | MAYOM ADHAL | 1 | 41 | 27 | 14 | 52 | 94 | 2 | 5 | 
 | Malual West | MAROL WEK | 2 | 50 | 36 | 14 | 252.00 | 53.181 | 5.94 | 15 | 
 |  | MAJAK BAI | 2 | 50 | 24 | 27 | 316.5 | 624.6 | 27 | 13 | 
 |  | MATHIANG | 2 | 50 | 28 | 23 | 340 | 50.445 | 20.205 | 16 | 
 |  | MAJOK AKOK | 2 | 50 | 30 | 21 | 189.5 | 14.94 | 2.43 | 0 | 
 |  | WARCUEI | 2 | 50 | 31 | 29 | 195 | 20.79 | 9.9 | 0 | 
 |  | MANYIEL | 2 | 50 | 31 | 20 | 180 | 30.6 | 6.885 | 0 | 
 | Ariath | LANAGER | 2 | 50 | 21 | 29 | 56 | 83 | 95 | 10 | 
 |  | PANDIT | 2 | 50 | 26 | 24 | 55.5 | 59 | 86 | 17 | 
 |  | AMEL | 2 | 21 | 9 | 12 | 24 | 50 | 25 | 6 | 
 |  | KAJIIK | 2 | 50 | 18 | 32 | 67 | 56 | 110 | 4 | 
 |  | LUETH LUAL | 2 | 30 | 10 | 20 | 37.5 | 60 | 20 | 19 | 
 |  | MAJOK DIING | 2 | 50 | 19 | 31 | 62 | 59 | 83 | 11 | 
 | Total |  | 43 | 1,119 | 628 | 429 | 2,655 | 2,528.81 | 1,186.36 | 177.25 | 

## Slide 8: Progress Against Indicators – SORUDEV
A Presentation to 06th QRM – April 2016
Results | Indicators | Baseline values |  |  | Target | Achievement/ Progress | Comments/ Issues
 |  | Ave | MHH | FHH |  |  | 
Result 1: Improved provision and access to sustainable extension services for poor, young and female farmers to improve knowledge to enhance food production and productivity | % of targeted SH farmers who have received advice/ training/ support from an extension worker in the past year | 11.6 | 12 | 25 | 50 | 90 | Farmer-led extension
 | % of targeted SH farmers who are very satisfied with the quality of the extension and advisory services they received | 48 | 55 | 55 | 60 | 75 | 
 | # of training courses conducted for smallholder farmers and extensionists at Nyamlell centre in past year (baseline/month (routine monitoring)) | 0 | 0 | 0 | 05 | 03 | 
 | % of targeted farmers who, if needed, could access veterinary services in the last 12 months (previous month for monitoring) | 48.6 | 49.3 | 45.5 | 55 | 00 | Challenges with getting letter of exemption for CAHWs kits
 | % who grew >1 crop in the last season | 64.8 | 64.5 | 66.2 | 90 | 90 | Crops grown sorghum, gnuts, sesame

## Slide 9: Last quarters achievements:
2. Planning meeting with Lead Farmers & CAHWs:
Agenda:
  Plan activities for the quarter,
  Review progress and challenges faced while providing extension support
  Discuss areas of support
Challenges:
  Breakdown of bicycles & difficult in getting spares
  Wide areas of operation
  Delay in delivery of kits making it difficult to offer services to beneficiaries
  Way forward:
    Increase bicycle maintenance allowance
    Encourage farmers to open group farms apart from the demonstration plot
    Speed up the delivery of CAHWs kit
A Presentation to 06th QRM – April 2016

## Slide 10: Last quarters achievements:
Mid term Review (MTR) for SORUDEV
Consultants selected & contracted to undertake the MTR
Field data collection completed & awaiting data analysis to be undertaken
HH survey, Focus group discussions (FGDs) & Key Informant Interviews (KIIs) conducted in selected locations in the 03 counties
A Presentation to 06th QRM – April 2016

## Slide 11: Progress Against Indicators – SORUDEV
A Presentation to 06th QRM – April 2016
Results | Indicators | Baseline value |  |  | Target | Achievement/ Progress | Comments /Issues
 |  | Ave | MHH | FHH |  |  | 
Result 2: Improved equality for market access, access to inputs and agricultural incomes for rural poor smallholder farmers in Aweil North and Aweil West, and Aweil Centre Counties | % of targeted HH who use ox and donkey ploughs during planting season | 12.4 | 10.8 | 12.7 | 25 | 20 | 
 | % of target farmers who use improved seed (i.e. certified seed) for their staple food crop in the last completed cropping season. | 03 | 03 | 02 | 10 | 05 | 
 | Average HH annual income from crop sales | 338 | 329 | 399 | 500 | MTR | MTR results
 | % of targeted beneficiaries who are members of marketing groups and/ or value additional for agricultural and livestock produce | 07 | 06 | 12 | 22.5 | 00 | Marketing groups just been formed
 | % of targeted beneficiaries who are members of VSLA groups | 06 | 05.8 | 06.2 | 50 | 69 | 
 | %households selling 1 or more crops from last completed cropping season. | 50.4 | 50.4 | 0 | 10 |  | 
 | No. of kgs of produce (sorghum, Simsim, groundnuts) sold by marketing groups on a monthly basis (measured on a quarterly basis) | 00 | 00 | 00 | 0 |  | 
 | Income from sale of Sorghum, Simsim and G/nuts in marketing groups/ quarter | 00 | 00 | 00 |  |  | 

## Slide 12: Last quarters achievements:
Agro-dealership
01 agro-dealer has been working with farmers in Aweil West County
01 agro-dealer identified in Aweil North County
34 ploughs sold to the project beneficiaries
Price per plough: SSP. 350
Payment module: In 03 instalments though some farmers paid full amount
A Presentation to 06th QRM – April 2016
County | Payam | Number of donkey ploughs bought | Number of donkey ploughs requested
Aweil West | Achana | 19 | 23
 | Ayat West | 09 | 16
 | Gumjuer East | 06 | 00
 | Total | 34 | 39

## Slide 13: Last quarters achievements:
A Presentation to 06th QRM – April 2016
Finished donkey ploughs ready for the beneficiaries
Agro-dealer/ Blacksmiths at work fabricating donkey ploughs in Marial Baai, AW county
Farmers in Majook Deng Dit boma, Achana Payam, display the purchased donkey ploughs

## Slide 14: Last quarters achievements:
Formation of marketing groups:
Community mobilisation & sensitization going on
03 marketing groups formed in Aweil West County; 03 in Aweil North County and none in Aweil Centre
Training of the groups scheduled to take place in May 2016
A Presentation to 06th QRM – April 2016

## Slide 15: Last quarters achievements:
VSLA activities:
Support to the VSLAs was provided within the quarter
VSLA training conducted for project staff under FSTP and BRACED as well as new SORUDEV staff
25 participants drawn from Concern, WHH and PIN trained for 5 days (15 from Concern, 1 from WHH and 9 from PIN).
Training delivered through presentation, practical demonstration, group work and participant interaction.
Current economic situation has affected the groups doing the savings
A total of 68 groups are currently saving and have over SSP. 88,004 as savings; SSP. 39,374
Purpose of loans: Start small business, buy ploughs, land clearance, school fees, medical treatment
A Presentation to 06th QRM – April 2016

## Slide 16: Last quarters achievements:
A Presentation to 06th QRM – April 2016
Money counter counts savings in front of VSLA members.
VSLA key holders open box in presence of VSLA members at in Peth Yiik Boma.

## Slide 17: Last quarters achievements:
7. Project monitoring & supervision support by SMoAF
SMoAF technical team visited Aweil Centre County to monitor the implementation of SORUDEV and FSTP projects
  To assess the project progress
  To ascertain quality & quantity of community assets created by beneficiaries.
  To evaluate the extension package received by Lead Farmers & frequency of trainings facilitated by implementing partners.
  To find out the challenges faced by farmers and chart way forward.
  To explore the synergies and complementarities between different projects & how they contribute to increasing food & nutrition security
A Presentation to 06th QRM – April 2016

## Slide 18: Last quarters achievements:
  Findings:
  Community assets e.g. feeder roads taken to different locations & thus not serving the purposes & therefore it would be important to consolidate for more impact
  VSLA doing well & it would be good to include dry season cultivation into VSLA as a source of income & food where water source can sustain a complete season
  Fast track the delivery of CAHWs kits
  Include more government extension staff in trainings so as to build their capacity
A Presentation to 06th QRM – April 2016
Joint monitoring team Comprised of SMoAF , GAA & CWW staff meeting with VSLA group at Nhomlau boma in Aweil Centre County

## Slide 19: Last quarters achievements:
Coordination & Steering committee meetings
Payam coordination meetings held in payams CWW is working in
Meetings attended by Payam & Boma administrators, RRC, Payam Agriculture & Livestock supervisors,
PSC committee meetings were held in the 03 counties during the quarter chaired by the Hon. County Commissioners & attended by department heads
A Presentation to 06th QRM – April 2016
Payam coordination meeting in Gumjuer East Payam at payam HQ
PSC meeting in Aweil Centre County at County HQ

## Slide 20: Project Fact Sheet:
Project Title: Implementation of Community sensitization, mobilisation and capacity building activities for Gok Machar - Mayom Angok feeder road in Aweil North County
Project Period: 13th August 2015 – 12th August 2016
Total budget: € 96,274
Implementing partners: Concern World wide (CWW);
Coverage: Aweil North County: 4 Payams – 24 Bomas;
A Presentation to 06th QRM – April 2016

## Slide 21
UNOPS Feeder Road Project:
A Presentation to 06th QRM – April 2016

## Slide 22: Project Fact Sheet:
Objective: Implement community sensitization, mobilization and capacity building activities in project affected communities to complement and ensure effective maintenance of the Gok Machar – Mayom Angok feeder road constructed by UNOPS
Specific objective:
Carry out local community sensitization, information dissemination & mobilization to ascertain adequate community participation & ownership in project implementation.
Create community awareness on objective & scope of feeder road construction & maintenance.
Facilitate local community to establish CBOs, provide training in supporting the road construction & maintenance using PPP concept rules and responsibilities.
Mobilize community & groups & start required works supporting road construction & maintenance.
Negotiation with communities to form a consensus on the proposed road alignment for implementation if and when there are issues and/or complaints.
Build M&E mechanism to ensure assessment & measurement of community awareness & participation
A Presentation to 06th QRM – April 2016

## Slide 23: Last quarters achievements:
Selection of support staff
CWW worked with the 03 Payam administrators to select 18 community members to support the UNOPS team to help in road marking and traffic counting.
To avoid conflict, each Payam where the road passes was represented to ensure none of the communities felt left out.
2. Road Alignment negotiations
  On marking the final road design, certain points selected by the community had been changed due to the topography of the land & this affected a number of HHs
  To address these changes, CWW & UNOPS held community meetings to explain why the changes & to agree on the possible new points
  Agreements were reached & road alignment agreement signed by the affected HHs
A Presentation to 06th QRM – April 2016

## Slide 24: Last quarters achievements:
Selection of trainees for technical training on road maintenance
Written tests on simple arithmetic were administered to select the trainees for the technical training on road maintenance
Over 100 candidates (Female – 15) drawn from the 03 payams covered by the road were tested & 07 participants selected.
A Presentation to 06th QRM – April 2016
Candidates for technical training undertaking the test

## Slide 25: Last quarters achievements:
Capacity building activities
Sectional road committees & central management committees received leadership skills training
115 participants received the training
Other training undertaken:
  Road safety awareness
A Presentation to 06th QRM – April 2016
# | Location | Gender |  | Total number of participants
 |  | Male | Female | 
01 | Malual North Payam | 16 | 05 | 21
02 | Malual West Payam | 57 | 08 | 65
03 | Mayom Angok | 23 | 06 | 29
Total |  | 96 | 19 | 115
CW staff undertaking leadership skills training for the road committees

## Slide 26: Implementation challenges:
Lack of adequate water:
  Many HHs could not participate in dry season cultivation due to lack of enough water
Economic downturn:
  Savings in VSLA’s gone down as priorities have changed due to economic situation.
Literacy levels:
  Low level of literacy affect the quality & way VSLA maintain their records.
Fear:
  Farmers – losing their money if they paid deposits for fabrication of the ploughs
  Agro-dealer - holding money if they brought ploughs without guaranteed market
Expectations:
  Farmers - CWW will pay for ploughs even when messaging was clear about the modality of getting the ploughs
  Lack of capital:
  Agro-dealers/ blacksmiths lacking enough capital to start off their activities
  Different approaches by different agencies in the same locations
A Presentation to 06th QRM – April 2016

## Slide 27: Lessons learnt:
Farmers & agro-dealers had a lot of expectation that the CWW would change the modality of operation with regards to plough. However continued sensitisation & mobilisation of the communities bore fruits & positive response has been realised looking at the number of ploughs that have been fabricated & bought by the farmers during the quarter
Involvement of the project management committees have helped address the challenge of agro-dealers/ blacksmiths thinking that CWW will pay for the ploughs
Adoption of animal traction is going to be taken to another level given the high demand for the ploughs by the farmers
The agro-dealers /blacksmiths in the locations where CWW is working have no capital to help them carry out this business. However with a little push they are able to do so much for themselves and the community they serve
A Presentation to 06th QRM – April 2016

## Slide 28: Synergies:
At Programme implementation level
  Standardization of approach on Agro-dealership with PIN & WHH implementing FSTP
  Standardization & harmonization of VSLA approach between SORUDEV, FSTP & BRACED projects – training for staff from CWW, PIN, WHH, LUYDA
  Information sharing & management, with FSL Partners e.g. Market information, FSL cluster report, assessments & baseline reports & extension training materials.
  Programme integration between SORUDEV & ZEAT-BEAD e.g. CWW is working with UNOPS in implementing the feeder road component.
  Use the same project implementing structures at community level to avoid duplication.
Promoting cooperation, coordination & collaboration
  Regular coordination meetings with LGA & stakeholders at State, County & Payam
  Participate in FSL cluster meeting with of the FSL partners.
  Work with line ministries during agriculture extension trainings & management of Nyamlell ADLC.
  Established MOUs with SMoAF & SMoARF to strengthen cooperation & coordination on Programme implementation.
Field level targeting
  Proper consultations with other FSL implementing partners on geographic areas and target beneficiaries to avoid duplication.
A Presentation to 06th QRM – April 2016

## Slide 29: Planned activities:
Technical training to the lead farmers & farmers on agricultural production
Form and Conduct community conversation forums at community level.
Refresher training of CAHWs on animal health & on business & marketing skills
Continue support to linking farmers and Agro-dealers/ blacksmiths
Establishment of marketing groups & value addition.
Training of marketing groups on business & marketing skills.
Vocational training for black smiths.
Training of tree nursery managers and provision of starter kits.
Programme monitoring & support supervision.
Conduct Project Management meetings at State, County & Payam level.
Construction of perimeter fence at Nyamlel ADLC & installation of drip irrigation
Conduct seeds fair at Payam level.
Promote seeds multiplication by farmers.
A Presentation to 06th QRM – April 2016

## Slide 30
Thank you listening
God bless you!
A Presentation to 06th QRM – April 2016