## Slide 1
6TH QUARTERLY REVIEW MEETING
GBEG RURAL DEVELOPMENT PROGRAMME
With funding by the European Union
ZEAT-BEAD / SORUDEV Project Managers’ Coordination Meetings Report
6th QRM, 26–28 April 2016, Grand Hotel, Aweil
European Union / South Sudan
Cooperation

## Slide 2
Background
Progress achieved
Challenges
The way forward
Presentation Outline

## Slide 3
1 - Background
25 November 2015, Amarula Lodge, Wau:
EU called a meeting with FAO, GIZ, UNIDO, HARD, NRC and TA.
It appeared that there was a need for closer coordination between Project Managers (PMs), and it was agreed:
A formal monthly meeting of PMs will be instituted
UNOPS feeder roads should guide geographical coverage of projects in the field
FAO, UNIDO, GIZ and UNOPS will collaborate to prepare a common integrated work plan listing common or related activities, allocated resources, and their geo-referenced locations at boma level
Each of the partners will communicate their nominated focal points at State and County levels and those of government counterparts and local authorities, and an integrated list will be prepared

## Slide 4
2 – Progress
07 December 2015, Amarula Lodge, Wau:
FAO, GIZ, UNIDO, HARD, NRC and AFOD held the first PMs Meeting. Several decisions were taken:
Meeting shall be called a Coordination Meeting and organised on first Tuesday of every month
Venue of meeting shall be on rotational basis and projects take responsibility for their organization
Every meeting shall begin with review of decisions made in previous meeting and review progress made since previous meeting
Draft outline of MoU was agreed upon, for synergies to be promoted among partners

## Slide 5
09 February 2016, GIZ-AMTIP Office, Wau:
GIZ, UNOPS, FAO, UNIDO, AFOD and HARD held the second PMs Meeting:
The outline of the MoU structure was finalised
All the organizations confirmed their willingness to identify areas of synergy with each other and develop them
It was agreed that a form to collect boma data from ZEAT-BEAD and SORUDEV partners will be finalised and circulated, before a Z-B/SORUDEV Coordination Workshop can be called to draw a common geographical coverage and clearly identify areas of synergy in the field
Two issues came up: (a) Should SORUDEV partners sign MoU with ZEAT-BEAD partners or not, owing to the difference in the lifespan of these two programmes? and (b) Whether each partner should have a focal person or should focal persons be identified for ZEAT-BEAD according to sector?
2 – Progress

## Slide 6
Structure of a Memorandum of Understanding (MoU) endorsed by the PMs Coordination Meeting of 09.02.2016
Preamble
Areas of coordination
Extension services development
Rural finance
Value chains for rural development
Coordinated communication with Government authorities
Harmonized communication with beneficiaries
Outputs of coordination
Harmonized approach for areas of interest
Common work plan for activities coordination
Sharing information on investment on coordinated activities
A map of coordinated activities
Coordination functions and operations
2 – Progress

## Slide 7
2 – Progress achieved
No | Subject | Achievement
1 | Monthly PM meeting instituted | DONE
2 | UNOPS feeder roads guide geographical coverage of projects | Using UNOPS and UNIDO infrastructure plan has enabled re-alignment of coverage area (case of FAO) . Issue: should WFP rehabilitated roads be also taken into account?
3 | A common integrated work plan | A model of MOU is in place (UNIDO-GIZ signed?) A database of geo-referenced boma is in progress.
4 | Focal points | Issues: At what level? Common focal points?

## Slide 8
2 – Progress achieved – case of FAO’s re-alignment of geographical coverage
State | County | Payam | Boma |  | State | County | Payam | Boma
Lakes | 1 Rumbek Centre | 1 Amongpiny Cuiadukani | 1 Adol Manyiel |  | Warrap | 8 Gogrial West | 12 Alek North | 41Adeer
 |  |  | 2 Meen |  |  |  |  | 42 Makuak Pagong
 |  |  | 3 Atok |  |  |  |  | 43 Panliet
 |  |  | 4 Mopeer |  |  | 9 Tonj North | 13 Akop | 44 Akob
 | 2 Wulu | 2 Bahr Gel | 5 Makoor |  |  |  |  | 45 Bundiir
 |  |  | 6 Kilo Saba |  |  |  |  | 46 Athieng
 |  |  | 7 Bahr Gel |  |  |  |  | 47 Pual Maguen
 |  | 3 Wulu | 8 Tonjo |  |  |  | 14 Awuul | 48 Aporlang
 | 3 Rumbek East | 4 Aduel | 9 Aduel |  |  |  |  | 49 Ageeny
Northern Bahr el Ghazal | 4 Aweil East | 5 Madhol | 10 Amarjal |  |  |  |  | 50 Pagakdit
 |  |  | 11 Amoth Akok |  |  |  |  | 51 Launoi Boma
 |  |  | 12 Dokul |  |  | 10 Twic | 15 Turalei | 52 Ayien Amuol
 |  |  | 13 Majok Yinthiou |  |  |  |  | 53 Tongliet
 |  | 6 Yargot | 14 Halbul |  | Western Bahr el Ghazal | 11 Jur River | 16 Kangi | 54 Ajugo
 |  |  | 15 Makuac Akuel |  |  |  | 17 Udici | 55 Achuol Guot
 | 5 Aweil North | 7 Malual North | 16 Gok-Machar |  |  |  | 18 Wadhalelo | 56 Wadhalel
 |  |  | 17 Malual Loch |  |  |  |  | 57 Aturo
 |  | 8 Malual West | 18 Kakou |  |  |  |  | 58 Bardogo
 |  |  | 19 Lolkou |  |  |  | 19 Wau Bai West | 59 Lol-Thou
 |  |  | 20 Mabior Nyang |  |  |  |  | 60 Akoon
 |  |  | 21 Majook Akok |  |  |  |  | 61 War-Cuai
 |  |  | 22 Mangar Aweit |  |  |  |  | 62 Bulic
 |  |  | 23 Mangar Bak |  |  | 12 Raj | 20 Uyu-juku | 63 Khor silik
 |  |  | 24 Mayom Angok |  |  |  |  | 64 Gonyo
 |  |  | 25 Nyiken |  |  |  |  | 65 Billi
 |  |  | 26 Panyic |  |  |  |  | 66 Uyu-juku South
 |  |  | 27 Warthou |  |  | 13 Wau | 21 Bagari | 67 Ugali
 | 6 Aweil South | 9 Nyocawan | 28 Mayom Lac |  |  |  |  | 68 Bringi
 |  |  | 29 Riang Maweel |  |  |  |  | 69 Ngolebo B
 |  |  | 30 Hong Wekdit |  |  |  |  | 70 Natabu
 |  |  | 31 Pagai |  |  |  | 22 Besselia | 71 Besselia
 |  |  | 32 Malual Aduet |  |  |  |  | 72 Gete
 |  | 10 Wathmouck | 33 Achuan |  |  |  |  | 73 Rihan Fei
 |  |  | 34 Majak Goi |  |  |  |  | 74 Ngobolo
 |  |  | 35 Nyocanoon |  |  |  | 23 Bussere | 75 Momoi
 |  |  | 36Pan Adhot |  |  |  |  | 76 Dukurongu
 |  |  | 37 Unkier |  |  |  |  | 77 Agok
Warrap | 7 Gogrial East | 11 Toch East | 38 Ajogo |  |  |  |  | 78 Ngoba
 |  |  | 39 Rout |  |  |  |  | 
 |  |  | 40 Thoramoun |  |  |  |  | 

## Slide 9
2 – Progress achieved – case of FAO’s re-alignment of geographical coverage
State | County | Payam | Boma | Potential synergy
Lakes | 3 Rumbek East | 4 Aduel | 9 Aduel | UNIDO-APC
Northern Bahr el Ghazal | 5 Aweil North | 7 Malual North | 16 Gok-Machar | UNIDO, UNOPS Lot 3
 |  | 8 Malual West | 18 Kakou | UNOPS Lot 3
 |  |  | 19 Lolkou | UNOPS Lot 3
 |  |  | 20 Mabior Nyang | UNOPS Lot 3
 |  |  | 21 Majook Akok | UNIDO, UNOPS Lot 3
 |  |  | 22 Mangar Aweit | UNOPS Lot 3
 |  |  | 23 Mangar Bak | UNOPS Lot 3
 |  |  | 24 Mayom Angok | UNIDO, UNOPS Lot 3
 |  |  | 25 Nyiken | UNOPS Lot 3
 |  |  | 26 Panyic | UNOPS Lot 3
 |  |  | 27 Warthou | UNOPS Lot 3
Warrap | 8 Gogrial West | 12 Alek North | 41 Adeer | UNIDO, UNOPS Lot 2
 |  |  | 42 Makuak Pagong | UNIDO, UNOPS Lot 2
 |  |  | 43 Panliet | UNIDO, UNOPS Lot 2
 | 10 Twic | 15 Turalei | 52 Ayien Amuol | UNIDO, UNOPS Lot 2
Western Bahr el Ghazal | 11 Jur River | 16 Kangi | 54 Ajugo | UNIDO, UNOPS Lot 1
 |  | 17 Udici | 55 Achuol Guot | UNIDO

## Slide 10
Maintaining regular meetings due to unavailability of PMs (they are too busy in their work so it is difficult for them to follow deadline of coordination meetings)
Different project time lines make it difficult for projects to easily work out common synergy (for example UNIDO & FAO)
Coordination vs implementation: How (and where) to keep the right balance between implementing the project along the agreement signed with EU and a more and more demanding PMs Coordination Meeting?
2 – Challenges

## Slide 11
2 – The way forward
The idea of PMs Coordination Meetings was an excellent one
There is a need to re-think the idea of the PMs Coordination Meeting in the light of its first months of existence (in terms of membership, frequency, interaction with TA…) to improve its effectivenes and efficiency
Some pending issues (should WFP rehabilitated roads be also taken into account? Focal persons, SORUDEV phasing out vs ZEAT-BEAD phasing in…) need to be addressed

## Slide 12
European Union / South Sudan
Cooperation