## Slide 1
Zonal Effort for Agricultural Transformation – Bahr El Ghazal Effort for Agricultural Development (ZEAT-BEAD)
With funding by the European Union
Quarterly Report: 2016 Quarter 1 of ZEAT – BEAD Project “Sustainable Agricultural Development through Strengthening Extension, Inputs Supply and Services” (EISS)
6th QRM, 26–28 April 2016, Grand Hotel, Aweil

## Slide 2
Background
Implementation of activities
Level of implementation of project
Administration & management
Problems & constraints
Work plan for next Quarter
Presentation Outline

## Slide 3
Background

## Slide 4
Background
The specific objective is to enable rural producers in the greater Bahr el Ghazal to increase agricultural production and productivity, as well as agriculture-based incomes on an economically viable and environmentally sustainable basis by enhancing the capacity of agro-dealers and private service providers to timely and continuously deliver required inputs, equipment and services in good quality and at competitive prices
The overall objective is to contribute to improved food security and income of the population of South Sudan

## Slide 5
Result1: Harmonized curricula for non-public Ext. w’kers & animal health service providers are defined, appropr. training expertise identified, & an Ext. standardizat. system established
Result 2: Understanding of the NALEP of both extension staff and non-public extension operators is enhanced and state-level extension support plans are developed
Result 3: A private sector driven system for the supply of inputs and equipment, as well as the marketing of produce is rolled out in the four states
Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states
4 Activities
2 Activities
4 Activities
6 Activities
Promote a more conducive institutional environment…
…for a sustainable impact in the field
Background

## Slide 6
Background
20 000 households of rural subsistence producers: from subsistence to commercial agriculture
1 000 producers’ groups: access to agricultural inputs through a coupon system combined to a cost-recovery mechanism
400 CBEWs and 200 CBAHWs: trained based on harmonized curricula and technical standards.
100 blacksmiths: supported to repair agricultural equipment & production spare-parts
Final beneficiaries

## Slide 7
Background
90 community seed producers and 40 traders/agro-dealers: trained & supported to satisfy producers’ needs in agricultural inputs
Extension staff of the state line ministries: capacities strengthened to backstop CBEWs and CBAHWs.
Period of implementation: Feb. 2015 – Jan. 2019
Budget: EUR 13 847 114 (with EUR 13 M by EU)
Final beneficiaries (cont’d)

## Slide 8
Implementation of activities

## Slide 9
Activities completed so far:
Implementation of activities
3 activities completed (/16 programmed):
Activities 1.1 and 3.1 concerning the assessment of extension services and Private sector supply & service delivery systems were completed during the baseline survey
Activity 4.6 concerned the development of an M&E plan for the project

## Slide 10
Activities completed during Quarter 1 of 2016:
Implementation of activities
8 activities were implemented including:
Activities | Sub-activities | Achieved
Result 1: Harmonized curricula for non-government extension workers and animal health service providers are defined, appropriate training expertise is identified and trained, and an extension standardization system is established in the four states |  | 
Activity 1.2: Develop harmonized curricula for the training of government and non-government extension practitioners and animal health care service providers | Develop TORs and recruit consultant to facilitate adapting of CTC & MLLTC curricula for community based extension training | TORs developed and advertised Selection in progress

## Slide 11
Activities completed during Quarter 1 of 2016:
Implementation of activities
Activities | Sub-activities | Achieved
Result 2: Understanding of the NALEP of both government extension staff and non-government extension operators is enhanced and state-level extension support plans are developed |  | 
Activity 2.1: Inform stakeholders of the NALEP and disseminate it among them | Seek formal approval for NALEP dissemination from MLFI & MAFCRD In collaboration with MLFI & MAFCRD develop 2-page NALEP brochures, banners and 15-page NALEP summary | Request submitted by FAO on 28/1/016 and approval granted by Minister of Agriculture on 14/4/2016 In progress

## Slide 12
Activities completed during Quarter 1 of 2016:
Implementation of activities
Activities | Sub-activities | Achieved
Result 3: A private sector driven system for the supply of inputs and equipment, as well as marketing of produce is rolled out in the four states |  | 
Activity 3.2: Support producers to access inputs to enhance their productive capacity | Develop TOR and select IP, Community mobilization, identification of beneficiaries and agro-dealers and preparations for the ITFs | TORs developed, and IPs selected (>7000 households targeted this year) Rest of the operation in progress
Activity 3.3: Establish cost recovery systems for beneficiary groups | Community mobilisation to introduce cost recovery mechanisms to beneficiaries | Forthcoming; To start as soon as activity 3.2 completed

## Slide 13
Activities completed during Quarter 1 of 2016:
Implementation of activities
State | Partner | ITF | FK | Total HHs
Lakes | Oxfam | 625 | 90 | 715
 | PI | 875 | 240 | 1115
NBEG | ACF | 300 | 120 | 420
 | CWW | 450 | 180 | 630
 | JAM | 500 | 480 | 980
Warrap | WVI | 300 | 300 | 600
 | SSGID | 1000 | 60 | 1060
 | NRC | 200 | 120 | 320
WBEG | AFOD | 550 | 510 | 1060
 | ACTED | 450 | 300 | 750
 | Total | 5250 | 2400 | 7650
Activity 3.2: targets of households (HHs) to be reached with seeds through Inputs Trade Fairs (ITFs) and Fisheries Kits (FK) with a cost-recovery system

## Slide 14
Activities completed during Quarter 1 of 2016:
Implementation of activities
Activities | Sub-activities | Achieved
Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states |  | 
Activity 4.1: Train CBAHWs to deliver treatment services at cost-recovery | Develop TOR, launch CfP for selection of IPs, select IPs Sensitize communities… Identify bomas/villages… Identify CAHWs … (totaling 200) Procure 200 CAHW kits, 15 solar fridges, 45 cool boxes… | TORs completed, CfP ready for advertisement Action to follow completion of 1) Action to follow completion of 1) Action to follow completion of 1) Action to follow completion of 1)

## Slide 15
Activities completed during Quarter 1 of 2016:
Implementation of activities
Activities | Sub-activities | Achieved
Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states |  | 
Activity 4.2: Support communities to establish and run 400 FFS in the four states; train CBEWs/facilitators | Develop TOR, launch CfP for selection of IP and select IP Develop TOR and recruit FFS Expert Conduct community awareness meetings to identify bomas/villages and introduce FFS approach in the 22 target payams | TORs prepared and CfP in progress Action to follow completion of 1) Action to follow completion of 1)

## Slide 16
Activities completed during Quarter 1 of 2016:
Implementation of activities
Activities | Sub-activities | Achieved
Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states |  | 
Activity 4.3: Enhance producers financial assets by promoting VSLAs | Develop TOR, launch CfP for selection of IP and select IP Conduct community awareness meetings to identify bomas/villages and introduce VSLA approach in the 22 target payams | TORs prepared and CfP in progress Action to follow completion of 1)

## Slide 17
Level of implementation of project

## Slide 18
Level of implementation of the project
Ref | Result description and Indicators | Overall target | Planned targets for 2016 Quarter 1 | Progress / Issues | Action Required
The overall objective: to contribute to improved food security and income of the population of South Sudan. |  |  |  |  | 
OO1 | Number of people (male and female) who become food secure | 12 000 HHs (60%) |  |  | 
OO2 | Increase in household income | 17 000SSP per HHs per year |  |  | 
The specific objective: to enable rural producers in the greater Bahr el Ghazal to increase agricultural production and productivity, as well as agriculture-based incomes on an economically viable and environmentally sustainable basis by enhancing the capacity of agrodealers and private service providers to timely and continuously deliver required inputs, equipment and services in good quality and at competitive prices |  |  |  |  | 
Report on the project based on the Logframe

## Slide 19
Level of implementation of the project
Report on the project based on the Logframe
Ref | Result description and Indicators | Overall target | Planned targets for 2016 Quarter 1 | Progress / Issues | Action Required
Result 1: Harmonized curricula for non-government extension workers and animal health service providers are defined, appropriate training expertise is identified and trained, and an extension standardization system is established in the four states |  |  |  |  | 
1.1 | Assessment of the extension delivery system conducted | 1 |  | 100% achieved during the Inception Phase | Nil
Result 3. A private sector driven system for the supply of inputs and equipment, as well as the marketing of produce is rolled out in the four states |  |  |  |  | 
3.1 | Assessment of private sector supply and service delivery systems | 1 |  | 100% achieved during the Inception Phase | Nil

## Slide 20
Administration and management

## Slide 21
Administration & management
Inception Report approved in February 2009 with recommendations on comments to satisfy
Position of Rural Finance Expert Officer was filled in early mid April 2016. The Officer was to assume duties on 18 April 2016, but travel is being delayed for security reasons
3 positions of Associate Extension and Training officers filled in Aweil, Kuajok and Rumbek; Wau yet to be filled
4 Positions for Associate Rural Finance Officers still not filled; were re-advertised; one was filled for Rumbek but resigned 5 months latter; the one Wau was identified for but never assumed duties for reasons of scholarship in Uganda.

## Slide 22
Problems and constraints

## Slide 23
Problems & constraints
Delay in having the Inception report finalized and approved has delayed the beginning of the implementation Phase.
Insecurity level raised, particularly in the Wau area has disturbed the planning of activity
Political instability has disturbed the launching of some of the activity in the field
The recruitment of a suitable national staff has continued to be a serious challenge, particularly for National Rural Associates

## Slide 24
Work plan for next quarter

## Slide 25
Work plan for next quarter
Activities | Sub-activities
Result 1: Harmonized curricula for non-government extension workers and animal health service providers are defined, appropriate training expertise is identified and trained, and an extension standardization system is established in the four states | 
Activity 1.2: Develop harmonized curricula for the training of government and non-government extension practitioners and animal health care service providers | Recruit a consultant to facilitate adapting of CTC & MLLTC curricula for community based extension training Establish committee to adapt CTC & MLLTC curricula for community based extension training Conduct 10 days workshop to adapt CTC & MLLTC curricula for CBEWs and CAHWs
Activity 1.3: Identify and strengthen extension training expertise | Identify and select TOTsS

## Slide 26
Work plan for next quarter
Activities | Sub-activities
Result 2: Understanding of the NALEP of both government extension staff and non-government extension operators is enhanced and state-level extension support plans are developed | 
Activity 2.1: Inform stakeholders of the NALEP and disseminate it among them | In collaboration with MLFI & MAFCRD develop 2-page NALEP brochures, banners and 15-page NALEP summary Print 5 banners, 500 brochures, 500 summary and 500 hard copies of NALEP Print 300 copies of each of the 3 sets of technical extension guides (900 total) Organize NALEP launching…

## Slide 27
Work plan for next quarter
Activities | Sub-activities
Result 2: Understanding of the NALEP of both government extension staff and non-government extension operators is enhanced and state-level extension support plans are developed | 
Activity 2.2: Support the development of NALEP-based extension support plans in the four states by extension department staff and non-government extension operators (NGOS, private sector operators) | Develop TOR and recruit consultant to facilitate extension work plan development based on NALEP Conduct 5-day workshops in each state for dissemination of NALEP and development of 4 state and 12 county extension work plans (invite state DGs, CAD and NGO staff)

## Slide 28
Work plan for next quarter
Activities | Sub-activities
Result 3: A private sector driven system for the supply of inputs and equipment, as well as marketing of produce is rolled out in the four states | 
Activity 3.2: Support producers to access inputs to enhance their productive capacity | Select IP, Community mobilization, identification of beneficiaries and agro-dealers and preparations for the ITFs Conduct of ITFs Monitoring of the use of inputs
Activity 3.3: Establish cost recovery systems for beneficiary groups | Community mobilisation to introduce cost recovery mechanisms to beneficiaries
Activity 3.4: Strengthen producers, agricultural inputs suppliers and service providers through a matching grant facility (MGF) | Identify implementation partners and establish steering committees (cont’d)

## Slide 29
Work plan for next quarter
Activities | Sub-activities
Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states | Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states
Activity 4.1: Train CBAHWs to deliver treatment services at cost-recovery | Develop TOR, launch CfP for selection of IPs, select IPs Conduct community meetings to create awareness on CAHWs and cost recovery approach in 31 target payams Identify bomas/villages for CAHW activities in the target payams ….

## Slide 30
Work plan for next quarter
Activities | Sub-activities
Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states | Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states
Activity 4.2: Support communities to establish and run 400 FFS in the four states; train CBEWs/facilitators | Develop TOR, launch CfP for selection of IP and select IP Develop TOR and recruit FFS Expert Conduct community awareness meetings to identify bomas/villages and introduce FFS approach in the 31 target payams Select and train 400 CBEWs/facilitators Conduct FFS group needs assessment and guide them to identify learning technologies

## Slide 31
Work plan for next quarter
Activities | Sub-activities
Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states | Result 4: A system for the delivery of good quality services including extension which strongly relies on the private sector is rolled out in the four states
Activity 4.3: Enhance producers financial assets by promoting VSLAs | Develop TOR, launch CfP for selection of IP and select IP Conduct community awareness meetings to identify bomas/villages and introduce VSLA approach in the 22 target payams Facilitate formation of 400 VSLAs

## Slide 32
European Union / South Sudan
Cooperation