## Slide 1
European Union / South Sudan
Cooperation
Funded by the European Union
Government of South Sudan
SOUTH SUDAN RURAL DEVELOPMENT PROGRAMME
Greater Upper Nile (GUN) and Greater Bahr el Ghazal (GBEG)
INTER-REGIONAL THEMATIC WORKSHOP
Theme :
"Transitioning From Emergency Response To Resilience Building: Is It Working "?
May 24 – 25, 2016

## Slide 2: Name of Presenter, Agency: Evans Owino, Programme Manager, Food Security and Livelihoods , HARD. Contract Reference: FED/2013/333-492 Project: SORUDEV Smallholder Food Security and Livelihoods Project 2014 - 2017
EU Pro-Resilience Action (PRO-ACT)
Juba, 24 - 25 May 2016
Outline
Extension Skills and Group Loans
1. Context.
2. Implementation.
3. Achievements.
4. Challenges and lessons learned.
Greater Upper Nile (GUN) and Greater Bahr el Ghazal (GBEG)
Inter-regional Thematic Workshop
WORKSHOP THEME
Transitioning from emergency response to resilience building: is it working ?
Two-day information sharing and learning and coordination workshop to Reflect on the strategies and progress of EU funded projects.

## Slide 3
1. Context.
Poor agronomic practices characterised by ‘slash-and-burn’ shifting cultivation.
There was no presence of government staff at the Payam and boma levels.
There were only 3 government extension staff based at the County i.e. one in each of the three Counties.
Very limited farmer-to-farmer learning was going on.
The target area is very vast with poor road network.
Farmers groups were not avenues for extension services.
Extension skills

## Slide 4
2. Intervention.
Community-based extension approach which was used in the past FSTP project was adopted.
48 CORPs, 2 from each of the 24 target bomas were selected and trained.
COPRs, Project and CAD staff form the County Extension System (CES).
CORPs are volunteers and their duties include; mobilising farmers in groups, managing demo farms, facilitate FFS, data collection, farm visits and role modelling.
FFS was adopted as the main approach in extension service.
5 satellite bases were set up in different locations to be closer to farmers.
Project area approach was used, i.e. project area zoned and assigned to different project staff.
In 2014, 12 additional government staff recruited and posted to Counties.
The project continues to provide transport and allowances to CAD staff.
Extension skills cont’d

## Slide 5
3. Achievements.
Improved access to extension services at boma level and fledgling referral system of extension services activated.
To date, there are 55 farmers’ groups (VSLAs, cooperatives and associations) which are avenues to provide extension services.
So far, 3,185 (M=1,756; F=1,129) farmers out of the 5,000 farmers have been reached through different extension methods.
At least 1,627 (M= 925; F=702) have adopted improved practices such as; animal traction, contour ploughing using animal traction, line planting, mixed cropping, compositing, using trash lines to control soil erosion, grain drying, cultural methods to control of pests and diseases.
At group level, extension is becoming demand driven.
COPRs continue to manage demo and bulking farms.
Extension skills cont’d

## Slide 6
4. Challenges and lessons learned.
Cultural barriers prevent women to work as CORPs i.e. only 3 out of 48 CORPs are women.
Up take of agronomic practices is low due to among other factors; illiteracy, lack of resources to invest in the farming and inadequate labour.
Absence of CAD staff at Payam level means support to CORPs is inadequate.
Innovative farmers and CORPs play a key role in scaling up innovations (in farmer-to- farmer extension).
Other agencies give incentives to Community-based workers which conflicts with our approach.
Insecurity in Wau County led to the suspension of activities.
Being volunteers, CORPs have different education levels thus training them as a group is sometimes poses a challenge.
Practical teaching in FFS approach and with demo farms are much more effective for farmers.
Extension skills cont’d

## Slide 7
1. Context.
There were minimal financial services at the Boma level, only few sanduks were available.
No micro-finance institutions that the project could partner with to implement agricultural loan scheme.
Farmers had no access to finances to purchase inputs at cultivation.
Inadequate investment in farming during cultivation time led to low agricultural production.
Cultivation period usually coincides with the lean season when food stocks are low, which require external resources.
Asset stripping was common during the cultivation season.
Group loans

## Slide 8
2. Successful Innovation.
The VSLAs and group loans were identified as vehicles to mobilise resources and improve access to agricultural finance.
VSLA operations began in October 2014 with staff training followed by training of groups.
After training, VSLAs were provided with basic items such as; stationary, cash box and padlocks.
Each member of the VSLA saves, takes out loans, repays loans with interest, and invests.
The project piloted a group loan scheme that supported 13 farmers groups with 298 farmers (M=168; F=130); selection was done by County Agriculture Committee .
The main target groups were; VSLAs (8) and farmers groups and associations (5)
A total of SSP 255,275 was disbursed to the groups in June 2015 at an interest of 15%.
The interest rate was set by representatives of County Agriculture Committees in February 2015.
The average loan amount per farmer was SSP856 which was equivalent to $100.
The loans were given to groups in one lump sum which they in turn disbursed to individual farmers.
Group loans cont’d

## Slide 9
3. Achievements:
The loans reached 93.6% of the farmers targeted, i.e. 279 farmers (M=157; F=122)
The loan usage was as follows: hire of labour (36%), purchase of inputs (25%), purchase of food (20%), hire of ox-plough (6%), construction of granaries (7%) and others (6%)
The total repayment rate has so far been 43%; i.e.11 groups/cooperatives have repaid a total of 125,879 SSP.
3 farmers groups have fully repaid the loan plus the interest.
Increased social capital, i.e. VSLA/group members have more trust in each other.
Anecdotal data indicate that loan beneficiaries achieved above average agricultural production compared to non-targeted farmers.
VSLA is not a resource-heavy program, groups need only training, stationary, and a metal lockbox to operate, and it revolves around skill acquisition and group generated capital.
Group loans cont’d

## Slide 10
4. Challenges and lessons learned.
Insecurity in Wau caused displacement of populations and thus the groups there are unable to repay the loans.
Risk of loan diversion, i.e. in some cases, the money paid to groups did not reach the farmers indicated in the loan application form.
There is high demand for agricultural loans, 123 applications were received totalling 1,765,900 SSP!
Training of groups in basic financial management is needed to improve management.
A simple but robust system of; selection, training and support, monitoring & data collection should be put in place to administer the group loan system.
Timing of loan disbursement is vital to avoid funds being diverted to other uses.
There is a potential multiplier effect through the reinvestment of the funds.
Group loan scheme represents one avenue to provide financing for the smallest of farms that is cost effective, community driven and proven to be scalable.
Group loans cont’d

## Slide 11
The end.
Thank you for your attention.