Key tasks and documents in the EC management cycle

| Programming – Tasks | Programming – Documents |
| --- | --- |
| Analysis of partner policies, priorities and capacities | Coutry strategy paper |
| Reviewing past and present projects/ programmes (EC and other donors) | Multiannual/National Indicative Programme |
| Strategic choice of a sector to support |  |
| Fixing the amount to be allocated and an indicative schedule of contributions |  |
| Identification – Tasks | Identification – Documents |
| Collecting and reviewing the relevant information to draft a project/project proposal, including the coherence with the priorities of national and sector policies |  |
| Deciding if the project drafted deserves deeper analysis and development (= pre-feasibility study) |  |
| If requested, preparing the ToR for a pre-feasibility study and the manage the study process | Pre-feasibility report |
| If the pre-feasibility study concludes positively on the project, preparing a Project Action document, including ToR for formulation phase |  |
| Evaluation and selection of a set of appropriate aid delivery methods |  |
| Submit the Action document to the oQSG for analysis and comment | Action document |
| Formulation – Tasks | Formulation – Documents |
| Based on the approved Identification Fiche, identifying the issues to be clarified and described more precisely |  |
| Preparing the ToR (as requested) to undertake the feasibility study and then manage the study process |  |
| Monitoring the feasibility study, assessing the content/quality of the study reports and then deciding the next steps | Feasibility report |
| Preparing a draft of financing decision |  |
| Submitting the draft Action document and draft TAP to oQSG for assessment | Draft Action document & Draft Technical and Administrative Provisions |
| Assessing the draft Action document (office Quality Support Group) | OQSG conclusions & recommendations |
| ## Financing Decision – Tasks | Financing Decision – Documents |
| Finalising the Action document according to oQSG comments | Annual Action Programme (AAP) |
| Launching the Inter-Service Consultation |  |
| Committee consultation for each instrument (representatives from Member States) | Memorandum and all the Action document for the AAP |
| Right of scrutiny of the European Parliament (1 month for the Parliament to consult the documents) |  |
| Green light by the Cabinet and launching the approval process |  |
| Adoption by the College |  |
| Preparing and Signing the Financing Decision | Financing Decision |
| Preparing and Signing the Financing Agreement (if applicable) | Financing agreement |
| Implementation – Tasks | Implementation – Documents |
| Launching the call for tender and contracting the necessary consultance/TA inputs | Documents related to the call for tender |
| Reviewing/approving the Anual action plans and budgets | Annual Action Plan |
| Taking part in steering committee of the project (as requested) | Monitoring and review reports |
| Conducting the continuous EC activities of monitoring, review and reporting. | Implementation report - CRIS |
| Evaluation & Audit – Tasks | Evaluation & Audit – Documents |
| Preparing ToR for the evaluation or audit | Evaluation report |
| Supervising/managing evaluation or audit | Audit report |
| Going from evaluation/audit recommendations to decision making |  |