Evaluation Network

‘Building an evaluation culture in DEVCO”

Narrative, diagram and logframe

Draft –2014

Narrative

Context

External

- Increasing scrutiny of aid effectiveness (Press; National Parliaments; Raised level of public awareness heightened by era of austerity in Western countries)

- Increased pressure on the Monitoring and Evaluation function and demand for transparent and evidence based results measurement

- Other donors’ agencies increasingly organising around results and evidence, creating standards  to which EU needs to respond .

EU institutional

- Agenda for Change (2011) ‘A4C’ emphasises : Results; Knowledge; Impact; placing greater demand on evaluation

- DG Letter to all Heads of Delegation January 2013, promoting :

  - Evaluation as part of the regular EU development toolkit

  - Developing links with other donors and to be more aware of their evaluation conclusions

  - Nomination of staff members to be evaluation correspondents

- DEVCO has established a knowledge sharing tool Cap4dev and is considering improving its knowledge management

DEVCO / Evaluation practice

- Uneven quality of project evaluations due to limited EUD capacity to manage project evaluations

- Lack of accessible materials on eval.

- Lack of capitalisation on evaluation findings to improve policy and practice

Rationale for Evaluation Correspondents Network

Recognition that:

- Evaluation needs to be perceived as something useful, creative and positive

- Information about evaluation needs to be easily accessible by staff

- Support needs to be provided to evaluation correspondents who seek to promote/share core messages and technical skills to colleagues and assist in evaluation processes.

- Evaluation support needs to reach operational staff in HQ and Delegation, more than it does at present

Need to contribute to build an evaluation culture in DEVCO, by creating and maintaining momentum around evaluation and developing evaluation capacity among the staff in Delegations and Headquarter

Objectives of the Network

To contribute to building an evaluation culture across DEVCO and improve the quality and use of evaluations;

through the creation and maintenance of a network of evaluation correspondents that will create momentum around evaluations and promote:

  - Awareness about evaluation use among DEVCO staff

  - Evaluation skills

  - Communication and interaction about evaluation results between Evaluation Unit, the Headquarter and Delegation and between Delegation themselves

Assumptions

Strategic assumptions

- Evaluation remains a priority for DEVCO Senior Management, and the Evaluation Network is seen to be supported by DEVCO Senior management so that adequate resources and energy are devoted to it.

- Network meets DEVCO staff needs and interest, the network content attracts its participant and respond to their needs

- Other corporate projects complement and contribute to shift towards a broad evaluation culture (PCM, Knowledge Management, Evaluation Policy, …)

- Evaluation correspondents are able to effect positive change within their Delegations

- The network is able to generate momentum on evaluation which affects the whole institution

- Focus on improving quality of evaluations will lead to greater use of evaluations

Operational assumptions

- Evaluation Unit Staff devote enough time and skills to develop the network

- Capacity for Dev is the appropriate support for communication

Inputs

- Evaluation Unit Staff & Skills – Planning and maintenance; Material collection and editing; Moderation of the network

- Content/materials – appropriate articles collected from both internal and external sources

- IT – C4D

Activities

- Start-up – 4 months

  - Design the concept

  - Create a Steering Group

  - Set-up the C4D Group

  - Establish Membership

  - Create an offer (content; planning; ….)

- Pilot activities – 4 months

  - Test the pilot offer (material, newsletter, debates, …)

  - Get feedback from the network

  - Adjust the offer

- Ongoing

  - Share evaluation methodology, findings and experience through blog-post and monthly newsletter

  - Establish feedback & reporting mechanisms

  - Ensure website maintenance and animation

Assumptions / Transforming inputs/activities into outputs

- Availability of sufficient Evaluation Unit Staff, and especially Evaluation Managers in charge of the network, to co-ordinate and manage the network

- Evaluation Unit Staff, and especially Evaluation Managers in charge of the network,  has the appropriate skills for network management

- Sufficient quality content available at appropriate level, accessible in time

- Priority for the network remains / Focus kept

Outputs

- Management and technical aspects of the network in place and functioning

  - Steering group established and functioning

  - C4D Online Group  running smoothly

- Network members identified and role clearly defined

  - active core group of contributing evaluation correspondents

- Reference material available (Methodology, examples, templates, ….)

- Newsletter produced regularly

- Feedback mechanisms established, to continuously make the available information stick to the correspondents needs and interests

Assumptions / Transforming outputs into outcomes

- Network has the ability to attract interest

- Evaluation correspondents are satisfied with the service

- Network reach and maintain the critical mass of active correspondents

- Network correspondents are given the right and incentives to invest time in the network

- C4D is the appropriate channel for communication

Outcomes

- Interactions between moderator and correspondents and correspondents themselves

- Improved communication on evaluation and findings within DEVCO, between Delegations, operational units, and between Delegation and HQ

- Development of a sense of community of practice amongst Evaluation correspondents

- Improved skills of evaluation correspondents within their Unit / Delegation

- Improved credibility of evaluation correspondents within their Unit / Delegation

Assumptions / Transforming outcomes into specific impact

- Network able to respond to evolving demand and ev. corresp. remain engaged

- Units and Delegations use correspondents to enhance their evaluation understanding and processes

- Ev.Corresp. are able to improve use & practice of evaluations in their unit/delegations

Specific Impact

- Improvement of evaluation understanding, skills and process within delegations and units through the evaluation correspondents

  - Better understanding of evaluation use and usefulness

  - Better general knowledge of evaluation methodology

  - Systematic set up of evaluation plans ate EUD/Unit level

  - ….

- Technical quality and use of evaluations improve

- Enhanced dissemination of evaluation findings across delegations

Assumptions / Transforming specific impact into impact

- Ev.unit and corporate environment is conducive (evaluation remains on DEVCO agenda)

Impact

- Evaluation culture and capacities are enhanced

- Evaluation is seen as a learning and necessary aspect of the EU development toolkit

Diagram

See PPT

Logical Framework

Draft

|  | Project description | Indicators & targets | Sources of verification |  |
| --- | --- | --- | --- | --- |
| Overall objectives | O.O.1. Improvement of evaluation understanding, skills and process within DEVCO | O.O.1.a Perception of DEVCO staff ‘evaluation understanding’ O.O.1.b Number of Delegation with an evaluation plan O.O.1.c Number of Delegations respecting their evaluation plan O.O.1.d Number of Unit with an evaluation plan | O.O.1. C4D Survey O.O.1.b EAMR – indicator XX O.O.1.c EAMR – indicator XX O.O.1.d - tbd |  |
|  | O.O.2. Improved technical quality and use of evaluations | O.O.2.a Perception by the correspondents… O.O.2.b perception by the strategic evaluation teams? O.O.2.c | Survey C4D Survey Strategic evaluation team Analysis…and comparison with the |  |
|  | O.O.3. Enhanced dissemination of evaluation findings across delegations |  |  |  |
| Specific objectives | S.O.1. Interaction between moderator-corresp. & corresp.-corresp. happening | S.O.1. … S.O.2. … | S.O.1. … S.O.2. … | - Network able to respond to evolving demand and ev. corresp. remain engaged - Units and Delegations use correspondents to enhance their evaluation understanding and processes - Ev.Corresp. are able to improve use & practice of evaluations in their unit/del |
|  | Improved communication on evaluation practice & findings among the evaluation corresp. |  |  |  |
|  | Development of sense of evaluation community of practice amongst corresp. |  |  |  |
|  | Improved evaluation skills of evaluation correspondents |  |  |  |
|  | Improved credibility of ev. correspondents within their unit/del. |  |  |  |
| Operational objectives | Management and technical aspects of the network in place and functioning |  |  | - Network has the ability to attract interest - Ev. Corresp. are satisfied with service - Network reach critical mass level of active participants - Ev.Corresp. can invest time in the network - The internet platform is the appropriate support for communication |
|  | Network members identified & clear role established |  |  |  |
|  | Feedback mechanisms established |  |  |  |
|  | OpO.1.Content (methodologies, templates, articles, …) available for evaluation correspondents. | OpO.1. … OpO.2. … | OpO.1. … OpO.2. Website metrics (conversion rate), n° of |  |
|  | Newsletter produced regularly |  |  |  |
| Activities | Design the concept |  |  | - Availability of sufficient Evaluation Unit staff to co-ordinate and manage the network - Appropriate skills of Evaluation Unit staff to launch and coordinate the network - Sufficient and quality material available to populate Newsletters - Within Evaluation Unit, priority for network remains |
|  | Test & adjust offer |  |  |  |
|  | 1.1.Put content on Cap4dev. | 1.1.Sufficient content on the network | 1.1. … |  |
|  | 2.1.Establish broad membership. | . 2.1.Target: make the remaining 45 out of86 evaluation correspondents member. | 2.1. Website metrics (n°visitors) |  |
|  | 2.2.Moderator feeds network. | 2.2.Regular activity (posts, e-meetings, set-up events,…) | 2.2. … |  |
|  | 2.3. Feedback and reporting mechanisms. | 2.3.Results of survey (to be launched in feb?) | 2.3. Survey |  |
|  |  |  |  | - Evaluation remains a priority for DEVCO senior management - Network meets DEVCO correspondents needs and interest - Other corporate projects complement and contribute to shift towards a broad evaluation culture (PCM, Knowledge Management, Evaluation Policy, …) - Evaluation correspondents are able to effect positive change within their Delegations - The network is able to generate momentum on evaluation which affects the whole institution - Focus on improving quality of evaluations will lead to greater use of evaluations - Evaluation Unit Staff devote enough time and skills to develop the network |