This action is funded by the European Union

ANNEX I

of the Commission Implementing Decision on the Annual Action Programmes 2015 in favour of Country Y, to be financed from the general budget of the European Union

Action Document for EU- Country Y Practical Partnership for Technical Vocational Education and Training Reform (TVET- PP) DCI-ASIE/2014/037-xyz

Information for Potential Grant Applicants Work Programme for Grants This document constitutes the work programme for grants in the sense of Article 128(1) of the Financial Regulation (Regulation (EU, Euratom) No 966/2012) in the following section concerning calls for proposals: 5.4.1.1 and in the following section concerning grant awarded directly without a call for proposals: 5.4.1.2.

| 1. Title/basic act/ CRIS number | EU- Country Y Practical Partnership for Technical Vocational Education and Training reform (TVET- PP). CRIS number: DCI-ASIE/2014/037-xyz financed under Development Cooperation Instrument |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 2. Zone benefiting from the action/location | Country Y The advisory team under component 1 will be located in Ministry of Education (MoE)'s premises in Capital City. |  |  |  |  |
| 3. Programming document | Multiannual Indicative Programme (MIP) for Country Y 2014-2020 |  |  |  |  |
| 4. Sector of concentration/ thematic area | Education focal area |  |  |  |  |
| 5. Amounts concerned | Total estimated cost: EUR 22,750,000 The EU contribution is for an amount of EUR 20,000,000 from the general budget of the European Union for 2015. This action is co-financed by: i) Council of Technical Education and Vocational Training (CTEVT) in Country Y for an indicative amount of EUR 550,000.00. ii) potential grant beneficiaries for an indicative amount of EUR 1,800,000 iii) Government of Country Y contribution in kind for an indicative amount of EUR 400,000 |  |  |  |  |
| 6. Aid modality(ies) and implementation modality(ies) | Project Modality Direct management mode: grants– call for proposal; grant– direct award; procurement of services. |  |  |  |  |
| 7. DAC code(s) | 11330 Vocational Education |  |  |  |  |
| 8. Markers (from CRIS DAC form) |  | General policy objective | Not targeted | Significant objective | Main objective |
|  |  | Participation development/good governance | ☐ | x | ☐ |
|  |  | Aid to environment | X | ☐ | ☐ |
|  |  | Gender equality (including Women In Development) | ☐ | x | ☐ |
|  |  | Trade Development | X | ☐ | ☐ |
|  |  | Reproductive, Maternal, New born and child health | X | ☐ | ☐ |
|  |  | RIO Convention markers | Not targeted | Significant objective | Main objective |
|  |  | Biological diversity | X | ☐ | ☐ |
|  |  | Combat desertification | X | ☐ | ☐ |
|  |  | Climate change mitigation | ☐ | x | ☐ |
|  |  | Climate change adaptation | ☐ | x | ☐ |
| 9. Global Public Goods and Challenges (GPGC) thematic flagships | NA |  |  |  |  |

Summary: The proposed action is in line with the specific objective n. 6 of the MIP for Country Y 2014-2020: "Strengthening the Vocational Training System". TVET-PP will act as a catalyst for an improved Government led coordination within the TVET sector in Country Y, contribute to the implementation of the Government of Country Y's (GoY) policies and enhance the quality, the relevance and the access to TVET, in view of achieving the overall objective to contribute to Country Y's inclusive and sustainable growth through investment in human capital and by creating better employment opportunities.

The specific objective is to formulate and implement more effectively a TVET policy responsive to labour market needs  and pilot an integrated Public Partnership Approach in three key economic sectors  i) agriculture (commercial farming and food production), ii) constructions, iii) tourism.

TVET- PP expected results are:

1. Coordination role of the GoY in the TVET system enhanced and TVET governance improved;

2. Quality of the TVET provision and implementation scaled-up and reach out to the most disadvantaged ensured;

3. Innovative PPP models to expand relevant TVET provision in Country Y tested.

# Context

## Sector/Country/Regional context/Thematic area

The UNDP Human Development Report (2014) states that Country Y, with a population of 15.9 million people, ranks 174 out of 187 countries on the Human Development Index (HDI), the lowest in the region. High population growth (2.87%) with a significant footprint on the environment, a deteriorating education system, a lack of decent work, high levels of unemployment and a HIV/AIDS prevalence with a major impact on health and mortality, are the main determinants for low life expectancy (55.3 years) and widespread poverty. In 2013, it was estimated that 62% of the population lived below the income poverty line and 29.8% lived in severe poverty - the majority of those ultra-poor households (living on US$1.25 per day or less) are female or child headed households.

The growth in Y’s GDP in 2013 was 5% and the services sector constituted the largest share of GDP (51.7%) followed by Agriculture (29.4%) and Industry (18.9%) but in practical terms Y's economy remains predominantly agricultural, with about 90% of the population living in rural areas and engaged in household farming. The country depends on substantial inflows of economic assistance from Development Partners (DPs) and it is estimated that more than a quarter of the budget is being funded by external assistance.

Country Y emphasizes development of the TVET sector as one of the engines of economic growth and employment. It believes that a workforce trained with skills in line with the needs of the labour market is an asset for improved enterprise productivity, as well as providing employment opportunities for the jobless. Around 83% of Country Y’s population aged 15–59 are economically active and 4.2 million are under-employed. More than 450,000 people enter the Country Y job market yearly, while around 1,200 leave Country Y every day for (mostly unskilled) employment elsewhere – often in poor and dangerous conditions and with unreliable rewards. More than 70 per cent of the economically active population is involved in the informal economy and the deficit in formal labour demand (insufficient job creation) is means it cannot absorb the still high level of informality. The estimated per capita income is around US$750, the lowest in the region, as is labour productivity, while income disparity is high. For poverty to be halved it is estimated that some 3 million jobs would need to be created.

### Public Policy Assessment and EU Policy Framework

Country Y’s national plans and policies recognise the importance of the TVET sector for economic growth. Country Y’s 2012 TVET policy puts inclusion, relevance and expansion at the heart of making the TVET system accessible and market-oriented, in line with contemporary international practice .The main long-term developments proposed in the policy include:

- The expansion of TVET institutes across Country Y;

- The development of model institutes and greater autonomy for public training institutions;

- The development of a national vocational qualifications framework and transformation of the National Skill Testing Board into a national vocational qualifications authority;

- The establishment of a rigorous and transparent system for quality assurance; and

- The introduction of an integrated financing mechanism.

The Council for Technical Education and Vocational Training's strategic plan (2014-2018) provides a framework for the development of national policies to address the challenges of the TVET sub-sector supporting socio-economic development and promoting technology in business and enterprises.

In addition, the approach paper for the 13th Development Plan 2013/14-2015/16 of the GoY includes proposals for reforming the TVET sector.

The proposed intervention fully complies with the EU policy framework.  It is in line with the MIP 2014-2020 for Country Y and in particular with its specific objective n. 6: "Strengthening the Vocational Training System". The programme's strategy is inspired by the principles of the 2014 EU Communication "Stronger Role of the Private Sector in Achieving Inclusive and Sustainable Growth in Developing Countries" and aligned to its action 3 aiming to support alliances between companies and relevant training providers to develop and implement demand-driven technical and vocational education and training programmes. Finally, it embraces the value of the Agenda for Change and of the Commission Staff Working Document: "More and Better Education in Developing Countries".

### Stakeholder analysis

The main stakeholders engaged in TVET development in the country are:

- Several ministries, particularly the MoE, the Ministry of Finance (MoF), the Ministry for Labour and Employment (MoLE), Ministry of Agricultural Development (MoAD), Ministry of Industry (MoI) and Ministry of Culture, Tourism and Civil Aviation (MoCTCA).

- The CTEVT and its divisions. CTEVT is the apex body of the TVET sector in Country Y with the mandate for policy formulation and implementation, quality control, curriculum development, occupational skill standards development and testing, conducting various research studies and training needs assessments.

- The Training Institute for Technical Instruction (TITI) which is being transformed into a centralised centre of excellence for the training and development of vocational education teachers.

- TVET providers. Formal TVET in Country Y is offered through 26 public institutes, 75 vocational units attached to district secondary schools, and over 450 privately run, publicly affiliated training providers. Many small unaffiliated providers offer informal training, and traditional apprenticeships offer informal learning on the job.

- Private sector organisations (enterprises, business associations etc.) in Country Y.

- Job seekers in both formal and informal sector, especially youth, women and other members of disadvantaged groups.

- The selected economic sectors (food production and commercial farming, construction and tourism).

### Priority areas for support/problem analysis

The TVET system in Country Y faces constraints and weaknesses in key areas including capacity, relevance and quality, access and participation, and governance and management.

Governance and management: the TVET structure in Country Y is highly fragmented. The MoE has the overall responsibility in the TVET sub-sector and the CTEVT has been mandated by the CTEVT Act for all the regulatory and delivery functions. CTEVT has the responsibility to coordinate all training along with educational programmes related to the preparation of a basic, middle and higher level skilled workforce. However, despite the authority given to CTEVT to coordinate and facilitate the preparation of a skilled workforce in Country Y, several ministries and some private bodies implement skills training programmes and much of this, including curricula and occupational standards, is uncoordinated so that the overall TVET system is fragmented and dysfunctional. 	                                                                                                                                                                                                                    Quality and relevance: the existing TVET system is supply driven. The majority of TVET curricula are not updated to address market demand, and learning materials including relevant textbooks are inadequate. The role of the private sector in developing curricula in order to prepare the workforce to meet their demands is seldom fulfilled, and a consolidated reliable database and labour market information is missing. In light of the fact that the establishment of a labour market information system (LMIS) has been attempted several times with limited or no success in Country Y, alternative and innovative solutions need to be identified to address this constraint. There is anecdotal evidence that many training opportunities exist in the informal sector, but these are not organised through any explicit curriculum or accredited instructors.  There is no clear plan to develop human resources in the TVET sector and the result is a lack of competent and motivated instructors in TVET schools, particularly in the remote areas. All this contributes to not fully grasp the potential of TVET which is perceived as having low social status and is only an option of last resort.

Access and Participation: Due to limited access to TVET facilities, those below the poverty line and ultra-poor, school drop-outs, people with disabilities, marginalised females and particularly people from remote areas still lack opportunities to obtain marketable skills for self/employment or starting enterprises. There is a need for a deliberate commitment to deliver TVET activities nationwide, not only in easily accessible areas.

Capacity: The vocational education and training capacity of the government has fluctuated over the years and is highly dependent on the donor-funded TVET projects under implementation. CTEVT has a capacity to enrol 14,286 students in Technical School Leaving Certificate (TSLC) programmes and 13,264 in Diploma programmes, while short term vocational skills training and longer duration TVET programmes together have a combined capacity of less than 100,000. As more than 450,000 young people enter the labour market every year, the opportunities offered by the TVET system are much fewer than required. In a situation where the majority of students drop out before completing secondary education, and the share of people with people with a degree level is still very low, Country Y needs to find new ways of developing people's skills and employ them at a larger scale.

# Risks and Assumptions

| Risks | Risk level (H/M/L) | Mitigating measures |
| --- | --- | --- |
| Lack of intra-governmental cooperation on TVET. | M | TVET-PP will serve as a platform for effective coordination within the sector. Support agreed cooperation modalities to implement the reforms among TVET stakeholders. Strengthening CTEVT so that its leadership role in TVET is effectively recognised. |
| Unwillingness of large parts of the private sector to participate in TVET reforms namely by: building curricula, offering internship and apprenticeship programmes, designing and providing market-oriented training, financing of the TVET sector etc. | L | Strengthen dialogue with the private sector; better focus on the industry sectors where employers show interest and where businesses themselves show growth (or potential) and are in need of improving international competitiveness; PPP will be encouraged and supported. TVET information campaign will contribute to raise the status of TVET in the country and therefore to make the sector more attractive for private investments. |
| Lack of cooperation from private TVET institutions and non-formal training providers | L | Capacity building activities designed for TVET providers and training of trainers in both formal and informal sector. |
| Donor overlap and weak coordination | L | Regular exchanges with other donors and Government; use the TVET coordination group as an effective platform for exchange; TVET-PP monitoring system establishment of an effective monitoring system within the sector within the sector. |
| Assumptions |  |  |
| It is assumed that the commitment to the TVET policy will be maintained and that CTEVT will decide to apply the TVET-PP approach beyond the three (agricultural, construction, tourism) selected sectors. Other assumptions cover the readiness of the Ministries, other than the MoE, and the apex organisations in the three designated sectors to cooperate and participate and the promulgation of the Constitution. |  |  |

# Lessons learnt, complementarity and cross-cutting issues

## Lessons learnt

This is the first EU programme in support of the TVET sector in the framework of bilateral cooperation with Country Y, although there has been earlier support at a project level through thematic instruments mainly targeting skills development and VET in the informal sector. A general conclusion from these successful interventions (such as the "Skills Development and Employment Project for the Informal Sector (SEIS)" implemented by Helvetas and the "High Impact Tourism Training Programme (HITT)" implemented by SNV) is that the link between relevant skills development and concrete job opportunities in Country Y needs to be strengthened.

The main ‘lessons learned’ from other donor experiences of TVET in Country Y include:

- High fragmentation and weak coordination within the sector. Sustainable solutions to address TVET challenges require strong Government leadership.

- Reaching out to members of disadvantaged groups is a challenge.

- The private sector participation in TVET remains limited.

These lessons are thoughtfully applied in the proposed TVET-PP intervention.

## Complementarity, synergy and donor coordination

Given the increased recognition of the TVET sector as one of the engines of inclusive and sustainable economic growth and social development in Country Y, several initiatives have been launched by various actors in support of the sector. However, many of these initiatives are not comprehensive as they do not cover all aspects of the 2012 TVET Policy. TVET-PP directly addresses the context of TVET reform in Country Y and in particular, supports the strategic and institutional frameworks designed by the GoY which designates CTEVT as the legitimate and competent TVET coordinating authority.

TVET-PP aims to coordinate with all key actors to efficiently link together and “top-up” as necessary for complementarity in actions, thereby addressing TVET challenges with a synergistic approach while avoiding overlap and duplication of efforts in support of the GoY.

The following describes the main ongoing and planned TVET initiatives in Country Y.

The Skills Development Project funded by the ADB (2013-2018; US$ 20 million) aims to support the government in implementing key aspects of the TVET Policy 2012 by: (i) initiating strategic reforms that aim to improve overall management and performance of the TVET system, (ii) improving the quality and relevance of public training, and (iii) increasing private sector engagement in training delivery and job placement.

The Enhanced Vocational Education and Training Programme of the World Bank (2011-2015; US$ 50M) aims to expand the supply of skilled and employable labour force by: (1) increasing access to quality TVET programmes; and (2) strengthening the TVET system in Country Y.

The Employment fund (2011-2015; USD 7.9 million), supported by the Swiss Agency for Development and Cooperation (SDC), Department for International Development (DFID) and the World Bank enables short term trainings and micro enterprise development for economically poor and socially discriminated youths.

The Support to the National qualification System in Country Y ( 2015-2020; CHF 4 million) is a new SDC project which aims at strengthening the capacity of the National Skill Testing Board (NSTB) in regards to its performance and for its gradual transformation in  National Vocational Qualifications Authority (NVQA) in future. SDC is also designing a new 10-year intervention to minimize the gap between supply and demand of TVET skills for an amount of CHF 25M.

Korea International Cooperation Agency (KOICA) is formulating a new project in support of the Training Institute for technical Instruction (US$ 5 million).

TVET-PP will also build synergies with the forthcoming EU intervention in the rural development and with the new EU funded study: "Country Y TVET sub-sector analysis” which complements the start-up of the TVET-PP by providing consistent baselines and data for the monitoring and evaluation framework of TVET-PP. Complementarity and synergies with existing and new initiatives funded by thematic instruments will also be ensured.

The donor coordination for TVET in Country Y takes place in the TVET donor group currently chaired by SDC. In addition, a thematic working group on vocational training and soft skills under School Sector Reform Plan (SSRP) is in place.  Despite quite regular TVET donor group meetings, the coordination in the sector remains rather weak.

## Cross-cutting issues

## The following cross-cutting issues are mainstreamed in the TVET-PP strategy:

- (a) Social inclusion and equality of opportunity. The programme will ensure that TVET provides opportunities for disadvantaged groups to fulfil their potential by among others, developing participatory TVET learning for less/ uneducated disadvantaged people and expanding the TVET offer in rural and remote areas. In particular, TVTE-PP will i) work together with CTEVT in expanding the TVET programmes in remote areas by increasing the number of technical schools and the scholarship scheme for the needy people with special quota for remote/ discriminated people and women; ii) conduct awareness programme to sensitize disadvantaged groups to TVET programmes; iii) give preference to disadvantaged groups in the call for proposals (CfP) by including special provisions in the guidelines to facilitate the reach out to vulnerable and marginalised people ( e.g. geographical focus on remote areas, development of specific modules for disadvantaged groups; post-training support for self-employment and job placement etc.). The expansion of TVET services to vulnerable groups will be monitored closely by the TVET-PP monitoring panel throughout the programme.

- (b) Gender equality will be an explicit TVET-PP strategy, from the numbers participating in training activities through to issues of curriculum and learning materials, occupational stereotyping and responsiveness to cultural prohibitions.

- (c) The intervention aims also to improve mechanisms for social dialogue, particularly between employers and their associations, the TVET system (including CTEVT and TVET providers) and local community and worker representative groups.

- (d) The improvement of relevance and quality of TVET in Country Y will aim at integrating best environmental practices and supporting sustainable national economic development.

# Description of the action

## Objectives/results

The overall objective is to contribute to Country Y's inclusive and sustainable growth through investment in human capital and by creating better employment opportunities.

The specific objective is to formulate and implement more effectively a TVET policy responsive to labour market needs  and pilot an integrated Public Partnership Approach in three key economic sectors  i) agriculture ( commercial farming and food production, ii) constructions, iii) tourism.

The expected results are as follows:

- Role of the GoY in the TVET system enhanced and TVET governance improved;

- Quality of the TVET provision and implementation scaled-up and reach out to the most disadvantaged ensured;

- Innovative Public-Private Partnership models to scale-up relevant TVET provision in Country Y tested.

## Main activities

For each result the main activities include:

R1: Provide support to GoY in:

- establishing a TVET coordination mechanism at national level under the GoY leadership;

- implementing the TVET reform through agreed cooperation modalities among TVET stakeholders;

- preparing for a sector-wide approach in close coordination with other donors;

- setting-up a monitoring panel to:

i) conduct a comprehensive baseline study at programme's outset;

ii) pilot a skills demand and supply information tool in each of the 3 key economic sectors. In the TVET-PP model the national federations for agriculture, tourism and construction, with the support of the monitoring panel, will have the major responsibility for collecting and providing skills demand and supply data by occupations, skills and training needs as required. Data from these apex associations will be linked with CTEVT’s Research and Information Division, and the consolidated information will be available for national level planning in a sustainable way;

iii) regularly review TVET reform progress.

- developing policy guidelines, materials and tools on the TVET practical-partnership approach to guide government agencies, industries, NGOs, providers and development partners (DPs) and all TVET stakeholder. The guidelines will also look at the TVET financing.

- organising national and international workshops and seminars to disseminate good practices in different areas of TVET (e.g. governance, planning, financing and delivery);

- conducting major information campaigns to raise the status and the attractiveness of TVET across Country Y. The campaign will promote the new image of the TVET sector, raise its profile and increase awareness of opportunities for obtaining employability through TVET.

- supporting in the preparation of the call for proposal under the component 3.

R2: In line with the CTEVT strategic plan 2014-2018:

- to improve the human resources management (HRM) system (CTEVT staff, teachers and managers of centres)

- to upgrade the Financial Information System ( FMIS) and the Integrated Training Management System (ITMS);

- to develop teaching and training resources, learning materials  including textbooks and training manuals;

- to develop and revise curricula as per market needs in close collaboration with the private sector;

- nationwide upgrading of public trainers and of selected CTEVT technical schools and training centres;

- to organise meetings, seminars, workshop and conferences in Country Y for sharing and learning experiences and innovations;

- to enhance the relationship with international TVET institutions through participation in international seminars and workshops ( within the SAARC region or in Europe) with the objective to share best practice in TVET provision.

- communication; monitoring and research.

R3: in each of the 3 key economic sectors:

- TVET-PP will explore innovative approaches and participatory and sustainable methodologies to pilot sustainable PPPs models for TVET. Private sector's participation in planning, provision and financing will add value by making the TVET system responsive to labour market needs and enriching it with specific capabilities and expertise, innovative approaches and technologies ( e.g. introduction of an apprenticeship/internship system to provide TVET learners with work experience; in-service training for current workers; provide experts from employers to be used as part-time trainers or guest lecturers in the TVET institutions; joint management of vocational schools/centres by public and private sectors; development of business-school partnership agreements etc.).

- To make all this happen, activities to strengthen the capacity of the formal and informal private sector to serve as partners for Government will be also supported at an initial stage of the process.

- A strategy to increase awareness of companies of skill training's benefits will be elaborated in order to encourage private sector's investment in skills training and upgrading.

## Intervention logic

The proposed intervention has a strong potential for scaling up beyond its initial scope. Indeed, TVET- PP focuses on 3 crucial pilot sectors with high potential for replication in other sectors. TVET-PP will act as a catalyst for an improved coordination within the TVET sector in Country Y. Through an effective multi-stakeholder approach, the programme strategically aims to enhance the leadership of the GoY, together with increased monitoring of the sector, as well as improved coordination of the many actors involved, thus enhancing sustainability beyond the project cycle.  Facilitating movement towards the TVET Fund, strengthening CTEVT’s role within the context of the National TVET Policy, supporting PPPs, and encouraging private investments in TVET will also contribute to the sustainability of the action.

# Implementation

## Financing agreement

In order to implement this action, it is foreseen to conclude a financing agreement with the partner country, referred to in in Article 184(2) (b) of Regulation (EU, Euratom) n. 966/2012.

## Indicative implementation period

The indicative operational implementation period of this action, during which the activities described in section 4.1 will be carried out and the corresponding contracts and agreements implemented, is 72 months from the date of entry into force of the financing agreement.

Extensions of the implementation period may be agreed by the Commission’s authorising officer responsible by amending this decision and the relevant contracts and agreements; such amendments to this decision constitute technical amendments in the sense of point (i) of Article 2(3)(c) of Regulation (EU) No 236/2014.

## Implementation of the budget support component- not applicable

## Implementation modalities

The Programme will be implemented under direct centralised management as follows:

R1: Service contract (through a call for tender) - module 3;

R2: Direct grant to CTEVT- module 2;

R3: Call for proposals- module 1.

#### Module 1 Grants- call for proposals "To test innovative Public-Private Partnership models to scale-up relevant TVET provision in Country Y"

(a) Objectives of the grants, fields of intervention, priorities of the year and expected results

The major purpose of the call for proposals is to address result 3 of TVET-PP and contribute to the establishment of a TVET system that can respond to the needs of the labour market by providing well skilled and employable workers in selected economic sectors through pilot sustainable PPPs models. The actions implemented under result 3 may also relate to the provision of TVET in relation to the informal sector. In each of the three sectors the indicative eligible actions may contribute to:

- To support enabling capacity building of the private sector (employers, employer associations, etc.) for effective Public-Private Partnership;

- To promote networks/ partnerships among TVET stakeholders (CTEVT, employers, TVET providers, NGOs etc.) to join forces and exchange ideas for significant improvements in TVET provision in formal and informal sector;

- To upgrade the capacity and the competencies of existing workers in the formal and informal sectors in order to boost the productivity and competitiveness of informal and formal sector enterprises;

- To enhance the links between the training for the informal economy and the formal TVET system;

- Development of participatory learning for less/uneducated disadvantaged groups in rural and remote areas and unemployed youth.

(b) Eligibility conditions

In order to be eligible for a grant, the applicant must:

-	be a legal entity,

-	be a NGO or network of NGOs, private non-for-profit and for profit educational/ training institutions, organisations from private sector (enterprises, employers, workers' federations and chambers of commerce with affiliated training institutions etc.);

-	be established in an eligible country in accordance to in the EU Regulation No 233/2014;

-	be directly responsible for the preparation and management of the action with the co-applicant(s) and affiliated entity (ies), not acting as an intermediary;

- to comply with the legislation of Country Y in force in the relevant context of the activities and the project.

Subject to information to be published in the call for proposals, the indicative amount of the EU contribution per grant should be EUR 3 million and the grants may be awarded to sole beneficiaries and to consortia of beneficiaries (coordinator and co-beneficiaries). Any grant awarded under this Call for Proposals must fall between the following minimum and maximum amounts:

-minimum amount: EUR 3 million

-maximum amount: EUR 9 million

The indicative duration of the grant (its implementation period) is 48 months.

(c) Essential selection and award criteria

The essential selection criteria are financial and operational capacity of the applicant.

The essential award criteria are relevance of the proposed action to the objectives of the call; design, effectiveness, feasibility, sustainability and cost-effectiveness of the action.

(d) Maximum rate of co-financing

The maximum possible rate of co-financing for grants under this call is

- 90% of the total eligible costs of the action in the case of Country Yi applicant and

- 80% of the total eligible costs of the action in case of non-Country Yi applicant.

(e) Indicative timing to launch the call: 3rd trimester of 2016.

(f) Exception to the non-retroactivity of costs: not applicable.

#### Module 2: Grant- direct award to CTEVT to scale up the quality of the TVET provision and implementation and to ensure the reach out to the most disadvantaged

(a) Objectives of the grant, fields of intervention, priorities of the year and expected results

The specific objective of the grant is to scale-up the quality of the TVET provision and implementation and to ensure the reach out to the most disadvantaged, following result 2 of TVET-PP. In line with the CTEVT strategic plan 2014-2018, indicative areas of support may include: system development; staff development; nationwide upgrading of public trainers and of selected CTEVT technical schools and training centres; TVET methodology development; curriculum revision; teaching and training resources and learning materials including textbooks; communication; monitoring and research; establishment of a TVET knowledge sharing platform; enhancement of the relationship with international TVET institutions                    ( within SAARC region and in Europe). Strong emphasis will be placed on enabling CTEVT to determine priorities, plans, and evaluate a wide range of demand-driven training activities in order to become generally recognised as the legitimate and competent TVET coordinating authority.

(b) Justification of a direct grant

Under the responsibility of the Commission’s authorising officer responsible, the grant may be awarded without a call for proposals to the Council for Technical Education and Vocational Training.

Under the responsibility of the Commission, the recourse to an award of a grant without a call for proposals is justified because the action has specific characteristics requiring a specific type of beneficiary for its administrative power.

(c) Eligibility conditions: not applicable.

(d) Essential selection and award criteria:

The essential selection criteria are the financial and operational capacity of the applicant.

The essential award criteria are relevance of the proposed action to the objectives of the programme; design, effectiveness, feasibility, sustainability and cost-effectiveness of the action.

(e) The maximum possible rate of co-financing for this grant is 90%.

(f) Indicative trimester to conclude the grant agreement: 1sttrimester of 2016.

(g) Exception to the non-retroactivity of costs: not applicable.

#### Module 3:  Procurement to enhance the coordination role of the GoY in the TVET system

A tender will be launched for the recruitment of the Advisory Team which will facilitate the activities under result 1 and ensure the coherence of the whole project's structure. The tender may be published, if necessary with a suspensive clause concerning the adoption of the Commission decision and/or the signature of the Financing Agreement.

The Advisory Team will be located in the MoE's premises and shall include at least 4 key experts: 3 senior experts and 1 junior expert:

- 1 senior expert/ team leader in charge of the capacity building activities for improved governance and coordination;

- Monitoring Panel (1 senior expert and 1 junior expert);

- 1 senior expert in charge of TVET information campaign.

The experts will be assisted in the implementation of the activities by a number of non-key experts in pre-defined areas.

| Subject in generic terms, if possible | Type (works, supplies, services) | Indicative number of contracts | Indicative trimester of launch of the procedure |
| --- | --- | --- | --- |
| Technical Assistance to MoE | Services | 1 | 3rd trimester 2015 |
| Communication and visibility | services | 1 | 2th trimester 2016 |
| Final evaluation (pre-completion) | services | 1 | 4th trimester 2021 |

## Scope of geographical eligibility for procurement and grants

The geographical eligibility in terms of place of establishment for participating in procurement and grant award procedures and in terms of origin of supplies purchased as established in the basic act and set out in the relevant contractual documents shall apply.

The Commission’s authorising officer responsible may extend the geographical eligibility in accordance with Article 9(2) (b) of Regulation (EU) No 236/2014 on the basis of urgency or of unavailability of products and services in the markets of the countries concerned, or other duly substantiated cases where the eligibility rules would make the realisation of this action impossible or exceedingly difficult.

## Indicative budget

| Module | EU contribution (amount in EUR) | Indicative third party contribution, in EUR |
| --- | --- | --- |
| 5.4.1.1 Module 1: Grants- call for proposal- direct management | 9 000 0000 | 400 000 In kind contribution |
| 5.4.1.2 Module 2: Direct grant to CTEVT- direct management | 5 500 000 | 550 000 |
| 5.4.1.3 Module 3: Services ( Technical Assistance)- direct management | 5 100 000 | 1 800 000 |
| Evaluation, Audit | 150 000 | N.A. |
| Communication and visibility | 150 000 | N.A. |
| Contingencies | 100 000 | N.A. |
| Totals | 20 000 000 | 2 750 000 |

## Organisational set-up and responsibilities

Under the TVET-PP model, the CTEVT will be supported to play an enhanced coordinating role at the technical level and MoE at the policy and strategic level in line with the 2012 TVET policy. A Steering Committee (SC) may be established not only to oversee and facilitate TVET-PP's implementation but its role would be that of representing a real platform for improved coordination among all TVET stakeholders. Tentatively, the SC may be chaired by the MoE Secretary or his representative and the EU Delegation. It may be include senior officials from relevant Ministries: Ministry of Finance, the Ministry of Finance, the Ministry for Labour and Employment, Ministry of Agricultural Development, Ministry of Industry and Ministry of Culture, Tourism and Civil Aviation, along with representatives of the private sector (such as Federation of Country Y’s Chambers of Commerce and Industries, European Economic Chamber- Country Y, the Confederation of Country Y’s Industries, the Federation of Construction Association of Country Y, the Hotel Association of Country Y, the agriculture cooperatives etc.), Donor Partners and relevant representatives from Civil Society. The functions and the activities which will fall under the responsibility of the SC will be clearly defined together with the MoE and the CTEVT during the inception phase of the programme. The Term of Reference for the SC will be also drafted and circulated among main stakeholders (Government, private sector and donor partners) for validation.

The MoE will ensure that the programme receives all necessary support for its smooth implementation, a/o nominating a Programme Director to act as counter-part to the programme and to supervise and co-ordinate the programme activities under the result 1.

## Performance monitoring and reporting

The day-to-day technical and financial monitoring of the implementation of this action will be a continuous process and part of the implementing partners’ responsibilities. To this aim, the implementing partners shall establish a permanent internal, technical and financial monitoring system for the action and elaborate regular progress reports (not less than annual) and final reports. Every report shall provide an accurate account of implementation of the action, difficulties encountered, changes introduced. The report shall be laid out in such a way as to allow monitoring of the means envisaged and employed and of the budget details for the action. The final report, narrative and financial, will cover the entire period of the action implementation.

The Commission may undertake additional project monitoring visits both through its own staff and through independent consultants recruited directly by the Commission for independent monitoring reviews (or recruited by the responsible agent contracted by the Commission for implementing such reviews).

## Organisational set-up and responsibilities

Under the TVET-PP model, the CTEVT will be supported to play an enhanced coordinating role at the technical level and MoE at the policy and strategic level in line with the 2012 TVET policy. A Steering Committee (SC) may be established not only to oversee and facilitate TVET-PP's implementation but its role would be that of representing a real platform for improved coordination among all TVET stakeholders.

## Performance monitoring and reporting

The day-to-day technical and financial monitoring of the implementation of this action will be a continuous process and part of the implementing partners’ responsibilities. To this aim, the implementing partners shall establish a permanent internal, technical and financial monitoring system for the action and elaborate regular progress reports (not less than annual) and final reports. Every report shall provide an accurate account of implementation of the action, difficulties encountered and changes introduced. The report shall be laid out in such a way as to allow monitoring of the means envisaged and employed and of the budget details for the action. The final report, narrative and financial, will cover the entire period of the action implementation.

The Commission may undertake additional project monitoring visits both through its own staff and through independent consultants recruited directly by the Commission for independent monitoring reviews (or recruited by the responsible agent contracted by the Commission for implementing such reviews).

## Evaluation

Having regard to the nature of the action, a final evaluation (pre-completion) will be carried out for the components via independent   contracted by the Commission. A final evaluation will be carried out for accountability and learning purposes at various levels (including for policy revision), taking into account in particular the fact this is an innovative action being piloted in the three sectors with the aim of moving towards a SWAP and ultimately to a SBS modality. The Commission shall inform the implementing partner at least 60 days in advance of the dates foreseen for the evaluation missions. The implementing partner shall collaborate efficiently and effectively with the evaluation experts, and inter alia provide them with all necessary information and documentation, as well as access to the project premises and activities. The evaluation reports shall be shared with the partner country and other key stakeholders. The implementing partner and the Commission shall analyse the conclusions and recommendations of the evaluations and, where appropriate, in agreement with the partner country, jointly decide on the follow-up actions to be taken and any adjustments necessary, including, if indicated, the reorientation of the project.  Indicatively, one contract for evaluation service shall be concluded under a framework contract in September 2021.

## Audit

Without prejudice to the obligations applicable to contracts concluded for the implementation of this action, the Commission may, on the basis of a risk assessment, contract independent audits or expenditure verification assignments for one or several contracts or agreements.

Indicatively, one contract for audit services shall be concluded in September 2021.

## Communication and visibility

Communication and visibility of the EU is a legal obligation for all external actions funded by the EU.  This action shall contain communication and visibility measures which shall be based on a specific Communication and Visibility Plan of the Action, to be elaborated at the start of implementation and supported with the budget indicated in section 5.5 above. In terms of legal obligations on communication and visibility, the measures shall be implemented by the Commission, the partner country, contractors, grant beneficiaries and/or entrusted entities. Appropriate contractual obligations shall be included in, respectively, the financing agreement, procurement and grant contracts, and delegation agreements.  The Communication and Visibility Manual for European Union External Action shall be used to establish the Communication and Visibility Plan of the Action and the appropriate contractual obligations.

6	Pre-conditions

No specific pre-conditions apply.

# APPENDIX - Indicative Logframe matrix (for project modality) 	                                                                                                                             The activities, the expected outputs and all the indicators, targets and baselines included in the logframe matrix are indicative and may be updated during the implementation of the action without an amendment to the financing decision. The indicative logframe matrix will evolve during the lifetime of the action: new lines will be added for listing the activities as well as new columns for intermediary targets (milestones) when it is relevant and for reporting purpose on the achievement of results as measured by indicators.                                        TVET-PP will be information driven. A baseline study to be carried out at project's outset will define baselines and realistic targets.  In addition, year-by-year targets for training participants, graduates, and subsequent employment will be presented by category and gender, subject and course duration in the first year's report (after completion of the baseline study) and reviewed and monitored thereafter.

|  | Intervention logic | Indicators | Baselines (incl. reference year) | Targets (incl. reference year) | Sources and means of verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Overall objective: Impact | To contribute to Country Y's inclusive and sustainable growth through investment in human capital and by creating better jobs opportunities | % of TVET-PP graduates hired/ (self) employed after training in commercial farming, tourism and constructions, disaggregated by gender, geography and socio-economic group, by year 5 | 2014 employment data in: a) agriculture: approx. 70% of population (data by sub sectors are expected to be much lower but will be available only upon completion of EU- Country Y TVET sub-sector analysis); b) tourism: approx. 3.2%; c) constructions: approx. 10%. | % Increase in the employment rate in agriculture, tourism and constructions by year 5 and underemployment reduced. | GoY's documents and statistic; National employment statistics; World Bank analysis; labour force survey | Political stability; no major economic crisis or natural disasters. |
| Specific objective(s): Outcome(s) | To formulate and implement more effectively a TVET policy responsive to labour market needs and pilot an integrated Public Partnership Approach in three key economic sectors i) agriculture and food production, ii) constructions, iii) tourism | % increase of people (disaggregated by gender, geography and socio-economic conditions) having access to TVET services in commercial farming and food production, tourism and constructions; 80% of trainees successfully completing or graduating from TVET programs in agriculture, constructions and tourism, in a given year. | B1: Indicative estimation of training needs: 350.000 young people entering the job market per year; baselines disaggregated by trainings needs in targeted economic sectors will be available upon completion of EU- Country Y TVET sub-sector analysis); B2: Information on the financial contributions from private sector is not yet available in the absence of a consolidated FMIS. Currently, PS investments in short term training program seems to be very low and mostly based on DPs projects. | T1: Gap between TVET supply and demand reduced by 15% by year 5 of the project in agriculture sub-sectors, tourism and constructions sectors; T2: Increased private sector funding for the TVET sector by the end of the programme; | TVET-PP's monitoring panel; GoY and CTEVT reports, statistical data. | i) Implementation of TVET Policy remains a priority for the GoY; ii) All stakeholders remain committed to the project; iii) Political willingness to improve the system; iv) the Administration is aware of the needs and committed to change; |
| Outputs | 1. To enhance the coordination role of the GoY in the TVET system and improve the TVET governance; 2. To scale-up the quality of the TVET provision and implementation and to ensure the reach out to the most disadvantaged. 3. To test innovative Public-Private Partnership models to scale-up relevant TVET provision in Country Y. | R1: 1.1 at least 4 policy documents ( including TVET financing, TVET-PP guidelines, TVET results framework) developed or updated ( apprenticeship guidelines) by year 3; 1.2 Pilot Skills Demand and Supply information tool established and effectively in use by year 3 for agriculture sub-sectors, tourism and constructions; R2: 2.1 CTEVT's HRD reinforced and FMIS and ITMS upgraded by year 4; 2.2 development of approx. 40 new VT curricula (20 apprenticeship based curricula and 20 competency based) and revision of approx. 80 curricula by year 5. 2.3 support in quality improvement the existing rural technical schools and polytechnics by year 5 (to be identified by CTEVT in the inception phase of the project). R3: n. of joint actions developed by public and private sector TVET service providers during the 5 years of the programme; | B1: TVET policy adopted in 2012; B2.1: CTVET strategic plan 2014-2018. Currently there are 14% F, 86% M staff among 932 staff available in CTVET. B2.2: Total existing curricula in Vocational Training : 172, TSLC: 67 and Diploma: 37 B2.3: CTEVT operates through: 14 owned technical schools/ polytechnic; 2 rural training centres; 5 technical schools in partnership; 18 polytechnic under construction ; 79 technical education in community schools. B3: Currently approx.5 TVET institutions run in partnership model | T1: institutional frameworks foreseen in the 2012 TVET policy in place and effectively implemented by year 4 of the project; T2:CTEVT restructuring process completed by year 4 in line with the CTVET strategic plan 2014-2018; T3: at least 6 additional Partnership models with business sector in selected economic sectors piloted and functioning by the 4th year | R1:Quarterly and annual project reports and evaluations; Monitoring panel reports; ADB's reports on the roadmap process; minutes of coordination's meetings; CTEVT's report and progress against the CTEVT Strategic Plan (2014-2018); Monitoring and survey of training courses provided before, during and after project. Field visit of the grants; | R1: i) Commitment to TVET policy maintained; ii) Private sector cooperation forthcoming; iii) Ministries beyond MoE with training centres cooperate in the letter and spirit of the National TVET policy; R2: i) CTVET support remains enthusiastic; ii) Availability of human resources within CTEVT; iii) No intra-ministerial disputes; iv) Training centres cooperate in the letter and spirit of the National TVET Policy R3: i) The employers are committed and available to take on more responsibilities; ii) Qualified applicants responding to the call for proposals; iii) Private sector organisations are responsive to the capacity building activities; iv) Interest of informal TVET providers to collaborate with CTEVT. |

Specific contract n.2014/352-624 which will be carried out in Country Y from May to June 2015.

The TVET-sub sector analysis- specific contract n.2014/352-624- which will be carried out in Country Y from May to June 2015,