## ECMP logframe
PROJECT NAME | END CHILD MARRIAGE PROGRAMME, ETHIOPIA
ASSUMPTIONS
IMPACT | Impact Indicator 1 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | Together with a conducive wider political, economic and social environment delaying child marriage leads to wider social and economic benefits for girls and their communities.
Improve the well-being (health, education, empowerment, and poverty) of girls and women, their children, and families in East and West Gojam zones of Amhara region | % of women age 20-24 who gave birth by the exact age of 18 in the Amhara region | Planned | 27.5% | 22.5% | 20.5% | 17.5%
Achieved
Source
DHS Ethiopia
| Impact Indicator 2 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| % of girls completing primary school in East and West Gojam: (a) % of those aged 14-18 having completed first cycle of primary school; and (b) % of those aged 15-18 having completed the second cycle | Planned | (a) 48.3%; (b) 28.1% | (a) 51%; (b) 31% | (a) 54%; (b) 36% | (a) 58%; (b) 38%
Achieved
Source
Baseline Survey; follow-up surveys (subject to budget), DHS Ethiopia raw data for triangulation at regional level
| Impact Indicator 3 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| % of girls who openly discuss with their parents about child marriage and negotiate the age at which they would like to get married | Planned | 64.3% | 68% | 71% | 74%
Achieved
Source
Baseline Survey; follow-up surveys (subject to budget), DHS raw data for triangulation at regional level
OUTCOME | Outcome Indicator 1 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | ASSUMPTIONS
200,000 girls in East and West Gojam delay marriage between 2012 and 2016 and government implements ongoing programmes to eliminate child marriage in Amhara | Number of girls in East and West Gojam estimated to have delayed the age at first marriage by at least one year | Planned | 0 | 50000 | 150000 | 200000 | External political, economic and social conditions are conducive to the effective delivery of the programme; sufficient capacity exists and/or can be built by the programme for delivery by women support associations and other stakeholders; MoWCYA and regional governments are adequately funded and politically supported to fulfil their mandates; alternatives to girl child marriage are acceptable to communities, families (e.g. schooling, economic activity) households are receptive to programme activities
Achieved
Source
ECMP Progress reports
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Percentage of girls age 15-18 first married by the exact age of 15 | Planned | 15.7% | 13.34% | 11.77% | 10.21%
Achieved
Source
Baseline Survey; follow-up surveys (subject to budget)
| Outcome Indicator 3 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| ECM activities are integrated into Amhara regional government annual plan and resources (in terms of staff and/or budget line items) are allocated | Planned | Plans for ECM exist but no resources are allocated | Plans for ECM exist but no resources are allocated | Activities in Amhara regional budget documentation are consistent with ECMP plans and budgets | Resources for ECM activities are allocated at the Amhara regional level
Achieved
Source
Amhara BoWCYA annual plans
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | ASSUMPTIONS
Empower and develop capacities of community leaders, teachers, peer facilitators, girls and boys to be an effective voice in eliminating child marriage | Number of Community Facilitators trained | Planned | 0 | 2400 | 3200 | 3200 | Communities and supporting institutions (e.g. schools, local government, etc) are willing to support and, as relevant, participate in programme activities.
Achieved
Source
ECMP Progress reports
| Output Indicator 1.2 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of school clubs in which girls or girls and boys are supported | Planned | 0 | 560 | 880 | 1120
Achieved
Source
ECMP Progress reports
| Output Indicator 1.3 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of community conversation training events held in expansion kebeles | Planned | 0 | 60 | 84 | 96
IMPACT WEIGHTING (%) |  | Achieved
60% |  | Source
ECMP Progress reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | ASSUMPTIONS
Deliver economic incentives to targeted households in pilot areas | Number of beneficiary households receiving support through the Economic Incentives revolving fund | Planned | 0 | 1600 | 3000 | 4400 | Nominated delivery institutions have the know-how and capacity to carry out Economic Incentives administrative, management and monitoring activities; prospective beneficiaries meet the criteria to qualify for revolving fund and/or material support provisions, sufficient budget is available to support Economic Incentives delivery
Achieved
Source
ECMP Progress reports
| Output Indicator 2.2 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of girls receiving material support | Planned | 0 | 2400 | 3600 | 5600
Achieved
Source
ECMP Progress reports
IMPACT WEIGHTING (%)
5%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | ASSUMPTIONS
Communication for behaviour change at community level developed and disseminated | Number of schools submitting mini-media outputs that are then disseminated | Planned | 0 | 144 | 224 | 304 | Schools and religious institutions/leaders are willing to participate in programme activities and effectively capacitated
Achieved
Source
ECMP Progress reports
| Output Indicator 3.2 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of regional meetings with religious leaders held | Planned | 0 | 4 | 7 | 10
Achieved
Source
ECMP Progress reports
IMPACT WEIGHTING (%)
5%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | ASSUMPTIONS
Policy dialogue on early marriage enhanced at regional and federal levels through strategic engagement | Number of knowledge sharing workshops conducted by Amhara Learning Community on Ending Child Marriage | Planned | 0 | 4 | 6 | 8 | Commitment, availability and interest of government officials to actively participate in ECM activities/events; capacity of Amhara Learning Community to deliver workshops is not restricted
Achieved
Source
ECMP Progress reports
| Output Indicator 4.2 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of high-level events/workshops held (involving senior government officials and other influential stakeholders) on early marriage in policy and programming | Planned | 0 | 1 | 2 | 3
Achieved
Source
ECMP Progress reports
IMPACT WEIGHTING (%)
10% | [6 empty] | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | ASSUMPTIONS
Government capacity to design, plan, implement, monitor, and manage programmes to end child marriage is strengthened | Number of HTP committees at the woreda and kebele levels determined to be operational | Planned | 0 | 90 | 100 | 190 | HTP committees have the critical masses and capacities to be functional; sufficient number of prospective grantees and projects exist that meet Capacity Building Fund eligibility criteria; sufficient capacity exists and/or can be built by the programme for MoWCYA and local governments to plan and budget for ECM activities
Achieved
Source
ECMP Progress reports
| Output Indicator 5.2 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of projects funded by the Capacity Building Fund | Planned | 0 | 8 | 23 | 28
Achieved
Source
ECMP Progress Reports
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
10% | Planning for ECM at woreda, and regional government levels is undertaken through joint planning process as per timing guidelines for the annual government planning/budget exercise | Planned | Joint planning does not take place | Joint planning for ECM undertaken but not within regular Bureau planning and budgeting exercise, as evidenced by ECM being at least discussed in Bureau planning and budgeting (via minutes, ECMP Progress Reports, etc) | Planning for ECM fully integrated into regular annual Bureau planning and budgeting exercise, as evidenced by ECM being a component in both plans and budgets | Planning for ECM fully integrated into regular annual Bureau planning and budgeting exercise, as evidenced by ECM being a component in both plans and budgets
Achieved
|  | Source |  |  |  |  | RISK RATING
ECMP Progress Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 6 | Output Indicator 6.1 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016) | ASSUMPTIONS
Knowledge base on programming effectiveness and value for money is strengthened, and systems for programme monitoring are established | Number of woreda government offices who are reporting on time to the WYCA using the programme reporting format and the programme MIS database | Planned | 0 | 18 | 20 | 38 | Sufficient capacity exists and/or can be built by the programme for regional and woreda government offices to fulfil ECM M&E requirements
Achieved
Source
ECMP M&E Reports
| Output Indicator 6.2 |  | Baseline (2012) | Milestone 1 (2014) | Milestone 2 (2015) | Target (2016)
| Number of early marriage prevention briefing notes produced for public dissemination | Planned | 0 | 4 | 8 | 12
Achieved
Source
ECMP Progress Reports
IMPACT WEIGHTING (%)
10% | [6 empty] | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)