## Slide 1: Session 6
Assumptions, risks, evidence and the Intervention Logic

## Slide 2: Assumptions and risks underlying change processes (I)
ASSUMPTIONS
What we reasonably think will happen in the change process;
What needs to happen in order for the logic to deliver as intended;
'Killer' assumptions – what MUST happen
RISKS
Anything which could prevent the change process from happening the way we think it will

## Slide 3: Assumptions and risks underlying change processes (II)
“Every programme is packed with beliefs, assumptions, hypotheses about how change happens – about the way humans work, or political systems, or eco-systems… intervention logic or 'theory of change' is about articulating these underlying assumptions about how change will happen in a programme”
  (Rogers and Funnell, 2011)
Bias !! Our own experience, and professional background shapes our assumptions and how we see the world.

## Slide 4: Assumptions - Example
Increased teachers’ salaries improve student learning
on the basis of what assumptions ?
exercicse

## Slide 5: Types of assumptions
Internal to the programme – do the inputs + outputs significantly contribute to/cause the changes sought – assumptions which transform inputs into outputs, outputs into outcomes…
External to the programme (including institutional) – assumptions about the operating environment which affect what happens
Assumptions may shift over time…
depending on what is happening on the ground
on the basis of lessons learned

## Slide 6: Which assumptions do we often miss?
exercicse

## Slide 7
Evidence underpinning assumptions in the Intervention Logic

## Slide 8: Why bother to assess strength of evidence of what we think might happen ?
To provide an indication of the reliability of the assumption, and therefore an indication of the likelihood that the change process will happen this way
To build on learning by comparing evidence from earlier similar/peer contexts
To learn from what happens in this action to improve future policy and practice

## Slide 9: Assumption column in the LFM
An assumption in the LFM is a condition :
  Required for project success;
  Which is not under the control of project management; and
  Which will need to be monitored
Assumptions provide the basis on which further risk analysis is carried out.
Assumptions & risks… two sides of the same coin
Assumptions are written as positive statements, not as risks !
In a LFM, be pragmatic with assumptions,
avoid general and vague considerations

## Slide 10
Identifying and managing risks

## Slide 11: Identifying risks
How/when do we start thinking about risks?
  Above all, from a sound knowledge of the context and stakeholders
  From the objective tree: objectives we expect to be achieved by other factors/parties than the project
  From the problem tree: problems we expect to remain at a bearable level
  From out of the trees: from risks related to new problems emerging in the future
Tools for risk analysis & risk mitigation:
risk assessment matrixes, premortem technique, scenario analysis, brainstorming, SWOT…
Notes: 11

## Slide 12: Understand where the risks lie
… by keeping an eye on what has not been kept in your intervention logic
To go from an objective tree to a graphic representation of the intervention logic we make choices to select some pathways as a roadmap for our action
This means some factors will not be dealt with by the action… and will have to be considered further in the risk analysis

## Slide 13
Assessment of external risks
Is the potential impact of the risk important?
Is it likely to happen?
Very unlikely
Possibly
Almost certainly
Redesign the project by adding activities or outputs, reformulate the project outcome if necessary
Include in the logframe
Is it possible to redesign the project in order to influence this external factor?
Do not include in the logframe
The project may not be feasible
yes
no
yes
no
Notes: 11/2/2015
PCM/ECOFIN Course - Brussels - October 28-31 2008
13

## Slide 14: Internal risks and negative externalities
LFM focusses on external risk factors.
However, internal risks are often factors of poor performance.
      Identify them in order to anticipate them
      Monitor them for sound management
LFM focusses on positives externalities.
However, negative externalities exist & need to be considered.
      Use the intervention logic thinking process to identify them and plan accordingly
      Include their analysis in the monitoring and evaluation system of the action

## Slide 15
Risk management matrix
Notes: 11/2/2015
PCM/ECOFIN Course - Brussels - October 28-31 2008
15

## Slide 16: Risk management
Managing risks deserves a lot of attention !
Use the intervention logic to reflect on the risks, their existence, their evolution and their (potential) impact on the results expected from the action.
Adopt mitigation measures as soon as you identify the need for them
Prepare a risk management matrix that includes an assessment of the risk level and possible actions to take
Include risk monitoring in the monitoring & evaluation system of your project/programme
Notes: 16

## Slide 17: Case Studies : Planning phase
Option 1: Building on a real case
Develop the first steps in your Intervention Logic (green cards)
Identify key assumptions and risks and place them according to where they might impact on your results chain (orange cards)
Option 2:
  Analyse sections 2 (Risks and Assumptions), 3 (Lessons Learned, Complementarity and cross cutting issues) and 4.1 (objectives/results of the action)
  Propose improvements.
Results Chain
(O.O. - OC - OP)
Activities
Assumptions
exercicse
Notes: 11/2/2015
PCM/ECOFIN Course - Brussels - October 28-31 2008
17