## Slide 1: Session 7
Developing a Logical Framework Matrix

## Slide 2
What is a Logical Framework Matrix?

## Slide 3: Purposes of the LFM
Synthesis
Planning
Coordination
Monitoring
Negotiation
Communication
Evaluation…
…in fact, your road map!
Where are you going?
How will you get there?
How will you know that you’ve arrived?
Notes: .

## Slide 4
PROGRAMMING
IDENTIFICATION
IMPLEMENTATION
FORMULATION
CLOSURE AND FOLLOW-UP
Monitoring & Reporting
Guides data collection on key elements of the results chain
Used to track progress
Source for reporting on results
Evaluation
used to structure the evaluation process
Reference to identify what has been achieved
Identification
Sections 1-3 (Context, risks and assumptions, LL and cross cutting issues) 4.1: Objectives, results and options and section 5 of AD: preliminary indications of aid and implementation modalities. Feeds (possible) QSG1 discussions
Formulation
Collecting baseline data
Completing AD
Final LFM feeds QSG2 discussions
Final LFM feeds approval and contracting process (as key element of the description of the action)
The LFM, the AD & the management cycle in DEVCO
Management
Roadmap for implementation
Structures the dialogue between partners, donor agency etc.

## Slide 5: What a LogFrame Matrix looks like
Results chain
Indicators
Sources & means of verification
Assumptions
Impact(s)/ (Overall objective)
Outcome (Specific objective)
Outputs
Activities
(optional)
Targets
Baselines

## Slide 6: Logical Framework Matrix (LFM)
Recursive process: As each part of the matrix is formulated, the logic of other parts should be tested and refined/revised, as required
Results Chain
Indicators
Sources & means of verification
Assumptions
Impact(s)/ (Overall objective)
Outcome (Specific objective)
Outputs
Activities
(optional)
Targets
Baselines
1
2
3

## Slide 7: Writing objective statements
Impact (Overall objectives)
Outcome (Specific Objective)
Outputs
Activities
(example for OpO1 only)
To contribute to a reduction in infant and maternal mortality in districts X & Y
Improved access to maternal and child health clinic services which meet minimum quality standards
Op1. Clinic management and administration systems improved
Op2. Health staff’s technical skills upgraded
Op3. Existing clinic facilities upgraded
Op4. New clinic facilities established
1.1 Conduct participatory systems audit
1.2.Prepare cost-effective systems improvement plan based on local needs and capacity
1.3 Implement identified improvements
1.4 Monitor and review progress and performance

## Slide 8
Additional tools to complement the LFM

## Slide 9
Workplan
Workplan
Workplan
An activity schedule based on the logical framework:
reinforces the result-orientation coming from the LFA
dispatches (and details) activities in coherent operational blocks;
clarifies the sequence, duration and priority between activities
identifies key steps (such as payments set out in the financing contract)
allocates management responsibilities
Activity schedule
How and why?
Identify sequences and interdependences between activities
Estimate durations
Set milestones: key dates and deadlines
See PCM guidelines p. 89
Notes: 9

## Slide 10
Activity schedule example
Notes: 11/2/2015
PCM/ECOFIN Course - Brussels - October 28-31 2008
10

## Slide 11: Activity schedule: tips & tricks
Start from the strategic design then go to the activity schedule. The work is often iterative!
The intervention logic provides us with a number of work packages structured around various outputs. The activity schedule should be based on these work packages but should be more detailed (sub-activities…)
Do not underestimate the conflict between resources (time, human resources, money…)and between the project core activities and generic management activities (monitoring, coordination…)
Be realistic, always leave some buffer time
Do not forget the interdependence between activities
Do not forget the seasonality of certain factors (climate, school calendar, agricultural season, tourist season…)
Notes: 11

## Slide 12
Salaries
Allowances
Vehicle Op.
Office
Tel/Fax
Seeds
Fertiliser
5000 5500
1250 1750
3750 4250
750 750
400 400
850 1100
2300 3100
Budget
Salaries
Allowances
Vehicle Op.
Office
Tel/Fax
Seeds
Fertiliser
5000 5500
1250 1750
3750 4250
750 750
400 400
850 1100
2300 3100
Budget
Salaries
Allowances
Vehicle Op.
Office
Tel/Fax
Seeds
Fertiliser
5000 5500
1250 1750
3750 4250
750 750
400 400
850 1100
2300 3100
Budget
A resource schedule and a budget linked to the logframe
reinforce the result-orientation coming from the LFA
support analysis of cost-effectiveness
support result-based budget planning and financial monitoring
is a cornerstone of resource mobilisation
allows the financial implications to be identified:
  co-financing by partners
  financial sustainability after project completion
How and why?
according to planned activities and their schedule, set up the resource schedule (availability of resources)
Resource schedule is the cornerstone for planning budget and cashflows
PCM guidelines p. 91
Resource schedule
Notes: 12

## Slide 13
Resource schedule example
Notes: 11/2/2015
PCM/ECOFIN Course - Brussels - October 28-31 2008
13

## Slide 14: Resource schedule & budget
The resource schedule is a step that should come before setting up the budget.
During the implementation of the project/programme, cash-flow constraints will be more likely than budget constraints so do not neglect cash-flow planning!
Pay attention to the balance in the budget: the balance between budget headings should reflect the nature of the project.
Once the financial rules the project/programme will have to comply with are known, be careful of the absolute and relative value of the budget headings. Some rules can have consequences when budget headings are very unbalanced.
A good budget is clear but allows for sufficient flexibility during implementation: detailed, but not too much!
Notes: 14

## Slide 15
How to adapt the logframe matrix to take account of an intervention logic with various levels of action

## Slide 16: Interlocking or « nested » logframes
PROGRAMME |  | PROJECT |  | COMPONENT
▲ |  |  |  | 
Impact |  |  |  | 
▲ |  |  |  | 
Outcome | ◄ | Impact |  | 
▲ |  | ▲ |  | 
Outputs |  | Outcome | ◄ | Impact
▲ |  | ▲ |  | ▲
Activities |  | Outputs |  | Outcome
 |  | ▲ |  | ▲
 |  | Activities |  | Outputs
 |  |  |  | ▲
 |  |  |  | Activities

## Slide 18: Case Study: Building a LFM
Option 1: Building on a real case.
Develop the results chain of your LFM (1st column), starting from the top to the bottom (green and blue cards)
Develop the assumption column of your LFM (last column), place the assumptions according to the LFM level they might influence (orange cards)
Option 2: Improving an existing LFM (in AD):
  Analyse the quality of the LFM considering the context analysis
  Propose improvements in the LFM
Results Chain (O.O. - OC - OP)
Activities
Assumptions
exercicse
Notes: 11/2/2015
PCM/ECOFIN Course - Brussels - October 28-31 2008
18