# Case Example: Libya Health System

Inspired by the Libya Health Systems Strengthening Programme (LHSS) Implemented by GIZ funded by the European Union

This case positions the intervention in a quite uncertain environment. It is inspired by the Libya Health Systems Strengthening Programme (LHSS) implemented by GIZ and funded by the European Union.

There is an acknowledged need to move fast in order to manage expectations and support the consolidation of democratic reforms. So, the projects explicitly builds in an inception phases followed by a phase for learning and innovation. During this first year a full stakeholder and political economy analysis is foreseen as well as an in-depth assessment of capacities. These will inform collective decision making for the 3-year implementation phase.

The case is particularly interesting since the LI is quite explicit about a process that respects ownership principles, learning and innovation based on an iterative approach and coalition building. The draft LIN has been annotated below and worked through to demonstrate the 4 basic options for laying out the content of section 4.1. and 4.2.  The version featured below follows option 2 whereby section 4.2 is kept separate and the narrative moves upward.

1.	Mock-up Logic of Intervention Narrative: Option 1 presented in relation to LFM	2

2.	Mock-up Logic of Intervention Narrative: Option 1 with annotations showing the links to other parts of the action document	3

3.	Mock-up Logic of Intervention Narrative: Option 1	4

4.	Mock-up Logic of Intervention Narrative: Option 2	5

5.	Mock-up Logic of Intervention Narrative: 0ption 3	7

6.	Mock-up Logic of Intervention Narrative: Option 4 (with annotations)	9

## Mock-up Logic of Intervention Narrative: Option 1 presented in relation to LFM

|  | The table below presents the Logic of Intervention Narrative as dynamic explanation of the nexus between Assumptions and results levels as contained in the LogFrame Matrix. It uses the same format as the LFM by replacing the indicator related columns in the middle by one column presenting the logic of intervention. Following the results hierachy the text goes from impact down to outputs and activities. |
| --- | --- |

| Results levels | Logic of Intervention Narrative (LIN) | Assumptions |
| --- | --- | --- |
| Overall Objective / Impact: To improve efficiency, effectiveness and quality of health service delivery in Libya | The purpose of the programme is to develop and support the Libyan health reform agenda, reengineer and/or strengthen the health system (HSS) in particular in the areas of strategic planning, health financing, management, human resources for health, quality of care and health service delivery. Priorities have been agreed at the highest level based on assessments. | Reform related risks are adequately managed (see below) |
|  | Given signs and stated commitment one can reasonably assume that the Libyan authorities will remain committed to the democratic transition and adopt the constitution within the year. Further, strong leadership can plausibly be expected by the new Minister. The initiative will further rely on concomitant initiatives to develop 2 of the 6 pillars under the national programme, an explicit expectation that adequate budget allocations will be made for implementing the reforms. Nevertheless, there are risks slow broader public sector reforms may hinder health sector reform, that democratic transition may stall or that the security situation may deteriorate leading to potential suspension of programme | - Stakeholders share a common understanding of reform priorities and direction - Political feasibility of reforms is duly taken into account - Implementation is adequately sequenced and proceeds at a reasonable pace - Expectations are adequately managed - Reform momentum is sustained - Local ownership principles are honoured through processes of validation by a wide cross-section of national stakeholders - Blueprint approaches are avoided - Plans and proposals are realistic and feasible and the ‘politics of implementation’ is duly taken into account - Resources are made available by the GoL to support the rollout of reforms - A viable interface between bottom up approaches and top down reforms is created - Broader public sector reforms do not hinder sector-wide reform processes |
| Specific objective/ Outcome: To strengthen strategic planning, financing, management and health service delivery through targeted reforms | Essential outcomes include the development of an overarching National Health Sector Strategy and Plan and a Health Service Package, out of which subsector policies, strategies and action plans will be developed and implemented. The strategy will be an absolute pre-condition for any initiative contributing towards a renewed and performing health system. |  |
|  | Coordination and a shared understanding among all stakeholders of reform priorities and direction will be therefore essential for success. The initiative will support national authorities to manage inclusive coordination, well aware of the significant challenges of high expectations for rapid change that need to managed and possible resistance among officials to taking strategic decisions beyond mandates and health staff once implications of reform are felt. |  |
| R1: Strategic Planning, Health Financing and Capacity Strengthened R2: Health Service Delivery and Quality of Health Care | While strategic planning results will be important it is widely agreed that moving determined and fast on results areas “Health Service Delivery” and “Human Resources for Health” will be vital and will need to be implemented with optimal traction for capacity |  |
| R3: Workforce Planning, Development and Management | The programme will do so by availing high quality technical assistance and by supporting capacity building, training and exposure visits to support authorities fully honouring local ownership principles through processes of validation by a wide cross section of national stakeholders. Since, there are unknown the implementation is envisaged in 3 phases, namely Inception that will allow complementing stakeholder, political economy and capacity analysis. It will be followed by a Learning and Innovation phase that will establish agreement around the concrete action plan to be implemented during the Scale up phase. Given the transitional nature of the political landscape in Libya, the programme understands the importance of being flexible and responsive to changing needs and will ensure that regular reviews, including political economy analysis are undertaken to monitor and adapt the programme approach. |  |

# Mock-up Logic of Intervention Narrative: Option 1 with annotations showing the links to other parts of the action document

| Annotations | Logic of Intervention Narrative (LIN) | Annotations |
| --- | --- | --- |
| Overall objective articulated 4.1 and LFM (not formulated as impact statement) | The purpose of the programme is to develop and support the Libyan health reform agenda, reengineer and/or strengthen the health system (HSS) in particular in the areas of strategic planning, health financing, management, human resources for health, quality of care and health service delivery. Priorities have been agreed at the highest level based on assessments. | The problem analysis and priority areas are spelled out in AD section 1.1.3. |
| Key assumptions / risks that are discussed in more detail in AD section 2. Implication: M&E and iterative adaptation during implementation | Given signs and stated commitment one can reasonably assume that the Libyan authorities will remain committed to the democratic transition and adopt the constitution within the year. Further, strong leadership can plausibly be expected by the new Minister. The initiative will further rely on concomitant initiatives to develop 2 of the 6 pillars under the national programme, an explicit expectation that adequate budget allocations will be made for implementing the reforms. Nevertheless, there are risks that will be carefully monitored, including: slow broader public sector reforms may hinder health sector reform, that democratic transition may stall or that the security situation may deteriorate leading to potential suspension of programme | AD section 1.1.1 & 1.1.2. provide detail on policy and commitment of government as key stakeholder. AD section 3.2 spells out the synergies expected and who is implied. The context analysis AD section 1. spells out the current conditions and potential implications. |
| Outcomes spelled out in 4.1 and the LFM The public policy analysis AD 1.1.1. has made the case based on evidence from prior studies. | Essential outcomes include the development of an overarching National Health Sector Strategy and Plan and a Health Service Package, out of which subsector policies, strategies and action plans will be developed and implemented. The strategy will be an absolute pre-condition for any initiative contributing towards a renewed and performing health system. | As critical outcome the assumptions to achieve it are spelled out in section 2. and in the LFM. |
| The analysis in s section 1.1.2. provides the stakeholder landscape and the design foresees a full stakeholder and political economy analysis to be regularly updated. | Coordination and a shared understanding among all stakeholders of reform priorities and direction will be therefore essential for success. The initiative will support national authorities to manage inclusive coordination, well aware of the significant challenges of high expectations for rapid change that need to managed and possible resistance among officials to taking strategic decisions beyond mandates and health staff once implications of reform are felt. | The coordination capacity will be a critical results underpinned by assumptions and risks spelled out in section 2. And the indicated in the LFM. Capacity assessment foreseen |
| Outputs in 4.1 and LFM | While strategic planning results will be important it is widely agreed that moving determined and fast on results areas “Health Service Delivery” and “Human Resources for Health” will be vital and will need to be implemented with optimal traction for capacity | Sense of priority. The context analysis spells out why. CD traction as principle |
| Inputs and activities are spelled out in 4.1 only. The LFM does not feature these. Section 5 on implementation will have a very limited reflection on inputs. Emphasis on flexibility and iterative adaptation as basic approach required in the given context. | The programme will do so by availing high quality technical assistance and by supporting capacity building, training and exposure visits to support authorities fully honouring local ownership principles through processes of validation by a wide cross section of national stakeholders. Since, there are unknown the implementation is envisaged in 3 phases, namely Inception that will allow complementing stakeholder, political economy and capacity analysis. It will be followed by a Learning and Innovation phase that will establish agreement around the concrete action plan to be implemented during the Scale up phase. Given the transitional nature of the political landscape in Libya, the programme understands the importance of being flexible and responsive to changing needs and will ensure that regular reviews, including political economy analysis are undertaken to monitor and adapt the programme approach. | Ownership indicated as fundamental approach. Uncertainties acknowledged and required analysis integrated into design. Emphasis on installing a Learning and review routine during the initial phase and throughout implementation. |

# Mock-up Logic of Intervention Narrative: Option 1

The purpose of the programme is to develop and support the Libyan health reform agenda, reengineer and/or strengthen the health system (HSS) in particular in the areas of strategic planning, health financing, management, human resources for health, quality of care and health service delivery. Priorities have been agreed at the highest level based on assessments.

Given signs and stated commitment one can reasonably assume that the Lybian authorities will remain committed to the democratic transition and adopt the constitution within the year. Further strong leadership can plausibly be expected by the new Minister. The initiative will further rely on concomitant initiatives to develop 2 of the 6 pillars under the national programme, an explicit expectation that adequate budget allocations will be made for implementing the reforms. Nevertheless, there are risks slow broader public sector reforms may hinder health sector reform, that democratic transition may stall or that the security situation may deteriorate leading to potential suspension of programme

Essential outcomes include the development of an overarching National Health Sector Strategy and Plan and a Health Service Package, out of which subsector policies, strategies and action plans will be developed and implemented. The strategy will be an absolute pre-condition for any initaitive contributing towards a renewed and performing Healthsystem.

Coordination and a shared understanding among all stakeholders of reform priorities and direction will be therefore essential for success. The initiative will support national authorities to manage inclusive coordination, well aware of the significant challenges of high expectations for rapid change that need to managed and possible resistance among officials to taking strategic decisions beyond mandates and health staff once implications of reform are felt. It is widely agreed that moving determined and fast on results areas “Health Service Delivery” and “Human Resources for Health” will be vital and will need to be implemented with optimal traction for capacity development in the concerned institutions.

The programme will do so by availing high quality technical assistance and by supporting capacity building, training and exposure visits to support authorities fully honoring local ownership principles through processes of vlidation by a wide cross section of national stakeholders. Since, there are unknown the implementaton is envisaged in 3 phases, namely Inception that will allow complementing stakeholder, political economy and capacity analysis. It will be followed by a Learning and Innovation phase that will establish agreement around the concrete action plan to be implemented during the Scale up phase.

Given the transitional nature of the political landscape in Libya, the programme understands the importance of being flexible and responsive to changing needs and will ensure that regular reviews, including political economy analysis are undertaken to monitor and adapt the programme approach.

# Mock-up Logic of Intervention Narrative: Option 2

Order adjusted for illustration – not edited

4. Description

4.1 Objectives/results and main activities

Overall Objective / Impact:

To improve efficiency, effectiveness and quality of health service delivery in Libya

Specific objective/ Outcome:

To strengthen strategic planning, financing, management and health service delivery through targeted reforms

Outputs:

The main expected results of the LHSS programme are summarised in the table below:

R1 Result Area One: Strategic Planning & Budgeting, Health Financing System and Institutional Capacity Strengthening:

- National Health Strategy developed (long term vision & mission and strategic priorities identified);

- Related policies analysed and formulated;

- Long term and short term action plans and budgets developed;

- Health financing options analysed and best options identified;

- Provider payment mechanisms reviewed;

- The institutional capacity of the Ministry of Health and Health Professionals Associations strengthened at all levels; and

- Coordination mechanism in place (as a secondary outcome)

R2 Result Area Two: Health Service Delivery and Quality of Health Care:

- Related policies analysed and formulated;

- A Health Service Package designed, costed, partially rolled out and evaluated through research initiatives in sentinel/pilot areas;

- Options for public private partnerships assessed and identified;

- Quality of outcomes framework and accreditation standards developed;

- Quality improvements initiatives tested, rolled out and reported.

R3 Result Area Three: Health Workforce Planning, Development and Management

- Related policies analysed and formulated;

- Recruitment and retention targets in place;

- Pre-service and in-service training needs assessed and addressed through targeted training and partnerships with training institutions (twinning);

- Licensing standards and management tools developed and rolled out in pilot areas

Activities and Inputs:

Result Area One: Strategic Planning, Health Financing and Institutional Capacity Strengthening

Activities under this Result Area focus on the development of the overall National Health Sector Strategy and related subsector policies and implementation guidelines. The programme will also assist the Ministry of Health, health professional organisations and other health sector stakeholders and build their capacity where required. As a result, institutional capacity will be strengthened both directly and indirectly.

Result Area Two: Health Service Delivery and Quality of Health Care

Activities to improve service delivery and quality of care are closely interlinked with the analysis of existing policies and the formulation of new ones in line with an overall National Health Strategy and Health Service Package. The approach will leverage bottom up initiatives to improve quality of care and ensure show quick and visible results. These will feed into evidence-based policy and decision-making processes and successes that can be rolled out nationwide.

The programme envisages the following activities and outputs, but remains flexible to the needs of the Libyan government and the reform agenda:

Result Area Three: Health Workforce Planning, Development and Management

Activities in this result area will focus on workforce planning, development and managements, which in turn will be inextricably linked to priorities dictated by the National Health Strategy and the chosen health care model. Good quality services require the right number of health care workers of the desired quality at the right time and in the right place. It is essential for health workers to be continuously trained and their technical skills upgraded. A conducive environment, inclusive of enabling working conditions and a viable career path, keeps the workforce motivated and enhances its performance. Therefore policies regarding health workforce strategic planning and redistribution, recruitment and retention, development and training and professional regulation need to be in place.

Strong links should be established with universities and other national training institutions. Their early implication in a process of review will accelerate the  implementation of new strategies. Family medicine, nursing curricula and continuous training with accreditation are already three major aspects of reform foreseen in the programme.

Inputs: The programme will avail five Long Term Experts (LTEs) with the following the roles and responsibilities:  LTE 1: A Team Leader (Health Economist) LTE 2: A Strategic Communications Expert LTE 3: A Quality Improvement Expert LTE 4: A Health Service Delivery Expert LTE 5: A Human Resources for Health (HRH) Expert. The team will be backstopped by a fully capable and permanently on-call management team to cover the many technical complexities that the implementation of the Libya Health Systems Strengthening (LHSS) Programme will present.

4.2 Logic of Intervention

The purpose of the programme is to develop and support the Libyan health reform agenda, reengineer and/or strengthen the health system (HSS) in particular in the areas of strategic planning, health financing, management, human resources for health, quality of care and health service delivery. Priorities have been agreed at the highest level based on assessments.

Given the transitional nature of the political landscape in Libya, the programme understands the importance of being flexible and responsive to changing needs and will ensure that regular reviews, including political economy analysis are undertaken to monitor and adapt the programme approach.

The programme will avail high quality technical assistance and by supporting capacity building, training and exposure visits to support authorities fully honoring local ownership principles through processes of vlidation by a wide cross section of national stakeholders. Since, there are unknown the implementaton is envisaged in 3 phases, namely Inception that will allow complementing stakeholder, political economy and capacity analysis. It will be followed by a Learning and Innovation phase that will establish agreement around the concrete action plan to be implemented during the Scale up phase.

Coordination and a shared understanding among all stakeholders of reform priorities and direction will be therefore essential for success. The initiative will support national authorities to manage inclusive coordination, well aware of the significant challenges of high expectations for rapid change that need to managed and possible resistance among officials to taking strategic decisions beyond mandates and health staff once implications of reform are felt. It is widely agreed that moving determined and fast on results areas “Health Service Delivery” and “Human Resources for Health” will be vital and will need to be implemented with optimal traction for capacity development in the concerned institutions.

Essential outcomes include the development of an overarching National Health Sector Strategy and Plan and a Health Service Package, out of which subsector policies, strategies and action plans will be developed and implemented. The strategy will be an absolute pre-condition for any initiative contributing towards a renewed and performing health system.

Given signs and stated commitment one can reasonably assume that the Libyan authorities will remain committed to the democratic transition and adopt the constitution within the year. Further strong leadership can plausibly be expected by the new Minister. The initiative will further rely on concomitant initiatives to develop 2 of the 6 pillars under the national programme, an explicit expectation that adequate budget allocations will be made for implementing the reforms. Nevertheless, there are risks slow broader public sector reforms may hinder health sector reform, that democratic transition may stall or that the security situation may deteriorate leading to potential suspension of programme

# Mock-up Logic of Intervention Narrative: 0ption 3

Order adjusted for illustration – overlapping passages (in blue) not edited

4. Description

(combining 4.1 Objectives/results and main activities & 4.2 Logic of Intervention)

The purpose of the programme is to develop and support the Libyan health reform agenda, reengineer and/or strengthen the health system (HSS) in particular in the areas of strategic planning, health financing, management, human resources for health, quality of care and health service delivery. Priorities have been agreed at the highest level based on assessments.

Overall Objective / Impact:

To improve efficiency, effectiveness and quality of health service delivery in Libya

Specific objective/ Outcome:

To strengthen strategic planning, financing, management and health service delivery through targeted reforms

Outputs:

The main expected results of the LHSS programme are summarised in the table below:

R1 Result Area One: Strategic Planning & Budgeting, Health Financing System and Institutional Capacity Strengthening:

- National Health Strategy developed (long term vision & mission and strategic priorities identified);

- Related policies analysed and formulated;

- Long term and short term action plans and budgets developed;

- Health financing options analysed and best options identified;

- Provider payment mechanisms reviewed;

- The institutional capacity of the Ministry of Health and Health Professionals Associations strengthened at all levels; and

- Coordination mechanism in place (as a secondary outcome)

R2 Result Area Two: Health Service Delivery and Quality of Health Care:

- Related policies analysed and formulated;

- A Health Service Package designed, costed, partially rolled out and evaluated through research initiatives in sentinel/pilot areas;

- Options for public private partnerships assessed and identified;

- Quality of outcomes framework and accreditation standards developed;

- Quality improvements initiatives tested, rolled out and reported.

R3 Result Area Three: Health Workforce Planning, Development and Management

- Related policies analysed and formulated;

- Recruitment and retention targets in place;

- Pre-service and in-service training needs assessed and addressed through targeted training and partnerships with training institutions (twinning);

- Licensing standards and management tools developed and rolled out in pilot areas

Activities (and Inputs):

Result Area One: Strategic Planning, Health Financing and Institutional Capacity Strengthening

Activities under this Result Area focus on the development of the overall National Health Sector Strategy and related subsector policies and implementation guidelines. The programme will also assist the Ministry of Health, health professional organisations and other health sector stakeholders and build their capacity where required. As a result, institutional capacity will be strengthened both directly and indirectly.

Result Area Two: Health Service Delivery and Quality of Health Care

Activities to improve service delivery and quality of care are closely interlinked with the analysis of existing policies and the formulation of new ones in line with an overall National Health Strategy and Health Service Package. The approach will leverage bottom up initiatives to improve quality of care and ensure show quick and visible results. These will feed into evidence-based policy and decision-making processes and successes that can be rolled out nationwide.

The programme envisages the following activities and outputs, but remains flexible to the needs of the Libyan government and the reform agenda:

Result Area Three: Health Workforce Planning, Development and Management

Activities in this result area will focus on workforce planning, development and managements, which in turn will be inextricably linked to priorities dictated by the National Health Strategy and the chosen health care model. Good quality services require the right number of health care workers of the desired quality at the right time and in the right place. It is essential for health workers to be continuously trained and their technical skills upgraded. A conducive environment, inclusive of enabling working conditions and a viable career path, keeps the workforce motivated and enhances its performance. Therefore policies regarding health workforce strategic planning and redistribution, recruitment and retention, development and training and professional regulation need to be in place.

Strong links should be established with universities and other national training institutions. Their early implication in a process of review will accelerate the  implementation of new strategies. Family medicine, nursing curricula and continuous training with accreditation are already three major aspects of reform foreseen in the programme.

Inputs: The programme will avail five Long Term Experts (LTEs) with the following the roles and responsibilities:  LTE 1: A Team Leader (Health Economist) LTE 2: A Strategic Communications Expert LTE 3: A Quality Improvement Expert LTE 4: A Health Service Delivery Expert LTE 5: A Human Resources for Health (HRH) Expert. The team will be backstopped by a fully capable and permanently on-call management team to cover the many technical complexities that the implementation of the Libya Health Systems Strengthening (LHSS) Programme will present.

Given the transitional nature of the political landscape in Libya, the programme understands the importance of being flexible and responsive to changing needs and will ensure that regular reviews, including political economy analysis are undertaken to monitor and adapt the programme approach.

The programme will avail high quality technical assistance and by supporting capacity building, training and exposure visits to support authorities fully honouring local ownership principles through processes of validation by a wide cross section of national stakeholders. Since, there are unknown the implementation is envisaged in 3 phases, namely Inception that will allow complementing stakeholder, political economy and capacity analysis. It will be followed by a Learning and Innovation phase that will establish agreement around the concrete action plan to be implemented during the Scale up phase.

Coordination and a shared understanding among all stakeholders of reform priorities and direction will be therefore essential for success. The initiative will support national authorities to manage inclusive coordination, well aware of the significant challenges of high expectations for rapid change that need to managed and possible resistance among officials to taking strategic decisions beyond mandates and health staff once implications of reform are felt. It is widely agreed that moving determined and fast on results areas “Health Service Delivery” and “Human Resources for Health” will be vital and will need to be implemented with optimal traction for capacity development in the concerned institutions.

Essential outcomes include the development of an overarching National Health Sector Strategy and Plan and a Health Service Package, out of which subsector policies, strategies and action plans will be developed and implemented. The strategy will be an absolute pre-condition for any initiative contributing towards a renewed and performing health system.

Given signs and stated commitment one can reasonably assume that the Libyan authorities will remain committed to the democratic transition and adopt the constitution within the year. Further strong leadership can plausibly be expected by the new Minister. The initiative will further rely on concomitant initiatives to develop 2 of the 6 pillars under the national programme, an explicit expectation that adequate budget allocations will be made for implementing the reforms. Nevertheless, there are risks slow broader public sector reforms may hinder health sector reform, that democratic transition may stall or that the security situation may deteriorate leading to potential suspension of programme

# Mock-up Logic of Intervention Narrative: Option 4 (with annotations)

| Logic of Intervention Narrative (LIN) | Comments |  |
| --- | --- | --- |
| Overall Objective / Impact: To improve efficiency, effectiveness and quality of health service delivery in Libya |  |  |
| The purpose of the programme is to develop and support the Libyan health reform agenda, reengineer and/or strengthen the health system (HSS) in particular in the areas of strategic planning, health financing, management, human resources for health, quality of care and health service delivery. Priorities have been agreed at the highest level based on assessments. Given signs and stated commitment one can reasonably assume that the Libyan authorities will remain committed to the democratic transition and adopt the constitution within the year. Further, strong leadership can plausibly be expected by the new Minister. The initiative will further rely on concomitant initiatives to develop 2 of the 6 pillars under the national programme, an explicit expectation that adequate budget allocations will be made for implementing the reforms. Nevertheless, there are risks slow broader public sector reforms may hinder health sector reform, that democratic transition may stall or that the security situation may deteriorate leading to potential suspension of programme |  |  |
| Specific objective/ Outcome: To strengthen strategic planning, financing, management and health service delivery through targeted reforms |  |  |
| Essential outcomes include the development of an overarching National Health Sector Strategy and Plan and a Health Service Package, out of which subsector policies, strategies and action plans will be developed and implemented. The strategy will be an absolute pre-condition for any initiative contributing towards a renewed and performing health system. Coordination and a shared understanding among all stakeholders of reform priorities and direction will be therefore essential for success. The initiative will support national authorities to manage inclusive coordination, well aware of the significant challenges of high expectations for rapid change that need to managed and possible resistance among officials to taking strategic decisions beyond mandates and health staff once implications of reform are felt. |  |  |
| Outputs: The main expected results of the LHSS programme are summarised in the table below: R1 Result Area One: Strategic Planning & Budgeting, Health Financing System and Institutional Capacity Strengthening: - National Health Strategy developed (long term vision & mission and strategic priorities identified); - Related policies analysed and formulated; - Long term and short term action plans and budgets developed; - Health financing options analysed and best options identified; - Provider payment mechanisms reviewed; - The institutional capacity of the Ministry of Health and Health Professionals Associations strengthened at all levels; and - Coordination mechanism in place (as a secondary outcome) R2 Result Area Two: Health Service Delivery and Quality of Health Care: - Related policies analysed and formulated; - A Health Service Package designed, costed, partially rolled out and evaluated through research initiatives in sentinel/pilot areas; - Options for public private partnerships assessed and identified; - Quality of outcomes framework and accreditation standards developed; - Quality improvements initiatives tested, rolled out and reported. R3 Result Area Three: Health Workforce Planning, Development and Management - Related policies analysed and formulated; - Recruitment and retention targets in place; - Pre-service and in-service training needs assessed and addressed through targeted training and partnerships with training institutions (twinning); - Licensing standards and management tools developed and rolled out in pilot areas | Given that the outputs marked in red are also fully incorporated in the LFM, they are probably not needed here |  |
| While strategic planning results will be important it is widely agreed that moving determined and fast on results areas “Health Service Delivery” and “Human Resources for Health” will be vital and will need to be implemented with optimal traction for capacity The programme will do so by availing high quality technical assistance and by supporting capacity building, training and exposure visits to support authorities fully honouring local ownership principles through processes of validation by a wide cross section of national stakeholders. Since, there are unknown the implementation is envisaged in 3 phases, namely Inception that will allow complementing stakeholder, political economy and capacity analysis. It will be followed by a Learning and Innovation phase that will establish agreement around the concrete action plan to be implemented during the Scale up phase. Given the transitional nature of the political landscape in Libya, the programme understands the importance of being flexible and responsive to changing needs and will ensure that regular reviews, including political economy analysis are undertaken to monitor and adapt the programme approach. |  |  |
| Activities and Inputs: Result Area One: Strategic Planning, Health Financing and Institutional Capacity Strengthening Activities under this Result Area focus on the development of the overall National Health Sector Strategy and related subsector policies and implementation guidelines. The programme will also assist the Ministry of Health, health professional organisations and other health sector stakeholders and build their capacity where required. As a result, institutional capacity will be strengthened both directly and indirectly. Activities: - Conduct broad stakeholder consultations - Identify health sector political and strategic orientations and priorities - Facilitate the establishment of a Roadmap to elaborate a National Health Strategy and related policies and action plans - Assist in conducting surveys and analyses related to health financing issues e.g. health expenditure surveys, costing studies, provider payment mechanisms - Develop and implement a Communication Strategy to support the reform agenda Result Area Two: Health Service Delivery and Quality of Health Care Activities to improve service delivery and quality of care are closely interlinked with the analysis of existing policies and the formulation of new ones in line with an overall National Health Strategy and Health Service Package. The approach will leverage bottom up initiatives to improve quality of care and ensure show quick and visible results. These will feed into evidence-based policy and decision-making processes and successes that can be rolled out nationwide. The programme envisages the following activities and outputs, but remains flexible to the needs of the Libyan government and the reform agenda: Activities: - Review and analyse existing policies regarding health service delivery - Assist in the formulation of related policies in line with the overall national health sector strategy and reform agenda, in particular: - Design and cost a Health Service Package - Formulate research initiatives to roll out part of the package in selected pilot areas - Assist in the development of accreditation standards - Advise on identified options for public private partnerships - Link the programme to a M&E strategy and integrate lessons learned with regards to HIS development, if possible - Facilitate quality improvement initiatives - Set up and test Systemic Quality Improvements such as a peer reviews, benchmarking and excellence-oriented mechanisms - Support continuous learning opportunities for health professionals to establish an accreditation system nationwide Result Area Three: Health Workforce Planning, Development and Management Activities in this result area will focus on workforce planning, development and managements, which in turn will be inextricably linked to priorities dictated by the National Health Strategy and the chosen health care model. Good quality services require the right number of health care workers of the desired quality at the right time and in the right place. It is essential for health workers to be continuously trained and their technical skills upgraded. A conducive environment, inclusive of enabling working conditions and a viable career path, keeps the workforce motivated and enhances its performance. Therefore policies regarding health workforce strategic planning and redistribution, recruitment and retention, development and training and professional regulation need to be in place. Strong links should be established with universities and other national training institutions. Their early implication in a process of review will accelerate the implementation of new strategies. Family medicine, nursing curricula and continuous training with accreditation are already three major aspects of reform foreseen in the programme. The programme further envisages the following activities and outputs: Activities: - Review and analyse existing policies regarding human resources for health at medical, dental, nursing and paramedical level - Assist in the formulation of related policies in line with the overall national health sector strategy and reform agenda - Assist in the analysis of existing and future workforce regarding numbers, categories and skill mix - Assist in the development and adaptation of state of the art curricula for all health service related professions Inputs: The programme will avail five Long Term Experts (LTEs) with the following the roles and responsibilities: LTE 1: A Team Leader (Health Economist) LTE 2: A Strategic Communications Expert LTE 3: A Quality Improvement Expert LTE 4: A Health Service Delivery Expert LTE 5: A Human Resources for Health (HRH) Expert. The team will be backstopped by a fully capable and permanently on-call management team to cover the many technical complexities that the implementation of the Libya Health Systems Strengthening (LHSS) Programme will present. |  | Given that the activities marked in red are also fully incorporated in the LFM, they are probably not needed here. The summary paragraphs are more insightful and go with the Logic of Intervention Narrantive |