## Slide 1
Brussels, 12-15 January 2016
Logical Framework Approach & indicators
for the result oriented management of projects & programmes

## Slide 2: Session 1
Introduction

## Slide 3: Objectives of the training
Understand key methodological principles for planning and managing projects and programmes (Logical Framework Approach/LFA, Logical Framework Matrix/LFM, Intervention Logic/IL, Theory of Change…) common to both aid modalities
Have a practical understanding of how to develop a useful, robust Intervention Logic
Have made practical use of LFA-related tools
Understand the strengths and limitations of a Logframe Matrix and IL
Have a practical understanding of the purpose and use of indicators
Have a clear understanding of the operational uses of different management tools
Be able to link the training content with their work on EU supported actions as well as with some related key documents and management mechanisms (Action Document, the EU Results Framework, …)
Be able to make informed choices to support the changes that projects and programmes seek to bring about

## Slide 4: How does this training fit with other courses?
UNDERSTANDING THE CONTEXT
Context for development (5 days):
Stakeholder analysis (2 day)
Public policy analysis (2 days)
Fragility and conflict sensitivity (1 day)
PLANNING & IMPLEMENTING ACTIONS
Logical Framework Approach and Indicators (4 days)
Policy dialogue (4 days)
Capacity development (2 days)
Monitoring (2 days)
LEARNING FROM EXPERIENCE
Evaluation (3 days)
Capacity4Dev platform
E-learning
PROJECT AND PROGRAMME
CYCLE MANAGEMENT (in preparation)
Focus on the phases
Aid effectiveness
Cross cutting issues
(2 days)

## Slide 5: Methodological references for the course
Downloadable on the Internet and Intranet
Action Document template and Instructions for AD template completion
« Guidelines – Project Cycle Management, EUROPEAID »
« Budget Support Guidelines, EUROPEAID »
« Policy Steering Note– The role and use of performance measurement indicators », EUROPEAID
Capacity Development Toolkit

## Slide 6
Day 1
Introduction to the Logical Framework Approach and the cycle of development actions
S1
S2
S3
Linking analyses and change process
S4
Developing a Logical Framework Matrix (LFM)
S5
S6
Building an Intervention Logic
S7
S8
Recap on the LFM and IL
S9
S10
Indicators (I): indicators & objectives
S11
Indicators (II): Sources of verification
S12
Day 2
Day 3
S
number
Session
Monitoring systems & result oriented management
S13
Working groups on LFM, indicators & sources of verification
S14
S15
Recap, conclusions & evaluation of the training course
S16
Day 4
Case study: How to improve the LFM with the IL
Assumptions, risks, evidence and the Intervention Logic
Indicators (III): Quantitative/qualitative indicators & critical analysis of data
First steps in the LFA
Plenary presentation of group work
Case study: understanding the context

## Slide 7
The Logical Framework Approach &
project and programme cycle management

## Slide 8: Projects and Programmes
A project is a set of inputs, activities and outputs, agreed with the partner country*, to reach specific objectives/outcomes within a defined time frame, with a defined budget and a defined geographical area. …A large project with a number of different components is sometimes referred to as a programme (…) (OECD – 2014)
A programme: can have various meanings, either: (i) a set of projects put together under the overall framework of a common Overall Objective/Goal; (ii) an ongoing set of initiatives/services that support common objectives (e.g. a Primary Health Care Programme); or (iii) a Sector Programme, which is defined by the responsible government’s sector policy (i.e. a Health Sector Programme).
(from the EC PCM guidelines – 2004)
Other terms: development actions or interventions
Above all: Projects and Programmes LEAD TO CHANGE

## Slide 9
DEVCO Project and Programme Cycle
Generally, each sector selected will be subject
of one Action document
Lessons
learned
FORMULATION
CLOSURE
Note
:
(
EU terminology
Identification
+
Formulation
=
Appraisal
+
D
esign
Evaluation
M
id
-
term,
final
E
x
-
post
Audit
Multi
Annual
Programming
docu
ment
Sector 1
Sector 2
Sector 3
Action Document
CONSULTATION
(AGR
E
valuation
and
ROM
missions
planned and under conditions
IDENTIFICATION
IMPLEMENTATION
PROGRAMMING
Quality Support Groups
(peer reviews)
Team Country Meetings
Monitoring
Internal but possibly
external (ROM)
review missions and support to result reporting missions
FINANCING DECISION
Possible financing agreement
Contractual arrangements

## Slide 10: Steps in the cycle
Programming – Analysing the situation and existing policies/strategies in order to identify the main issues that international cooperation could address
Identification – Defining the basis for the design of an action based on programming priorities and a thorough understanding of the context in order to focus on the priority areas and/or problems to be addressed.
Formulation – Designing the action, based on the analysis carried out during identification. This leads to the elaboration of a full Action Document to be quality assessed, and (often) to a financing decision.
Implementation – Mobilising the resources (budget, HR etc.) and executing the action, including monitoring of progress
Closure & follow up – Assessing project results and drawing lessons for the future

## Slide 11
The project cycle is not linear and not static
All steps are closely interlinked

## Slide 12
Budget Support
(BS)
PROJECT MODALITY
(PM)
Box 7: aid modalities and their categories
Two aid modalities
See also: training on budget support
The aid modality is selected during programming and/or identification and decided upon during formulation.
Both types have common features:
Context analysis
Risk analysis (partially)
Lessons learned
Policy dialogue
(support to) Capacity Development
Results
-> only one Action Document template for both aid modalities
Note: some categories:
For BS: Good Governance and Dvp Contracts
State Building Contracts
Sector Reform Contract
For PM: to be defined in new guidelines, tentatively:
Sector Support Programmes
Projects

## Slide 13: The LFA to preparing projects and programmes
Partner's Strategy/programmes
Priority areas for support/problem analysis
Analysis of the context
Public policy
Stakeholders
(elements of Political Economy)
Lessons learned
Risks and assumptions
LOGICAL FRAMEWORK APPROACH
INTERVENTION LOGIC (IL)
What outcomes are sought, for whom and why, what has been done before in this field to build on, how change might happen, over what period of time, based on what assumptions? How will we measure progress and evaluate achievements? What learning indicators do we need, what are the risks?
LOGICAL FRAMEWORK MATRIX (LFM)
A tool that can be used for planning an action, and for monitoring and results reporting
Gender
Environment+CC
RBA
Complementarity, value added, synergy and donor coordination

## Slide 14: The Logical Framework Approach
Challenge:
Is to convert ideas and questions into a realistic, manageable action!
LOGICAL FRAMEWORK APPROACH
Not a simple, linear, solitary task
Key concepts that we will develop further:
FACILITATION
PARTICIPATION
ITERATIVE
CONTEXT SENSITIVITY
ASSUMPTIONS
REACH (who benefits? what do we control?)

## Slide 15: The LFA goes beyond planning
EVALUATION
MONITORING
IMPLEMENTATION
The IL and LFM should be adapted to take account of possible changes in the context
The LFM is an essential reporting tool
The LFM provides the basis for scheduling activities and resources
The LFM provides a good summary of the action and therefore helps communication among stakeholders (dialogue)
The LFM in particular will be crucial for the monitoring on results
The IL and LFM will facilitate evaluation in terms of relevance, efficiency, effectiveness, impact and sustainability and will allow lessons to be drawn (what went wrong or well? Why? Are there conclusions relevant to other similar actions? etc…)
Notes: 1/5/2016
PCM/ECOFIN Course - Brussels - October 28-31 2008
15

## Slide 16: The Action Document is structured around the LFA
There is a progressive approach from programming through to formulation with a corresponding shift in focus:
During programming, the choice of sectors and related indicators is based on partner’s plans, EU policies and relationship with the partner, and EU values;
During identification the focus is on context analyses (for each sector), risks, assumptions, lessons learned, complementarity, cross cutting issues and outcome(s).
During formulation, the focus is on the IL, LFM (or indicative list of result indicators for BS) and implementing arrangements.
What does the AD formally request?
  All the elements needed for a sound IL (i.e. analyses, etc..)
  The Logical Framework Matrix for project modality (or the indicative list of result indicators for Budget Support)
  The Intervention Logic summarized in a short narrative

## Slide 17: Key messages
The LFA is DEVCO’s chosen method for project planning and management: this method combines a critical thinking process (Intervention Logic - IL) and tool: the Logical Framework Matrix – LFM)
A robust LFA can identify possible pitfalls, help to avoid failures and allow corrective measures to be taken in a timely manner
The LFA (IL and LFM) are flexible (not a straight jacket)
The LFA can be challenging (it deals with the real complex world, it requires thinking outside of the box etc.) but it can be very rewarding.