## Slide 1: Session 3
Linking analyses
and change processes

## Slide 2
LFA tools
for the analysis of problems and objectives

## Slide 3: The LFA is an iterative process
Complementarity with other actions
Context analysis
(PPA, SA, elements of PEA)
Possible area for support
Capacity assessment
Assessment of Risks and Assumptions
mitigation measures
Lessons learned from other actions ("evidence", good practices etc.)
Cross cutting issues
Progressively building the Intervention logic

## Slide 4: The problem-objective tree method
Simple and useful
cause
cause
cause
cause
effect
effect
problem
output
output
output
output
outcome
outcome
impact
2° From "-" to "+"
----------------
3° Selecting the strategy
-----------------------
1° cause-effect
relationship
----------------
This planning method can easily produce a results chain and ultimately a logical framework matrix but :
1° It is not the only planning method
2° It is crucial to take into account the assumptions and the evidence that will lead from the outputs to outcome(s) and finally to impact, in other words, the intervention logic

## Slide 5: Problem tree: steps
What is a problem tree?
The problem tree is an LFA tool that establishes cause and effect relationships to ensure that root problems are identified and then addressed.
Main steps:
  Identify one or two (initial) major problem(s) affecting the target group/beneficiaries
  Identify related problems/constraints
  Analyse and identify cause and effect relationships and create a draft problem tree
  Check the logic of causality

## Slide 6: Problem tree: simplified example
EFFECTS
CAUSES
The problem tree
helps to understand the cause/ effect relationship between problems
Depletion of the natural fish stock
Low selling prices obtained in the villages
Income of traditional fishermen in decline
Destruction of natural habitats and mangroves
Illegal fishing practices
Poor quality of processed fish
Limited access to markets
The development of a problem tree will often be skipped when working on sector support actions (cf session 4)

## Slide 7: Top tips for problem trees
1 problem per box
A problem is not the absence of a solution. The solution is the project, but it is not determined at this stage
Statements should be clear and specific
The way the tree is presented should be easy to read and it should be possible to grasp the structure instantly
The product of the exercise (the problem tree) should provide a robust but simplified version of reality. Not too complicated, not too simple

## Slide 8: Objective tree: simplified example
ENDS
MEANS
The objective tree
converts problems into positive achievements by establishing means/ends relationships
Depletion of the natural fish stock reduced
Selling price obtained in villages increased
Income of traditional fishermen increased
Natural habitats and mangroves better protected
Illegal fishing practices significantly reduced
Processing of the catch improved
Improved access to markets
An objective tree
is not a summary of the action
it is a structured mapping of possible diverse objectives with different pathways
Notes: 11

## Slide 9: Top tips for objective trees
  Beware of unrealistic objectives
  Beware of natural factors that cannot be changed
  Check the logic of causality… The objectives at a level below should be necessary and sufficient to achieve the objective on the next level up
  A project is a process of change towards a more satisfying situation… the wording should reflect this gradual nature
The development of a problem tree and its conversion into an objective tree can be replaced by other processes working directly on developing the intervention logic (cf session 4)
Notes: 11

## Slide 10: Key Messages
The working process in the identification and formulation phases is highly iterative/repetitive. Going back to a previous stage of questioning or analysis is often necessary. In fact, as the context evolves, the programme or project will most likely have to adapt during implementation.
It is nonetheless a gradual process: in particular, the definition of the priority areas for support allows us to focus more and more on the change process and therefore to address with more accuracy some topics (risks, lessons learned, etc.) that are already part of - and will nourish - the intervention logic.
The problem-objective tree method is useful in order to determine the results chain from the analyses and therefore to build the logical framework matrix but it must be subjected to critical thinking: in particular the passage from one level to another (output to outcome(s) and outcome(s) to impact) has to be thoroughly assessed and coherent with the intervention logic (mini steps, pathways of change, assumptions, evidence)
Notes: 11