## Slide 1: Session 5
Building an Intervention Logic

## Slide 2: What makes us think the change we desire will really happen?
This question is central to meeting our « result orientation » and consequently it must be addressed in the (new) way we consider the LFA; it means in particular that we must focus on the key assumptions we are making and the evidence which underpins those assumptions.
The practitioners (e.g. evaluation specialists) refer to this adaptation of the LFA as the "theory of change" as an enhanced exploration and understanding of the intervention logic.
Through the LFA we need to place much more emphasis on analysing the change processes which need to take place in order to deliver the desired goal…

## Slide 3: What is an intervention logic?
identifies the changes we (key stakeholders) want to help bring about, in a given context, as we understand them at a given point in time, and demonstrates how we think the associated change processes might happen, why, and on the basis of what evidence, and the quality of that evidence.
The IL comprises two elements:
An intervention logic …
‘theory of change’
i.e. why & how change might happen (broader)
‘theory of action’
i.e. what steps need to be taken to achieve the results we seek (=LFM)

## Slide 4: Intervention logic – both a thinking process and a product
A ‘thinking process’ which helps us design/ reconsider/ adapt what we do – i.e. a process for thinking about how the desired change might be achieved, it generates ideas on how to intervene to bring about that change, it explores and weighs up different causal pathways and operational options
A ‘product’ – which describes the intended pathway of an action and explains why this has been selected. Product having 2 shapes:
‘Narrative’
Explains how change will unfold using evidence/ value data
‘Diagram ’
Schematises the many pathways of change

## Slide 5: The intervention logic process in design
Within this process, the stakeholder group needs to address the following key components:
Analysis of context, particular issue (s) and change(s) to be brought about
Exploration of change processes and underlying assumptions
Assessment of the evidence
Analysis of
context + issue(s)
Exploration of change processes and underlying assumptions
Assessment of the evidence

## Slide 6
How to identify the priority areas
for support (our strategy)?

## Slide 7: Strategy analysis and context analysis
Strategy?
Fit with partner’s policy and programme priorities
Contribution to the reduction of poverty and inequalities (e.g. gender)
Complementarities with other programmes or projects
Availability of financial resources, expertise, etc.
Institutional capacities of partner/ implementing agencies
Urgency
Economic and financial costs and benefits
Context, risks & assumptions
In any case, the choice is rooted in the context analysis
ADDED VALUE
LESSONS LEARNED

## Slide 8: Strategy analysis
  Consists of:
  Analysing identified potential objectives (=potential results of a change process – ideally the partner’s objectives) in relation to a set of ‘feasibility’ and ‘policy priority’ criteria;
  Assessing the costs and benefits of different potential approaches (possible tool: matrix of criteria)
  Choosing an appropriate strategy
In LFA jargon: strategy = group of consistent objectives
i.e. in an objective tree or in a ToC diagram, there are many different possible strategies

## Slide 9: Strategy analysis & objective tree
Fish stock control strategy
Market orientation strategy
OUTCOME / SPECIFIC OBJECTIVE
IMPACT / OVERALL OBJECTIVE
OUTPUTS
These excluded statements should be considered in the analysis of assumptions/risks
In the project
Out of the project
Depletion of the natural fish stock reduced
Selling price obtained in villages increased
Income of traditional fishermen increased
Natural habitats and mangroves better protected
Illegal fishing practices significantly reduced
Processing of the catch improved
Improved access to market
Besides an in/out visualisation, a « russian doll » one can be developed, compatible with the nested LFM (see later chapter & hand out)

## Slide 10: Strategy analysis and the theory of action
The selection of a strategy will lead to the development of a “Theory of Action”
The theory of action:
Identifies the key elements of our results chain
Shows how planned outputs will lead to planned outcomes and planned outcomes to the overall objective… It is a linear representation of the proposed change process.

## Slide 11
Political processes: contestation and negotiation of power, wealth and goods
Economic and financial processes, and their links with politics
Formal and informal institutions
Relations, incentives and interests of actors « under the surface »
Why do reforms fail to take root?
Need for a systemic approach with a specific focus on:
The visible world: national strategies, action plans, formal institutional structures etc.
Don’t forget the hidden part of the iceberg…
Revealing interests of stakeholders is part of the process

## Slide 12
Factoring in change processes

## Slide 13: Change process for the overall action
-Make explicit the core overall change process for the action
- What are the common types of change processes ?
e.g. empowerment, capacity building, constituency building, educative, instructive, enforcement, dissemination, knowledge transfer, imitation, diplomacy (negotiation, mediation, lobbying)…

## Slide 14: LFM Example
Let’s look at the PIZZA LFM example and see if we can build in the change processes
exercicse

## Slide 15
Pathway of change
Input
Output
Specific Impact
Impact
Activities
Improved technical quality and use of evaluations
Assumptions / risks
from specific impact to impact
Assumptions / risks
from outputs to outcomes
Assumptions / risks
from inputs/activities to outputs
Evaluation culture and capacities are enhanced within DEVCO
Evaluation is seen as a learning and necessary aspect of the EU development toolkit
Enhanced dissemination of evaluation findings across delegations
Start-up & Pilot
Design the concept
Establish member-ship
Test & adjust offer
Network members identified & clear role established
Management and technical aspects of the network in place and functioning
Newsletter produced regularly
Reference material available
Improvement of evaluation understanding, skills and process within delegations and units through the evaluation correspondents
Feedback mechanisms established
On-Going
Newsletter & material posting
Feedback and reporting mechanisms
Content/materials:
appropriate articles (from internal and external sources)
IT system
C4D group
Evaluation Unit Staff Time and Skills :
Network coordinators
Eval. Unit staff providing information
Outcome
Improved communication on evaluation practice & findings among the evaluation corresp.
Improved evaluation skills of evaluation correspondents
Interaction between moderator-corresp. & corresp.-corresp. happening
Assumptions / risks
from outcomes to specific impact
.
Improved credibility of ev. correspondents within their unit/del.
Evaluation Network
Intervention Logic
Development of sense of evaluation community of practice amongst corresp.
Transformatory change processes i.e. which turns one step of the action into the next

## Slide 16: Key messages
Choice of strategy is rooted in context analysis
Lessons learned, complementarity, coordination and added value should always inform choice of strategy
An intervention logic comprises a theory of action and a theory of change
The theory of action will only tell us what change is planned, not how that change will happen
We need to understand the pathways of change and identify the assumptions underpinning those change processes and the quality of evidence supporting them.
Notes: 16