## Slide 1: Session 9
Recap on LFM and IL

## Slide 2
How to check the internal logic of a LFM

## Slide 3: Vertical Logic
Results Chain
Indicators, baselines & targets
Sources & means of verification
Assumptions
« For each level of the intervention logic, if “results” are achieved and assumptions hold true, then ... »
Outputs
Outcome
Impact
Activities
Notes: 13

## Slide 4: The intervention logic
A detailed and clear vertical logic is required by the action document (§4.3 “ Intervention Logic”)
by articulating the Logframe’s first column (Results chain) and the Logframe’s last column (assumptions) into a structured narrative that explains how and why the action will bring about change.
Results-based management requires the intervention logic to be regularly questioned
By regularly thinking through the extent to which the implemented activities and outputs have a reasonable probability of attaining the desired results, and by making continuous adjustments as needed to ensure that they are achieved.
in design AND management
Notes: 4

## Slide 5: Horizontal logic
Results chain
Indicators, baseline & targets
Sources & means of verification
Assumptions
Outputs
Outcomes
Impact
How to verify ‘success’ in achieving objectives
Activities

## Slide 6: Indicators, what for?
  Indicators:
  Specify how success/performance can be assessed and measured
  Support decision making (but do not replace it!); monitoring and evaluation for tracking progress and improving the quality of operations

## Slide 7
Check carefully the consistency between objectives, indicators and sources of verification
Sources of verification should be identified when selecting an indicator. This source is not neutral in terms of time, money and skills required. A cost-benefit assessment is necessary when designing a performance measurement framework.
Sources & means of verification
in the LFM