## Slide 1: Session 10
Indicators (I)
Indicators, baselines, targets & milestones

## Slide 2: In a logframe every result needs
Indicators
What is to be measured (not what is to be achieved; that’s the job of targets)
Targets
The desired value or direction for progress
Milestones
On the path towards your target
Baselines
Sources
The starting point
Crucial for target setting
Where the information/data comes from

## Slide 3
Indicators and Objectives

## Slide 4: Linking indicators to development objectives
More than one indicator is sometimes needed (or required) to cover the scope of development objectives.
Nevertheless: It is necessary to clearly link indicators with each related objective to assess the relevance of the indicators chosen
(cf chap 2.1 guide on « Performance measurement… »)

## Slide 5: Defining indicators – Focus on what will be measured not by how much
Impact
Long term goal to which the project contributes
e.g. MDG/SDG indicators, EURF level one, health improvement, poverty reduction, economic development
Outcome
What will change for the beneficiaries/target groups – behaviour/ perceptions/ systems
Output
The services or facilities delivered to the target groups
e.g. # of water points constructed
e.g. # of people using improved water sources
Notes: An indicator is not the same as a target.. A lot of people confuse the two… Get participants to give an example of a target for each of these indicators.. When defining indicators make sure the corresponding data is reliable and that it can be collected. Ask participants what other factors should be taken account of when defining an indicator ie what makes for a good indicator. Then move to next slide.
Go to page 83 of PCM guidelines. Before, you had to include indicator, quantity, quality and timeline. Now, indicator is in one column, then baseline, target and SoV.

## Slide 6: Good indicators depend on clearly stated objectives/results on all levels: Outcome level
Not so good 
Good 
National Malaria response is improved
An intermediate outcome – not the most important
Adoption of malaria prevention practices by target group
The main strategic objective
Clear about behavioural change

## Slide 7: Good & not so good objective/result statements: Output level
Not so good  Good 
More people use mosquito nets when sleeping particularly babies who are at higher risk during the rainy season
Too long & not clear
Wrong level – use of mosquito net is an outcome
Increasing availability, access to and promotion of mosquito nets by target group
Succinct and clear
Right level – availability of mosquito nets is an output

## Slide 8: Defining clear results
SMART results
Specific, Measurable, Achievable, Relevant, Timebound

## Slide 9: What makes a good indicator?
Specific – what will be measured?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Can be disaggregated if necessary
Good mix of qualitative and quantitative
Already defined e.g. MDGs or other internationally agreed indicators

## Slide 10: Examples of good & not so good indicators Objectives or indicators?
Not so good 
Better
Increased primary enrolment
Court systems providing effective access to citizens
Strengthened capacity of parliament
Net primary enrolment rate per annum
Percentage of citizens who say that they have access to court systems to resolve disputes
Public perception of parliamentary effectiveness

## Slide 11: The use of proxy-indicators
Using only existing or easy to collect indicators (among which proxies)
easier to manage
but do not always reflect the exact objective of the operation
Keeping the most theory-compliant indicators
difficult to deal with (target setting, data collection)
but help to keep in mind what the ultimate goal of the operation is
Between these two options, an indicator should at least be:
Relevant (linked unambiguously to a policy/strategy/action/objective)
Accepted (by all stakeholders)
Credible
Easy (to monitor and measure regularly)
Robust (using a stable methodology)

## Slide 12: Individual Exercise
Are these indicators more likely related to outputs, outcomes or impacts?
% of births attended by skilled health professionals
Number of CSOs trained
% growth rate in agricultural output
% of homes sprayed with insecticide
Number of additional women using family planning
% of the population vulnerable to food insecurity
Number of active tax payers
% of the population below the national poverty line
exercicse

## Slide 13: Top tips for indicators
The selection of each indicator should be based on the availability of data and its relevance to the objective/result
Don’t pick too many indicators for each result – choose the most important or strategic ones
Choose & develop indicators with partners – agree data collection responsibilities, including frequency
Involve (final) beneficiaries in choice of relevant indicators
Be clear on whether they are annual, cumulative etc.

## Slide 14
Baselines, targets and milestones

## Slide 15: How to measure change?
Step 1
Set the baseline
Step 2
Set the target
Step 3
Set milestones

## Slide 16: What is a baseline?
A baseline is a measure of the situation before the action starts (could be zero if a new action)
It is used to measure change and monitor progress
All indicators must have a baseline before the start of the action (or should state when it will become available)
Use existing data where possible, but check reliability
If you need to collect your own data; collect baseline data early i.e. as soon as beneficiaries have been identified

## Slide 17: Top tips with baselines
Good in theory – often weak in practice
Requires a minimum level of information (can imply complexity & costs)
Look to existing sources first
Costs/benefits of different options for collecting information
Inception phase often the most appropriate time to complete or refine baselines (budget/resources required)
A lot of difficulties that arise in the course of a project/programme are not foreseen because there is:
  No baseline and no estimation of past and present trends
  No real preparation of the monitoring and evaluation system

## Slide 18: What is a target?
A target is the desired end point for each indicator. It is often planned to be achieved in the last year of a project
Must be included where baseline data is available
Disaggregated where relevant e.g. by sex/ geography/ income
Should be time specific (i.e. clear when the target is expected to be met)

## Slide 19: Indicators & targets: examples
Indicator
(variable)
Number of service delivery points (SDPs) per population of reproductive age in each priority district where a package of at least three types of clinical services and related information and counselling activities are offered.
Target
(Value)
500 SDPs/1.5 million population of reproductive age in the three districts of (names) offer Maternal Health and preventive and curative services as well as related interpersonal counselling, group communication activities and information materials by 2006.
Example from the Monitoring and Evaluation toolkit for programme managers, FNUAP
The further you are in the chain of results on the side of effects and impacts, the higher the probability that targets are reformulated during project implementation.

## Slide 20: How to set a target?
To set a target, one should:
Have a reference value (baseline)
Assume a rhythm of progression
Give an exit value (target) in consequence of the two previous points
Be careful!
The baseline value must be sound: reflecting previous situations/progressions if relevant
Rhythms of progression are often calculated starting from target level (ex MDGs), that are often more a declaration of a political ambition
(Cf chap 2.6 guide on « Performance measurement… »)

## Slide 21: Top tips for targets
Can be a powerful tool (what gets measured gets managed) - but need to be treated with some caution
SMART approach remains valid for setting good targets
Where possible – specify quantity, quality, time (QQT)
Be realistic
Involve the right people in their selection (don’t impose)
Review targets on a regular basis
Provide incentives to report honestly (don’t shoot the messenger!)

## Slide 22: What are milestones?
Milestones…
are points along the desired trajectory from baseline to target;
will help to track progress and make timely changes to address under-performing areas;
should be annual at the output level (at the outcome level data may not be available annually).

## Slide 23: Top tips for milestones
Be REALISTIC when setting milestones (given resources and capacity).
Go back to your intervention logic to look at the pathway of change and the many steps necessary to achieve the project/programme outcomes. In these ministeps you will find the milestones.
Milestones can be identified from the intermediary outcomes of your intervention logic. The graphic representation of the intervention logic and the objective tree can help you.
To quantify your milestone values, adopt the same attitude as for target setting: make projections using a realistic rythm of progression (see further exercise on methods of comparisons).

## Slide 24: Targets & baselines - Key messages
Be realistic with targets. Expected levels of performance should be quantified and documented against reality and experience of what is feasible.
If baseline information is weak in formulation phase, baseline assessment and target setting should be planned in the inception phase of the project/programme.
Notes: 24